## Pivot
Category | (All)
Sum of Estimates - Incl. Testing (PDs) | Column Labels
Row Labels | Vital | Vital? | Grand Total
Admin | 421.75 |  | 421.75
Admin portal
API | 4 |  | 4
Audit | 6 |  | 6
Auth Service
BI
Client | 100 |  | 100
Data protection
General | 10 |  | 10
ID-Authentication | 332 |  | 332
ID-Authentication/Core Team | 0 |  | 0
ID-Repository | 41 |  | 41
Kernel | 41 | 5 | 46
Partner Management | 333.45 |  | 333.45
Pre-registration | 276.25 |  | 276.25
Pre-registration/Reg. Client
Reg. Client, Reg. Processor, IDA | 0 |  | 0
Registration Client | 1196 |  | 1196
Registration Processor | 554 | 16 | 570
Reporting
Resident portal
Resident Services | 54 |  | 54
Security Integration
Server | 71 |  | 71
Testing
UIN Recovery Service
Grand Total | 3440.45 | 21 | 3461.45

## Consolidated
MOSIP - Consolidated Roadmap post 30Jun
S.No. | Module/Area | Feature | Category | JIRA IDs | Description | Priority | Estimates - Incl. Testing (PDs) For items that need estimates from multiple modules, please provide estimate in module specific column | Estimates - Kernel | Estimates - Admin | Estimates - Pre-registration | Estimates - Registration client | Estimates - Registration Processor | Estimates - ID Authentication | Estimates - ID Repository | Estimates - Partner Management | Estimates - Resident Services | Comments
1 | General | Refactoring of MOSIP repository | Additional |  | 1. Aligning current MOSIP git repository to the open source one 2. Others if any | Vital | 10 |  |  |  |  | 10
2 | Reg. Client, Reg. Processor, IDA | Real Biometrics Release | To be deleted | IDA: Estimates covered as part of - MOS-22416, MOS-21758, MOS-18214, MOS-12073, MOS-12072, MOS-10831, MOS-10308, MOS-1150 Reg Client & Processor:Effort has been covered in the below individual module list | 1. Integrating with Reg. devices (Iris, FP,Face) 2. Auth devices (Iris,FP,Face) 3. ABIS - One ABIS, multi-modal | Vital | 0
3 | Registration Processor & IDA | Face ABIS & Auth | Real Biometrics |  | TBD - What should the plan be, discussion with Vivek and its tangible impact for us to do | Desirable
4 | Registration Processor | Automated check by system to identify photo/age/gender matchness, other validations to reject packets at an early stage based on automated checks |  |  | QC module | Desirable | [10 empty] | SI customization
5 | Registration Processor | Manual Adjudication System |  |  | Manual Adjudication System/framework - For QC results verification, biometrics duplicate verification, others to be identified | Desirable | [10 empty] | SI customization
6 | General | Fraud & Data Analytics |  |  |  | Desirable | [10 empty] | SI customization
7 | General | External Integration - Open CRVS / SIA etc |  |  |  | Desirable | [10 empty] | Community contribution
8 | General | Features which can be considered if there is Usecase / demand |  |  |  | NA
9 | General | Role of Block Chain in MOSIP (where, how) |  |  |  | NA | [10 empty] | Community contribution
10 | Pre-registration/Reg. Client | Configurable UI for Pre-reg. & Reg. Client | Need clarity for estimating | Need clarity for estimating |  | Vital
11 | Resident Services | Reference UI portal for resident services |  |  |  | Desirable | [10 empty] | Community contribution
12 | Registration Client | Make Reg client - a browser based (with local server) solution (moving away from heavy client) |  | Needs to be estimated | Ramesh can explain more | NA | [10 empty] | Community contribution
13 | Registration Client | Installable Dongle for Reg Client. |  | Needs to be estimated |  | NA | [10 empty] | Community contribution
14 | Testing | Device Ecosystem testing & certification Target |  | Testing team to provide effort |  | NA | [10 empty] | Community contribution
15 | Testing | Performance testing | Additional |  |  | Vital
16 | Testing | Security testing | Additional |  |  | Vital
17 | ID-Authentication | Separating ID Repo and ID Auth modules…. i.e., exporting ID data to ID Auth |  |  |  | Essential? | [10 empty] | Subject to bandwidth
18 | Reporting | Basic system reporting | Need clarity for estimating | Need clarity for estimating | System health monitoring reports | Vital
19 | Admin | Integrating all modules with the KeyCloak implementation for authentication and authorization |  |  |  | Vital | 4 |  | 4
20 | IDA/Resident Services | Offline Verification - QR code with Photo | Additional |  | MOSIP to have the ability to consume UIN/VID as input, authenticate the individual with OTP and further generate a document with digitally signed QR code bearing demographic data [Name, Address, Photo, Gender, DOB, registered Phone Number (hashed) and registered Email Address (hashed)] | Vital? | 8 | [9 empty] | Subject to bandwidth
21 | ID-Authentication | SPR Seeding for Morocco (HoH requirement) |  |  |  | Essential
22 | ? | Device registration - API, Integration with Management server from biometric device vendor |  |  |  | Desirable
23 | Registration Client | Registration client sync without running instance or login |  | Needs to be estimated |  | Desirable
24 | General | Audit Logging for Product Management Directives |  |  |  | Essential?
25 | ID-Authentication | eKYC Auth - Reference App |  |  | eKYC Auth Reference App for Partners | Desirable
26 | Registration Client | Online registration |  |  |  | NA
27 | Resident Services | Mosip Resident Services - Reference App |  |  |  | NA
28 | ID-Authentication | Offline Auth Verification App |  |  |  | NA
29 | General | Browser Support - Support IE |  |  |  | Essential? | [10 empty] | Krishnan to determine
30 | Testing | Testing: UTC check in APIs, audit and DB entries - Pre-reg, Reg. Client, Reg. Processor, IDA | Pending work |  | UTC check in APIs, audit and DB entries - Pre-reg, Reg. Client, Reg. Processor, IDA | Vital | 50 | [9 empty] | Pending testing activities - From Gita
31 | Testing | Testing: Audit log checks - Reg. Client, Reg. Processor | Pending work |  | Audit log checks - Reg. Client, Reg. Processor | Vital | 20 | [9 empty] | Pending testing activities - From Gita
32 | Registration Client | Upload Portal for Registration packets | Additional |  | Includes disabling "Save to Device" option until the upload portal is provided | Vital | 100 | [9 empty] | Web application to upload packets
33 | Pre-registration | UX Enhancement - MOSIP | UX Enhancements | MOS-26253, MOS-20300, MOS-25102 | UX enhancements to fix padding, alignment, header/footer, refinement of Demographic page, revised approach for Appointment booking & document upload, enhanced UX across all pages | Vital | 260.25
34 | Pre-registration | UX Enhancement - GoM | UX Enhancements | MOS-14511 | To accomodate the Location Hierarchy changes as a part of the Demographic form, as per GoM requirement | Vital | 10 | [9 empty] | Desirable, To be decided after GoM interactions
35 | Pre-registration | Removal of Applicant Type |  | MOS-22039 | Currently, documents required to be updated depend on the Applicant Type/Doc Category/Doc Type mapping setup by the admin. This story intends to remove this concept and adopt the process as per Reg. Client (Docs required to be uploaded are driven by fields filled) | Desirable
36 | Pre-registration | Blacklisted Words Validation |  | MOS-19541 | Inclusion of blacklisted words validation in both languages for Name and Address fields L1,L2,L3 fields of Demo form: On entry of a Blacklisted word the Individual should be alerted “XXX word(s) are not permitted in the ABC field by the system. Please correct it”. | Desirable
37 | Pre-registration | Configurability of Features |  | MOS-15474 | Ability to switch on/off a feature | Desirable | [10 empty] | Architects to further discuss
38 | Pre-registration | OCR for Document quality check |  | MOS-13147 | Perform OCR validation on docs uploaded, to evaluate Doc quality, validate data of doc | Desirable | [10 empty] | Community contribution
39 | Pre-registration | Group Concept |  | MOS-13133 | Include ability to make a group booking, by providing the total number of members in group | NA
40 | Pre-registration | Reminders to Applicant |  | MOS-13059 | Trigger reminder(s) to an individual, prior to the booked appointment | Desirable | [10 empty] | Community contribution
41 | Pre-registration | Login - With Username & Password |  | MOS-790, MOS-621 | Ability to login with Username & Password Currently - Login is possible only with Mobile/Email id - API/UI | NA | [10 empty] | Community contribution
42 | Pre-registration | Password Management |  | MOS-791, MOS-622 | Ability to reset password/manage profile - API/UI | NA | [10 empty] | Community contribution
43 | Pre-registration | Login - Include Captcha | Additional | MOS-25103 | To accommodate captcha feature on Login page | Vital | 6
44 | Pre-registration | Application Status Enhancement |  | MOS-19858 | This story is to accommodate change to the various statuses of Pre-registration - To be relevant to its own stage.EG: If docs and/or demo data is updated, the status is still Pending Appointment. Instead, the suggestion was to update it relevant to its respective stage, i.e., Demo Data Updated/Docs Uploaded - To be discussed and evaluated | NA
45 | Registration Client | Age/DoB Calculation Display | Additional | MOS-21861 | New Registration - Age/Date of Birth:If we enter age, the DoB should display 01/Jan/xxxx. If we enter DoB, the age should be auto calculated and displayed. Both fields should remain editable. | Vital | 6
46 | Registration Client | Parent/Guardian Authentication - Multi factor |  | MOS-1175, MOS-1320 | To authenticate each introducer based registration with their password/biometrics/multi factor elements. | NA
47 | Registration Client | Biometric Capture - Device Manager Implementation | To be deleted | MOS-23070 | VDM technical specification to be adhered by the vendor to adopt their devices to the MOSIP platform to capture the biometric data and manipulate the same. | Vital | 0 | [9 empty] | Will be taken care by vendor, hence no estimate provided
48 | Registration Client | Biometric Capture - Device Service Integration | Real Biometrics | MOS-22410 | MOSIP device manager integration - 3rd party integration. | Vital | 40 | [9 empty] | 15 PDS for development
49 | Registration Client | Biometric Capture - Photo Validations & ICAO Standards check |  | MOS-23544, MOS-16008, MOS-13522 | 1. Implement additional validations of the photo: Liveness check, photo of a passport photo 2. Implement ICAO validations that are not implemented in MOS‌-16008: - Plain light-coloured background - Close up of the head and top of the shoulders so that the face takes up 70–80% of the photograph 3. Provide ability to capture live photo (Maybe a short video instead of a photo) | NA | [10 empty] | > Community contribution - What pluggability should we provide? > Based on MDS implementation
50 | Registration Client | Biometric Exceptions - Capture multiple docs/photos per exception type |  | MOS-19011 | Capture Biometrics Exception Photo: 1. Provide ability to capture multiple photos based on each reason and for example, one photo for fingerprint and one photo for iris exception – Either refer or capture different photo for each exception 2. Provide ability to upload documents to support each exception | Desirable
51 | Registration Client | Biometric Exceptions - Manually mark exception for low biometrics quality |  | MOS-15999 | Device story for marking low quality biometrics as exceptions | NA
52 | Registration Client | Biometrics exception approval - Configuration if approval is required at one/two levels |  | MOS-13523 | In case of biometric exceptions, provide ability to configure if operator authentication is required at multiple levels | NA
53 | Registration Client | Device/SDK Integration - Biometrics - Fingerprint quality ranking | Real Biometrics | MOS-12187, MOS-1291 | Device story for providing ranking by fingerprint quality in the registration receipt Device story for capturing an individual's fingerprints as per quality threshold values defined. | Essential? | [10 empty] | Subject to bandwidth
54 | Registration Client | Device/SDK Integration - Capture Parent's biometric for Child | Real Biometrics | MOS-21701 | If age of the applicant is less than or equal to 5, capture any one biometric-fingerprint, IRIS of the parent/guardian. It could be any Parent/guardian – Same Parent/guardian as during registration or another Parent/guardian) | Vital | 40 | [9 empty] | 20 - all bio type integration.
55 | Registration Client | Device/SDK Integration - Login with Iris/Face | Real Biometrics | MOS-12185 | During Login, multifactor authentication using username + password and/or OTP, fingerprint, iris. | Vital | 40 | [9 empty] | 20 PDS for development
56 | Registration Client | Device/SDK Integration - Scan PRID QR Code | Real Biometrics | MOS-13556 | While starting a new registration, the registration client should support scanning a QR code to populate the pre-registration ID on screen | Vital | 60 | [9 empty] | kernel + device dependencies
57 | Registration Client | Device/SDK Integration - Iris capture | Real Biometrics | MOS-1205 | Device--As the MOSIP registration client, I should enable iris capture as per defined specifications. | Vital | 70
58 | Registration Client | Device/SDK Integration - Lost UIN | Real Biometrics | MOS-18989 | Device story for lost UIN | Vital | 48
59 | Registration Client | Device/SDK Integration - UIN Update | Real Biometrics | MOS-15998 | Device story for UIN update | Vital | 24
60 | Registration Client | Device/SDK Integration - Registration Officer and Supervisor Onboarding | Real Biometrics | MOS-19001, MOS-22161 MOS-22005 | Device Integration for below features: 1. Enable capturing an officer's biometrics during onboarding in order to support login, local duplicate checks and registration submission 2. Operator On-boarding - Biometrics capture - Validate quality before authentication - The exception photo should not be captured | Vital | 54
61 | Registration Client | Device/SDK Integration - Registration Officer authentication | Real Biometrics | MOS-1334 | Enable RO to authenticate each registration with biometrics/multi factor elements | Vital | 60
62 | Registration Client | Device/SDK Integration - UIN update-Scan QR code | Real Biometrics | MOS-19014 | UIN Update: i. Provide ability to scan QR code besides manually entering UIN number - New requirement ii. Additionally, pre-populate data from QR code (if available), based on option selected for update (EG: If address is marked for update, then address to be pre-populated from QR code). Implementation aspects to be discussed - New requirement iii. Evaluate if CNIE/UIN/EC Number Update is required, as if the number captured is incorrect, packet processing would have failed | Desirable
63 | Registration Client | Device/SDK Integration - Local duplicate check for iris and face | Real Biometrics | MOS-10555 | Perform a local duplicate check for irises and face of an individual against the mapped registration officers' biometrics | Vital | 40
64 | Registration Client | Stubbed/MDS Implementation - Display device status |  | MOS-15996 | This is the proxy (stubbed) implementation of MOS‌-13562 to display the device statuses on the client as green/red indicators in the header. | Essential | [10 empty] | If MDS is implemented, this will be implied
65 | Registration Client | Validation Checklist - Ability to validate each field/stage of registration/Update (EG: DoB Verification) |  | MOS-14566 | Mark an individual’s date of birth as ‘Verified’ during new registration or UIN update. | NA | [10 empty] | Community contribution
66 | Registration Client |  |  | MOS-14565 | Mark an individual’s date of birth as ‘Verified’ during new registration or UIN update. | NA | [10 empty] | Community contribution
67 | Registration Client | Introducer attestation (Introducer concept) |  | MOS-5482, MOS-1382 | Should enable uploading/scanning applicable documents of an introducer (Others) during registration of an individual. | Desirable | [10 empty] | This is already covered by virtue of having Parent/Guardian introducing a Child - MOSIP in any case doesn't maintain relationships
68 | Registration Client | Geo-location capture using phone |  | MOS-19006 | Geo-location Capture using GPS:1. Usage of phones for GPS vs. GPS on machine | Desirable | [10 empty] | Community contribution
69 | Registration Client | Location Hierarchy Update as per GoM | Additional | MOS-16544 | Reflect the new location hierarchy for Morocco | Vital | 40 | [9 empty] | Currently Desirable, Dicussion with GOM can change these.
70 | Registration Client | Login/Authentication - Token to authenticate RO |  | MOS-21523 | Registration Client should send a Token to Registration processor, when Officer or Supervisor authenticate themselves during Packet Creation | Desirable | [10 empty] | Community contribution
71 | Registration Client | Multi factor login - With Biometrics |  | MOS-8368 | Enforce multi factor login for Admin/Reg. users | Desirable
72 | Registration Client | OCR Document upload |  | MOS-12176 | MOSIP should support OCR as part of quality check of documents during document upload. | Desirable | [10 empty] | - Since this is a reference implementation, SI can implement as requried
73 | Registration Client | Operator onboarding - Training content | Additional | MOS-21998 | Operator On-boarding: The landing page should have a placeholder for training content. UX team to come up with the design. - Link on Login page/home page to the training content - Template based | Vital | 30
74 | Registration Client | Proof of consent document (GoP requirement) |  | MOS-18100 | As a Registration Officer, I should be able to capture Proof of Consent Document as required | Desirable | [10 empty] | SI implementation
75 | Registration Client | Reports |  | MOS-1309, MOS-1275 | Include statistics on EoD Approval and Re-registration only | Desirable | [10 empty] | SI implementation
76 | Registration Client | Supervisor's/an authorized user's ability to unlock a locked account - GoM requirement |  | MOS-12199 | Supervisor or Admin to unlock a user’s account that has been locked due to five consecutive unsuccessful login attempts. | Desirable | [10 empty] | Community contribution
77 | Registration Client | Transliteration in other languages |  | MOS-1288, MOS-1293 | Enable viewing transliterated data. - Other than French and Arabic | Desirable | [10 empty] | - Re-factor for pluggability - Move to UI - Standardize interface
78 | Registration Client | UIN update - VID input to initiate process |  | MOS-18319 | As a MOSIP registration client, I should support input of VID to initiate UIN Update | Essential? | [10 empty] | Subject to bandwidth - Reputational impact as per Anadi
79 | Registration Client | UIN update - OTP authentication of UIN holder in real-time (Online mode) |  | MOS-19739 | Support OTP authentication of the individual for UIN update | Desirable
80 | Registration Client | UX Enhancement- MOSIP | UX Enhancements | MOS-22011, MOS-22008, mos-22000, MOS-21924, MOS-22007, MOS-21923 MOS-21870, 21999, MOS-21997, MOS-21887, MOS-21888, MOS-21996, MOS-21926, MOS-21860, MOS-25101, MOS-25104, MOS-21922, MOS-21922, MOS021921, MOS-21863, MOS-21920, MOS-21897, MOS-21873, MOS-22013, MOS-26151, MOS-26779 | UX enhancements to fix padding, alignment, header/footer, refinement of Demographic page, revised approach for document upload, biometrics capture, enhanced UX across all pages | Vital | 644 | [9 empty] | Continue with UX VD enhancement track
81 | Registration Client | VID management |  | MOS-18483 | VID management - Reference Shrikant: - Ability to provide resident services features through Reg. Centre (Revoke VID etc) | Desirable
82 | Registration Client | Windows Installation script |  | MOS-22423 | Windows Installation Script for Registration Client Installation - Batch script | Desirable | 100
83 | Registration Client | Download pdf option |  | MOS-26354 | Able to download acknowledgement as a pdf using “Download pdf” button | Essential
84 | Registration Processor | Resident Services Dependency | Additional | MOS-24767, MOS-24108 MOS-24107, MOS-24106 MOS-24104, MOS-24943 | 1. Retriving a LOST UIN/RID when requested from Resident Services 2. Retriving a E-UIN Card using UIN/VID when requested from Resident Services 3. Retriving Status of Packet using RID when requested from Resident Services 4. Update Individual's Demographics when requested from Resident Services 5. Sending UIN Card for Printing using UIN when requested from Residnet Services 6. Reg Proc should be able to provide an external link so that Resident should be able to download a Password protected UIN card | Vital | 272 | [9 empty] | Refer Reg. Processor sheet for task breakdown
85 | Registration Processor | Admin Requirement | Additional | MOS-23848 - Refer Comments for effort inclusions | Send Transaction history of a Packet using RID when requested from Admin | Vital | 44 | [9 empty] | This service does not exist currently - To fetch complete history of a packet with RID. Efforts are appropriate
86 | Registration Processor | Enhancement - Password protected UIN |  | MOS-23306 | Send Password Protected UIN Card to Printing Queue. In Current implementation UIN Card is not password protected. | Essential | 12 | [9 empty] | Description updated - This was an internal observation from Security perspective - To password protect the pdfs sent to Print & postal queue. Refer Reg. Processor sheet for task breakdown
87 | Registration Processor | Bio-dedupe for Parent/Guardian instead of Auth |  | MOS-22034 | For Authentication of Introducer - Bio Dedupe could be used instead of IDA because Child registration would fail if Officer captures wrong UIN/RID of Introducer or Introducer UIN generation has failed. | Desirable
88 | Registration Processor | Token to authenticate Operator during packet creation |  | MOS-22032 | A Token can be used to Authenticate Officer and Supervisor in Registration Processor when they use OTP or Password based authentication in Reg Client when they create a Packet. | Desirable
89 | Registration Processor | On-Hold scenarios implementation |  | MOS-22030 | If a packet validation fails then instead of rejecting the packet registration processor should flag the packet and process it. Just before UIN allocation - these flaged packets should be verified by a manual intervention and UIN should get allocated based on the verifier's decision. | NA | [10 empty] | OK - Community contribution
90 | Registration Processor | GoM requirement - Update Request from External System: Combine Two Packets and Create a Third Packet - Perform Check Sum Validation | Additional | MOS-21755 | Reg Proc should be able to Merge two Packets and create a third packet. After merging the packet, reg proc should calculate the check of the merged packet using the check sum of the initial packets. | Vital | 110 | [9 empty] | Refer Reg. Processor sheet for task breakdown
91 | Registration Processor | SDK Integration - Minutiae extraction | Real Biometrics | MOS-17805 | Reg proc should be able to intergate with an actual device to extract minutiae of a Fingerprint Image File | Vital | 2 | [9 empty] | Refer Reg. Processor sheet for task breakdown
92 | Registration Processor | SDK Integration - Biometric quality score | Real Biometrics | MOS-17610 | Reg Proc should be able to integrate with an actual device to get the quality score of a biometric image file. | Vital | 2 | [9 empty] | Refer Reg. Processor sheet for task breakdown
93 | Registration Processor | Implement Finger Print Quality Checks to categorize FP as Real Finger, Finger of Same Person | Real Biometrics | MOS-8460 | Reg Proc should be able to integrate with SDKs that perform validations to check if captured biometrics is of a Real Finger and Finger of the Same person | Vital | 40 | [9 empty] | Need more clarity - Refer Reg. Processor sheet for details
94 | Registration Processor | SDK Integration - Photo/Age/Gender validation |  | MOS-1082 | Reg Proc should be able to integrate with a SDK to perform Photo/Age/Gender validations | Desirable | [10 empty] | SI customization
95 | Registration Processor | Implementing ABIS - One ABIS, multiple-modalities | Real Biometrics | MOS-26088 | Integrating with the ABIS Vendor who Supports Multiple Modalities i.e. Face, Finger and Iris | Vital | 84 | [9 empty] | Refer Reg. Processor sheet for task breakdown
96 | Registration Processor | Multi-partner ABIS - One ABIS per modality |  | MOS-1097 | Reg Proc should be able to integrate with Actual as well as multiple ABISs | Essential
97 | Registration Processor | Multiple ABIS with all modalities |  | MOS-26089 | Implementing Multiple ABIS with all modalities | Desirable
98 | Registration Processor | Auto-deactivation of UIN |  | MOS-1085 | Reg Proc should be Auto Deactivate UINs | NA | [10 empty] | SI customization
99 | Registration Processor | OCR Implementation for Doc quality check |  | MOS-1081 | Reg Proc should be able to integrate with a SDK to perform OCR Validation of ID Object Fields using Documents | Desirable
100 | Registration Processor | Archival of rejected packet |  | MOS-25374 | Reg Proc should be able to process a Packet rejected by Supervisor | Desirable
101 | Registration Processor | Extract Bio-metric Data and Store it IDA Database for Authentication |  | MOS-21733 | Reg Proc should be able to seed UIN/VID/ID Object and Biometric data of an individual to IDA after UIN Generation, Data Updation in ID Repo. | Essential
102 | Registration Processor | Date maintainance in DB for Analytics & Reporting and Audit Log Changes/Storage | Need clarity for estimating | MOS-18400 - Need discussion with Ramesh on approach | - Data maintenance in DB for Analytics & Reporting - Reg Proc should be able to store meta data in DB for sending it for analytics - Audit Changes - Reg. Proc. should be able to make changes to Audit implementation if there are any changes to Audit Fields - Audit log storage - Reg Proc should be able to store audit logs of a Packet received from Registration Client, in Audit table - Audit data to Analytics system - Weak/Strong Mobile Identification - Reg proc should be able seed audit data to an Analytics system to identify a Weak or Strong Mobile Number | Vital | 0 | [9 empty] | Need more clarity - Refer Reg. Processor sheet for details
103 | Registration Processor | First user registration |  | MOS-25398 | Reg Proc should be able to register the 1st User in MOSIP without any Supervisor and Officer validation | Essential | [10 empty] | OK
104 | Registration Processor | Remove notification to Reg. Client to inform individual to re-register, when Reg. processor in any case triggers notification to individual |  | MOS-26406 | Non-MVP: Packet Processing Flow Change - Remove notification to Reg. Client to inform individual to re-register, when Reg. processor in any case triggers notification to individual | Desirable | [10 empty] | Refernce mail from Shrikant on 26Jun - PF review feedback mail
105 | Registration Processor | Configurability to include/exclude VID Issuance for every UIN |  | MOS-26743 | Country should be able to flag to include/exclude VID issuance on generation of each UIN. Currently - VID issuance for every UIN is hard coded. | Desirable | [10 empty] | Reference mail from Sasi/Ramesh on 02Jul - SUB: RE: UIN privacy policy
106 | Registration Processor | Display of VID in UIN Card | Additional | MOS-26758 | VID Should be displayed in UIN Card | Vital? | 16
107 | ID-Authentication | Analytics Module Feature - UINs for Auth Failure | To be deleted | MOS-25615 - Accommodated | To provide Analytics module the hashed UINs of successive authentication failures. MOSIP should be enabled to provide hashed UINs | Vital | 0
108 | ID-Authentication | Audit Enhancement | Additional | MOS-23840 | To enhance auditing to include error code for each audit event | Vital | 6
109 | ID-Authentication | Biometric Authentication - Best Finger Detection |  | MOS-1120 | Best Finger for Authentication to be implemented for IDA. The quality of fingerprints may wear out with time. BFD during authentication will help in identifying Best Finger after registartion | NA | [10 empty] | Addressed as part of analytics
110 | ID-Authentication | Biometric Authentication - Fingerprint Image based Authentication | Real Biometrics | MOS-12165 | In addition to the Fingrprint Minutiae based authentication already implemented, Fingerprint Image based authentication has to be implemented | Vital | 12
111 | ID-Authentication | Biometric Authentication - Integration with devices and SDK | Real Biometrics | MOS-22416, MOS-21758, MOS-18214, MOS-12073, MOS-12072, MOS-10831, MOS-10308, MOS-1150 | 1. To integrate with devices and SDK for biometric authentication requests from Registration Client and Registration Supervisor 2. To integrate with PM/Admin for Device Related Requirements like Device Registration and Device Provider Registration 3. To integrate with MOSIP device services for biometric attributes in IDA . Also integrate with Partner Management services for Device Registration etc 4. When the devices and SDK are available, to integrate with SDK for Iris, face & FP match score generation 5. When the devices and SDK are available, to integrate with SDK for biometric match score for composite fingerprint/IRIS 6. Master story for Biometric implementation to be implemented once the devices and SDK are available | Vital | 136
112 | ID-Authentication | Biometric Authentication - Redesign biometric authentication independent of biometric type/provider |  | MOS-20783 | Need more clarity to understand the requirement - MOSIP should identify biometric type and pass on the CBEFF from auth client to SDK - Agnostic of biometric type | Essential
113 | ID-Authentication | Biometric Authentication - send signed biometrics to Reg Client |  | MOS-22937 | Need additional details on the 'Signed Biometrics' to understand the requirement | NA | [10 empty] | As a policy, MOSIP should not send out biometrics - Refer discussion with Vivek
114 | ID-Authentication | Biometric Authentication - Notify Individual to Update Biometrics due to poor quality |  | MOS-13190 | After successive failure in authentication due to quality issue, individual to be intimated to update biometrics | NA | [10 empty] | Addressed as part of analytics
115 | ID-Authentication | Demographic Authentication - Morocco Address mapping | Additional | MOS-21585 | To support Morrocco specific address attributes for Demo authentication based on full address and address line items | Vital | 6
116 | ID-Authentication | Demographic Authentication - Phonetics and Partial Match |  | MOS-12166 | In the demo authentication implementation, in addition to the exact match, partial and phonetics based match has to be implemented | Desirable
117 | ID-Authentication | KYC Service - Morocco HoH API |  | MOS-13161 | To support for an additional eKYC api for Morrocco, to retrieve data of a family/child on consent to the head of family | NA | [10 empty] | This should be handled as part of Consent provided during Registration and as part of Reg. Proc. during integration
118 | ID-Authentication | Multi-factor Authentication | Real Biometrics | MOS-1124 | Master story for Multi-factor implementation to be implemented once the devices and SDK are available | Vital | 6
119 | ID-Authentication | NFR | To be deleted | MOS-9128, MOS-1136, MOS-1126, MOS-1143 - These will not be considered. Only Perfromance Testing will be accommodated | 1. Performance related NFRS of IDA to be tested 2. Verify the NFR once multiple DCs are configured - High availability 3. Disaster Recovery 4. Verify once Horizontal scaling is available in IDA - Auto scale | Vital | 0
120 | ID-Authentication | OTP Authentication - Integrate with Kernel for OTP Validator fix | Additional | MOS-24077 | Integrate with corrected format of error codes and messages of kernel OTP validator | Vital | 6
121 | ID-Authentication | Partners Authentication and Authorization - Integration with Kernel for Digital Signature | Security | MOS-23836 | Integrate with kernel Digital Signature service once Digital Signature is generated using Digital Certificate | Vital | 8
122 | ID-Authentication | Partners Authentication and Authorization - Integration with PM | Security | MOS-24115, MOS-13157, MOS-13156, MOS-1099 | 1. Integrate with PM to retrieve partner public keys to encrpt eKYC request 2. To integrate with PM to validate Partner ID in the auth/eKYC request and retrive the policy corresponding to a partnerID and partner key 3. To integrate with PM to validate MISP License Key 4. Integrate with PM services, to validate the partner's Digital certificate used in signing auth/eKYC request | Vital | 56
123 | ID-Authentication | Resident Services Feature - Auth Transaction History | Additional | MOS-24680 - Refer Comments for effort inclusions | To provide authentication history for an individual for all associated id types - UIN and VID | Vital | 24 | [9 empty] | Estimates are based on data model change and includes testing. Revised from 16 to 24. This includes: 1. SALT generator job for hashing and encrypting UIN
124 | ID-Authentication | Security - Integration with kernel Cryptomanager fix (To accommodate key index based encryption/decryption) | Security | MOS-23741 | - IDA receives Key index in input, which is to be used to decrypt the auth request, by calling Kernel Cryptomanager Current implementation of Cryptomanager doesn't support it. - Also when the associated public keys are expired, IDA needs to inform partner with the relevant error message | Vital | 6
125 | Security | Technical - Docker Signing | Security | MOS-17514 | Verify once Dockers are signed | Vital | 30 | [9 empty] | Core team to implement
126 | ID-Authentication | Technical - Integrate with upgraded CBEFF | Additional | MOS-24840 | When CBEFF XSD is upgraded to 2.0, IDA to integrate with upgraded CBEFF | Vital | 10
127 | ID-Authentication | Technical - Integration with Kernel on removal of 500 http status | Additional | MOS-24598 | When 500 http status is removed from kernel apis, IDA needs to verify if the integration to all kernel services are working as expected | Vital | 6
128 | ID-Authentication | Technical - Synchronise IDA DB, Secured UIN storage |  | MOS-21584, MOS-1141, MOS-25377 | 1. Design Change of IDA based on Security review by Sasi/Ramesh: Sychronise ID Repo DB with IDA DB, UIN should be securedly stored in IDA 2. Sychronize ID Repo DB with IDA DB, UIN should be securedly stored in IDA 3. To sync ID Repo DB data to IDA/Auth DB | Essential
129 | ID-Authentication | VID Service | Additional | MOS-24732, MOS-26742, MOS-26641 | 1. To maintain auth-type lock/unlock policy in ID Repo based on the request from Resident Services. The policy is to be validated before any authentication request is processed 2. Retrieve status of Auth Types for Individual 3. Authenticate an Individual based on input Authentication Type only when it is unlocked for an Individual | Vital | 36 | [9 empty] | DB changes, Policy to be creaated, create and update API to be created
130 | ID-Authentication | Internal Auth | Additional | MOS-26647, MOS-26649 | 1. To enable Individual request for an OTP via Resident Services 2. To enable authenticating an Individual via Resident Services | Vital | 14
131 | ID-Repository | Audit Enhancement | Additional | MOS-26745 | To enhance auditing to include error code for each audit event | Vital | 4
132 | ID-Repository | VID Service | Additional | MOS-24760, MOS-24761 | 1. To de-activate all VIDs associated to a deactivated UIN 2. To re-activate all VIDs associated to a reactivated UIN. This UIN is reactivating a deactivated UIN | Vital | 24
133 | ID-Repository | Identity Service Enhancement | Additional | MOS-26747 | To retrieve RID for a given UIN | Vital | 3 | [9 empty] | Required for Registration Processor
134 | ID-Repository | Technical - Integrate with upgraded CBEFF | Additional | MOS-26748 | When CBEFF XSD is upgraded to 2.0, IDRepo to integrate with upgraded CBEFF | Vital | 10
135 | Kernel | SMS/EmailNotification |  | MOS-23810 | Adding an interface to support capturing of delivery reports sent by thrid party Email/SMS Vendor | Essential
136 | Kernel | Crypto Management |  | MOS-23599 | Ability to decrypt data using Key Index instead of Timestamp in IDA | ? | [10 empty] | Need clarification from John
137 | Kernel | Audit Management | Additional | MOS-23263 | Tech Story - Implementing Kafka as message queue to prevent data loss during Audit Logging | Vital | 15 | [9 empty] | Architects to further discuss
138 | Kernel | Sync Data | Additional | MOS-22655 | Change in Sync data response based on the Morocco Location Hierarcy | Vital | 15 | [9 empty] | Architects to further discuss
139 | Kernel | License Key Validation | Additional | MOS-22446 | Perfroming a Pattern and Length validation on License Key | Vital | 4
140 | Kernel | Parter ID Validation | Additional | MOS-22445 | Perfroming data type and Length validation on Partner ID | Vital | 4
141 | Kernel | Partial Search on Location | Additional | MOS-22038 | Adding support/query to search and fetch location data based on a partial search on pre-registration | Vital? | 5 | [9 empty] | Subject to bandwidth
142 | Kernel | OTP Management |  | MOS-21931 | Ability to have multiple OTPs active for a single UIN - Inclusive of mapping each active OTP to a transaction | Desirable
143 | Kernel | Moving to hardware HSM | Security | MOS-26254 | TBD | Vital | 8 | [9 empty] | Estimates covers only the code change. Pre-Requirtes is HSM should beavilable for usage
144 | Kernel | Technical - Integration with Kernel on removal of 500 http status | Additional | MOS-26255 | - 500 http status to be removed from kernel apis | Vital | 3
145 | Resident Services | View Auth History |  | MOS-23863 | An individual can view authentication- requests history for a specific UIN/VID. The system will fetch unarchived data and show it in a paginated format to user. | Vital | 6 | [9 empty] | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
146 | Resident Services | Download e-UIN |  | MOS-23862 | An individual can raise a request to download his/her e-UIN by providing the UIN/VID, full name, postal code, and security code. | Vital | 6 | [9 empty] | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
147 | Resident Services | Track UIN Generation Status |  | MOS-23861 | An individual can track the stats of UIN generation by providing a Registration ID(RID). | Vital | 6 | [9 empty] | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
148 | Resident Services | Track UIN Update Request |  | MOS-23860 | An individual can track the status related to UIN updates based on a registration ID.An individual provides the Registration ID for which he/she wants to track the status of UIN updates. | Vital | 6 | [9 empty] | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
149 | Resident Services | UIN Update |  | MOS-23859 | MOSIP allows an individual to process a request to update the demographic data of the UIN. An individual provides the UIN/VID for which he/she wants to update. | Desirable | 6 | [9 empty] | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
150 | Resident Services | Retrieve Lost UIN |  | MOS-23858 | MOSIP allows an individual to initiate a request to retrieve the Registration ID by providing the Full Name, Mobile Number/E-Mail ID, Postal Code | Desirable | 6 | [9 empty] | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
151 | Resident Services | Retrieve Lost RID |  | MOS-23856 | An individual can retrieve the RID by providing the Full Name, Mobile Number/E-Mail ID, Postal Code. | Desirable | 6 | [9 empty] | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
152 | Resident Services | Reprint UIN |  | MOS-23746 | MOSIP allows an individual to raise a reprint request for their UIN. The individual provides the UIN/VID for which he/she wants to reprint. | Vital | 6 | [9 empty] | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
153 | Resident Services | Lock/Unlock AUTH |  | MOS-23745, MOS-23744 | 1. MOSIP allows an individual to unlock/lock the authentication type(s) (Demographic, Biometrics (FP/Iris/Face/All)) associated with the UIN/VID. Only the unlocked authentication type(s) of demographic and biometric (FP/Iris/Face/All) can be used for any required authentication purpose | Vital | 12 | [9 empty] | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
154 | Resident Services | Generate VID |  | MOS-25580 | Upon receiving a VID generation and storage request with the parameters: UIN, ver, requestTime, vidType, the system performs steps to create VID in the defined policy. | Vital | 6 | [9 empty] | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
155 | Resident Services | Revoke VID |  | MOS-25583 | Upon receiving a request with the parameter: VID, ver to revoke a VID based on the type, the system performs steps to revoke a VID based on the type. | Vital | 6 | [9 empty] | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
156 | Resident Services | Address Validation Letter |  | MOS-24702 | Address Validation Letter is letter which is sent to the Address Verifier’s address. The letter will contain a secret code sent for validation after the Address Verifier consents to the use of his/her address by the requesting resident. | Desirable
157 | Resident Services | Authentication with non-registered mobile |  | MOS-24701 | Resident Service should be able to validate a user on a different mobile number other than the registered mobile number. | Desirable
158 | Resident Services | Weak Mobile Identification |  | MOS-25624 | Resident Service should be able to call an API which can determine if a mobile number as weak based on multiple associations to UIN's for that mobile number. | Desirable
159 | Resident Services | Retrieve VID |  | MOS-25600 | An individual should have the provision to retrieve the existing valid Virtual Identity for the resident by taking PIN and OTP as input. | Desirable
160 | Resident Services | Track UIN Reprint Status |  | MOS-26651 | An individual can track the status of Reprint UIN by providing a Request ID(RID). | Desirable
161 | Partner Management | Digital Certificate Signing/Resigning |  | MOS-24500, MOS-24068 | 1. Validate and Re-Issue the Digital Certificate provided by a Partner 2. Integrate with kernel for Partner Certificate signing and resigning | Vital | 19.5
162 | Partner Management | ID/Key Generation and Validation |  | MOS-24069, MOS-26025, MOS-26024, MOS-26023, MOS-26022, MOS-26021, MOS-24504, MOS-24072, MOS-24071, MOS-24070, MOS-24067, MOS-24066 | ID/Key Generation and Validation | Vital | 70.85
163 | Partner Management | Integration with IDA for PM |  | MOS-24503 | Integrate with IDA to provide IDA requested services | Vital | 7.8
164 | Partner Management | Master Data Management |  | MOS-24481 | Define the master data for PM services | Vital | 11.7
165 | Partner Management | MISP Self-Service |  | MOS-24479 | Regenerate license keys | Vital | 7.8
166 | Partner Management | NFR |  | MOS-24505 | Implement the NFR requirements | Essential | 33.8 | [9 empty] | This would cover Logging, Tracing, Performance, Load, Availability, Security, Config
167 | Partner Management | Partner API key Issuance/Management |  | MOS-26026, MOS-26020, MOS-26019, MOS-26018, MOS-24492, MOS-24491 | 1. Update Partner api key to Policy Mappings 2. Activate/deactivate Partner api key based on 'policy group' 3. Approve/reject Partner api key requests based on 'policy group' 4. View Partner api key requests based on 'policy group' 5. Retrieve Partner API key to Policy Mappings 6. Create Partner API key to Policy Mappings | Vital | 38.35
168 | Partner Management | Partner Authentication |  | MOS-24490, MOS-24478 | 1. Check status of a Partner 2. Retrive policy of a partner with partner-ID and partner api key | Vital | 7.8
169 | Partner Management | Partner Management |  | MOS-26017, MOS-24489 | 1. View Auth/E-KYC Partners 2. Deactivate Auth/E-KYC Partners | Vital | 13
170 | Partner Management | Partner Self-Service |  | MOS-26016, MOS-26015, MOS-24488, MOS-24487, MOS-24486 | 1. View Partner api key request status 2. Submit Partner api key request 3. Update Auth/E-KYC Partners 4. Retrieve Auth/E-KYC Partners 5. Create Auth/E-KYC Partners | Vital | 32.5
171 | Partner Management | Policy Management |  | MOS-26014, MOS-26013, MOS-24483, MOS-24482 | 1. Deactivate Auth/E-KYC Policy 2. Update Auth/E-KYC Policy 3. Retrieve Auth/E-KYC Policy 4. Create Auth/E-KYC Policy | Vital | 27.3
172 | Partner Management | Public Key Management |  | MOS-24502, MOS-24501 | 1. Retrieve Public key from Partners for encryption of e-kyc response 2. Distribute Public Key to Partners for Encryption of auth/KYC Request | Vital | 15.6
173 | Partner Management | Role Management |  | MOS-24473 | Integrate with Kernel (IAM) for Role Mangement for PM services | Vital | 10.4
174 | Partner Management | User Management - Admin |  | MOS-26012, MOS-26011, MOS-26010, MOS-26009, MOS-26008, MOS-26007, MOS-26005, MOS-26003, MOS-24477, MOS-24476, MOS-24475, MOS-24474 | 1. Deactivate, Update, Retrieve, Create Partner Managers 2. Deactivate, Update, Retrieve, Create Policy Managers 3. Deactivate/Suspend (Update MISP License Key Status), Update, Retrieve, Create MISP | Vital | 70.85
175 | Admin | Account Unlock: API & UI |  | MOS-23691, MOS-23690 | Unlock my locked account | Desirable | 5.2 | [9 empty] | Key Cloak Feature
176 | Admin | Approvals with Approval Framework |  | MOS-24132, MOS-23791 Need clarity for estimating | Approve created Centers, Machine, Devices, Users and Masterdata | Desirable | 0 | [9 empty] | Need more clarifiaction on Requirements and Design
177 | Admin | Auto Logout |  | MOS-23606 | Auto-Logout a logged in user | Desirable | 5.2 | [9 empty] | Key Cloak Feature
178 | Admin | MDM - Blacklisted Words Management: API |  | MOS-23666, MOS-23671 | Create, Update, De-activate Blacklisted Words | Vital | 7.8
179 | Admin | MDM - Blacklisted Words Management: UI |  | MOS-23667, MOS-23670, MOS-23668 | Create, Update, De-activate Blacklisted Words | Desirable | 11.7
180 | Admin | Store history of Creations and Update of Registration Centers |  | MOS-24829 | Store history of Creations and Update of Registration Centers | Vital | 2.6
181 | Admin | MDM - Center - Activate/Deactivate - API |  | MOS-25634 | Activate/Deactivate a Registration Center | Vital | 3.9
182 | Admin | MDM - Center - Activate/Deactivate - UI |  | MOS-23635 | Activate/Deactivate a Registration Center | Desirable | 3.9
183 | Admin | MDM - Center - Creation - API & UI |  | MOS-23631, MOS-23630, MOS-23629 | Creation of Registration Center | Vital | 13
184 | Admin | MDM - Device - View - API |  | MOS-24950 | Implementation of Registration Search API | Vital | 5.85
185 | Admin | MDM - Device - View - API |  | MOS-24950 |  | Vital | 5.85
186 | Admin | MDM - Center - Decommission - API |  | MOS-25261 |  | Vital | 5.2
187 | Admin | MDM - Center - Activate/Deactivate - UI |  | MOS-25368 |  | Desirable | 3.9
188 | Admin | MDM - Center Detail View - UI |  | MOS-23619 |  | Vital | 2.6
189 | Admin | MDM - Center List View - API & UI |  | MOS-23617, MOS-23616 |  | Vital | 7.15
190 | Admin | Center List View Machine List View Device List View |  | MOS-25638 |  | Vital | 2.6
191 | Admin | MDM - Center - Update - API |  | MOS-23632, MOS-23630 |  | Vital | 7.8
192 | Admin | MDM - Center - Update - UI |  | MOS-23633 |  | Desirable | 2.6
193 | Admin | Center-Device Mapping - Create - API |  | MOS-23624 |  | Vital | 3.9
194 | Admin | Center-Device Mapping - Create - UI |  | MOS-23625 |  | Desirable | 3.9
195 | Admin | Location Update |  | MOS-25217 | Update details of a Location | Vital | 5.2
196 | Admin | Center-Machine Mapping History Storage |  | MOS-24836 |  | Vital | 2.6
197 | Admin | Center-Machine - Unmap - API |  | MOS-23674 |  | Vital | 3.9
198 | Admin | Center-Machine - Unmap - UI |  | MOS-23675 |  | Desirable | 3.9
199 | Admin | Center-User Mapping - Create - API |  | MOS-23620 |  | Vital | 5.2
200 | Admin | Center-User Mapping - Create - UI |  | MOS-23621 |  | Desirable | 5.2
201 | Admin | Center-User Mapping History Storage |  | MOS-24835 |  | Vital | 2.6
202 | Admin | Center-User - Unmap - API |  | MOS-23672 |  | Vital | 5.2
203 | Admin | Center-User - Unmap - UI |  | MOS-23673 |  | Desirable | 3.9
204 | Admin | Change Password - API & UI |  | MOS-23611, MOS-23610 |  | Desirable | 6.5 | [9 empty] | Key Cloak Feature
205 | Admin | Device Activate/Deactivate: UI |  | MOS-23647 |  | Desirable | 3.9
206 | Admin | Device Activate/Deactivate: API |  | MOS-25636 |  | Vital | 3.9
207 | Admin | Device Create: UI |  | MOS-23643 |  | Desirable | 3.9
208 | Admin | Device Create: API |  | MOS-23642 |  | Vital | 3.9
209 | Admin | Device Decommission: API |  | MOS-25263 |  | Vital | 3.9
210 | Admin | Device Decommission: UI |  | MOS-25372 |  | Desirable | 3.9
211 | Admin | Device History Storage: API |  | MOS-24831 |  | Vital | 2.6
212 | Admin | Device List View: UI & API |  | MOS-23629, MOS-23626 |  | Vital | 6.5
213 | Admin | Device List View: UI - View associated Devices for a Registration Center |  | MOS-25373 |  | Desirable | 6.5
214 | Admin | Device Update: UI |  | MOS-23645 |  | Desirable | 3.9
215 | Admin | Device Update: API |  | MOS-23644 |  | Vital | 3.9
216 | Admin | Device View: UI |  | MOS-23785 |  | Vital | 3.9
217 | Admin | Document Type Activate/Deactivate, Create: UI |  | MOS-23653, MOS-23649 |  | Desirable | 6.5
218 | Admin | Document Type Create & Update: API |  | MOS-23648, MOS-23650 |  | Vital | 6.5
219 | Admin | Document Type Update: UI |  | MOS-23651 |  | Desirable | 3.9
220 | Admin | Document Type-Category Mapping Activate/Deactivate: UI |  | MOS-23659 |  | Desirable | 3.9
221 | Admin | Document Type-Category Mapping Create & Update: UI |  | MOS-23655, MOS-23657 |  | Desirable | 7.8
222 | Admin | Document Type-Category Mapping Create: API |  | MOS-23654 |  | Vital | 5.2
223 | Admin | Document Type-Category Mapping Update: API |  | MOS-23656 |  | Vital | 3.9
224 | Admin | Dssign |  | MOS-24134 |  | Vital | 7
225 | Admin | Edit Personal Details: UI & API |  | MOS-23609, MOS-23608 |  | Desirable | 19.5 | [9 empty] | Key Cloak Feature
226 | Admin | Export data (CSV): UI |  | MOS-25370 |  | Desirable | 5.2
227 | Admin | Forgot Username: UI & API |  | MOS-23685, MOS-23684 |  | Desirable | 7.15 | [9 empty] | Key Cloak Feature
228 | Admin | Home Page: UI |  | MOS-23607 |  | Vital | 2.6
229 | Admin | Location Data Activate/Deactivate: UI |  | MOS-23665 |  | Desirable | 5.2
230 | Admin | Location Data Create & Update: UI |  | MOS-23661, MOS-23663 |  | Desirable | 10.4
231 | Admin | Location Data Create: API |  | MOS-23660 |  | Vital | 6.5
232 | Admin | Location Data Update: API |  | MOS-23662 |  | Vital | 5.2
233 | Admin | Login: API & UI |  | MOS-23788, MOS-23223 MOS-23168 |  | Vital | 9.1
234 | Admin | Login - UI - Validate & respond with Auth Token | To be deleted | MOS-25637 - De-scoped |  | Vital | 0
235 | Admin | Login - Captcha: UI |  | MOS-25105 |  | Desirable | 3.9 | [9 empty] | We will only use KeyCloak Captcha Feature
236 | Admin | Logout: API & UI |  | MOS-23855, MOS-23248 |  | Vital | 5.2
237 | Admin | Machine Activate/Deactivate: UI |  | MOS-23641 |  | Desirable | 3.9
238 | Admin | Machine Activate/Deactivate: API |  | MOS-25212, MOS-25635 |  | Vital | 7.8
239 | Admin | Machine Create: UI |  | MOS-23637 |  | Desirable | 3.9
240 | Admin | Machine Create: API |  | MOS-23636 |  | Vital | 3.9
241 | Admin | Machine Decommission: API |  | MOS-25262 |  | Vital | 3.9
242 | Admin | Machine Decommission: UI |  | MOS-25371 |  | Desirable | 3.9
243 | Admin | Machine History Storage: API |  | MOS-24830 |  | Vital | 3.25
244 | Admin | Machine List View: UI & API |  | MOS-23623, MOS-23622 |  | Vital | 6.5
245 | Admin | Machine: List View & Update: UI |  | MOS-25369, MOS-23639 |  | Desirable | 10.4
246 | Admin | Machine Update: API |  | MOS-23638 |  | Vital | 2.6
247 | Admin | Machine Detailed View: UI |  | MOS-23784 |  | Vital | 4.55
248 | Admin | Masterdata View: UI & API |  | MOS-23896, MOS-23612 |  | Vital | 10.4
249 | Admin | Masterdata View List: API & UI |  | MOS-23787, MOS-23613 |  | Vital | 9.1
250 | Admin | Mobile Number Validation: API |  | MOS-23897 |  | Desirable | 3.25 | [9 empty] | Key Cloak Feature
251 | Admin | Navigation: UI |  | MOS-25362, MOS-25363 |  | Vital | 9.1 | [9 empty] | Key Cloak Feature
252 | Admin | Machine Update: API |  | MOS-24947 |  | Vital | 3.9
253 | Admin | Location Create: API |  | MOS-24833 |  | Vital | 5.2
254 | Admin | Requirement Detailing |  | MOS-24172 |  | Vital | 11
255 | Admin | Reset Password: UI & API |  | MOS-23689, MOS-23688 |  | Desirable | 9.1 | [9 empty] | Key Cloak Feature
256 | Admin | Sort/Filter/Search: UI |  | MOS-25367 |  | Vital | 7.8
257 | Admin | Tech Story: Setup LDAP, Create Jenkins Pipeline, Create Separate Enviroment for Admin, Restructure UI Project Structure |  | MOS-25625, MOS-25626 MOS-25627, MOS-25628 |  | Vital | 15.6
258 | Admin | UIN Activation/Deactivation: UI & API |  | MOS-23694, MOS-23693, MOS-23683 |  | Desirable | 16.9
259 | Admin | User Blacklist: UI |  | MOS-23687 |  | Desirable | 3.9 | [9 empty] | Key Cloak Feature
260 | Admin | User Creation: Tech Story - Modify code for Ldap |  | MOS-24834 |  | Vital | 3.9
261 | Admin | User Creation: API - Add Password and RID against a Username |  | MOS-24723 |  | Desirable | 2.6
262 | Admin | User Creation - API - Change the existing Auth (LDAP) code - Enable functionality to create a MOSIP User |  | MOS-24722, MOS-23678 |  | Vital | 11.7
263 | Admin | User Creation - UI - Complete Registration into MOSIP |  | MOS-23681, MOS-23679 |  | Desirable | 7.8 | [9 empty] | Key Cloak Feature
264 | Admin | User History Storage: API |  | MOS-24832 |  | Vital | 2.6
265 | Admin | User List View: UI & API |  | MOS-23615, MOS-23614 |  | Vital | 5.2 | [9 empty] | Key Cloak Feature
266 | Admin | User Update: UI |  | MOS-23682 |  | Desirable | 3.9 | [9 empty] | Key Cloak Feature
267 | Admin | User Detailed View: UI |  | MOS-23786 |  | Vital | 2.6
268 | Admin | Username Validation: API |  | MOS-23898 |  | Desirable | 2.6
269 | Admin | Validate ID Schema: API |  | MOS-23790 |  | Desirable | 7.8
270 | Admin | Validate Process Flow Config: API validate Document Upload rule in Process Flow Configurations |  | MOS-23692 |  | Desirable | 5.2
271 | Admin | View Packet Status: UI & API |  | MOS-23696, MOS-23695 |  | Desirable | 11.7
272 | Admin | View API for Master Data: Document Category-Type Mapping View, Titles, Templates, Location Data, Holidays, Individual Types, Gender, Document Types, Document Category, Machine Specifications, Machine Types, Blacklisted Words, Machine, Device |  | MOS-26636, MOS-26173, MOS-26172, MOS-26171, MOS-26170, MOS-26169, MOS-26168, MOS-26167, MOS-26166, MOS-26164, MOS-26163, MOS-26160 MOS-26156, MOS-26106 |  | Vital | 65
273 | Admin | View API for Master Data: Center Types, Device Specifications , Device Types, |  | MOS-26165, MOS-26162, MOS-26161 |  | Desirable | 14.3
274 | Admin | Search Utility: API |  | MOS-25831 |  | Vital | 6.5
275 | Admin | Login: UI |  | MOS-25710 |  | Desirable | 14.3
276 | Admin | UI Template - Detail View & List View of Entities |  | MOS-25705, MOS-25703 |  | Vital | 11.7
277 | Admin | Document Type Update & Create: API |  | MOS-26656, MOS-26655 |  | Vital | 7.8
278 | Admin | Center Update & Create: UI Add Zone as a drop-down field and replace Stubbed values by Configurable Values |  | MOS-26654, MOS-26653 |  | Desirable | 13
279 | Admin | Center Update & Create: API - Validate updation of Registration Center belonging to the Zone of the Administrator |  | MOS-26652, MOS-26643 |  | Vital | 7.8
280 | Admin | Center View: UI |  | MOS-26640 |  | Vital | 3.9
281 | Admin | Device Update & Create: API |  | MOS-26637, MOS-26408 |  | Vital | 7.8
282 | Admin | Machine Create: API |  | MOS-25719 |  | Vital | 3.9
283 | Admin | Location Clone & Creation: UI |  | MOS-26393 |  | Desirable | 3.9
284 | Admin | UIN Activation/Deactivation: UI - Maker-checker process |  | MOS-26392 |  | Desirable | 3.9 | [9 empty] | More Clarification Needed
285 | Admin | Center-Device List View: UI |  | MOS-25640 |  | Desirable | 3.9
286 | Admin | Center-Machine List View: UI |  | MOS-25639 |  | Desirable | 3.9
287 | Admin | UI Template - Detail View of Entity |  | MOS-25709 |  | Desirable | 0 | [9 empty] | De-scoped
288 | Client | TPM for Windows (initial design is not enough) | Security |  |  | Vital | 100 | [9 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
289 | Client | Device enrollment and validation | Security | Need input from Ramesh/ Sasi, What validation required from Reg. Client? |  | Vital | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
290 | Client | Protection of local data management | Security | Need clarity for estimating |  | Vital | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
291 | Client | Certificate pinning | Security | Need clarity for estimating |  | Vital | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
292 | Client | Protection of residents document and receipts | Security | Need clarity for estimating |  | Vital | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
293 | Client | No rollback | Security | Need clarity for estimating |  | Vital | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
294 | Client | Lockdown the signed jars and launcher so fake jars or older jars can not be used |  |  |  | Essential | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
295 | Client | TPM for Android |  |  |  | Essential | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
296 | Client | TPM for Linux |  |  |  | Desirable | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
297 | API | All external facing API’s will be digitally signed with domain (segregation of keys by security domain) specific keys | Security | Covered as part of - MOS-23836 |  | Vital | 4 | 4 | [8 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
298 | API | All the API’s are validated for JWT | Security | Need clarity for estimating |  | Vital | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
299 | API | JWT token based authorization for all the services. | Security | Need clarity for estimating |  | Vital | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
300 | API | API registration as service so only registered API’s and services are accessible over proxy |  |  |  | Desirable |  | Need more clarification | [8 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
301 | API | All internal API’s will need to be over two way SSL channel |  |  |  | Desirable |  | Same as line item 19 | [8 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
302 | Server | Role engineering & filtering | Security | This is under progress. Every module should change the code of encryption logic using Kernel services to DTO Layer. |  | Vital | 21 | Need more clarification |  | 7 | 7 | 7 |  |  |  |  | Input from Sasi/Ramesh - Refer mail dtd 25Jun
303 | Server | IAM Integration | Security | We had decided to use the Keycloak and we might have to roll back this. Will get more clarification after tomorrows meeting. |  | Vital |  | Same as line item 19 | [8 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
304 | Server | HSM integration | Security | This will affect only Kernel module. |  | Vital | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
305 | Server | CORS settings and optimization | Security | This will have minor effect on web applications and micro services |  | Vital | 17 | 8 |  | 2 | 4 | 3 |  |  |  |  | Input from Sasi/Ramesh - Refer mail dtd 25Jun
306 | Server | CSRF Protection | Security | Web applications and microservices will have impact on this. Need more clarity on this also. |  | Vital | 12 | 8 |  | 4 | [6 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
307 | Server | Server configuration to be protected for sensitive data | Security | Need more clarity on this. |  | Vital | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
308 | Server | Approval flow for sensitive server configuration | Security | Might not have impact in any module in the application layer |  | Vital | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
309 | Server | JWT Auth Token Renewal | Security | Depends on the 3rd party IAM decision. Need clarity for estimating |  | Vital | [7 empty] | Need clarity for estimating |  |  | Input from Sasi/Ramesh - Refer mail dtd 25Jun
310 | Server | Key Management (Auto renewal, auto rotation) | Security | Only Kernel will be affected |  | Vital | 0 | Already Done | [5 empty] | Need clarity for estimating |  |  | Input from Sasi/Ramesh - Refer mail dtd 25Jun
311 | Server | Encryption layer moved to hibernate | Security | Kernel has to make changes to the DAO layer and everybody have to refer to this new version. And everybody have to stop calling Kernel services for encryption and use the declarative features in their DTOs |  | Vital | 21 |  |  | 7 | 7 | 7 |  | Need clarity for estimating |  |  | Input from Sasi/Ramesh - Refer mail dtd 25Jun
312 | Server | API throttling & DDOS protection | Security | Might not have impact in any module in the application layer |  | Vital | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
313 | Server | Master data should be publish and read not CRUD | Security | Need more clarity on this. |  | Vital | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
314 | Server | Domain specific otp messages | Security | Need more clarity on this. |  | Vital | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
315 | Server | OCSP Stapling | Security | Need more clarity on this. |  | Vital | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
316 | Server | File protection | Security | Need more clarity on this. |  | Vital | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
317 | Server | Device management | Security | Need more clarity on this. |  | Vital | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
318 | Server | Anti spam/anti bot solutions. | Security | Need clarity for estimating |  | Vital | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
319 | Auth Service | VID only Auth | Security | Need clarity for estimating - Can we use UIN for internal auth? |  | Vital | [6 empty] | Need clarity for estimating - Can we use UIN for internal auth? |  |  |  | Input from Sasi/Ramesh - Refer mail dtd 25Jun
320 | Auth Service | Distributed readonly Zero knowledge database | Security | Need clarity for estimating |  | Vital | [6 empty] | Need clarity for estimating |  |  |  | Input from Sasi/Ramesh - Refer mail dtd 25Jun
321 | Auth Service | Auth message replay protection | Security | Need clarity for estimating |  | Vital | [6 empty] | Need clarity for estimating |  |  |  | Input from Sasi/Ramesh - Refer mail dtd 25Jun
322 | Auth Service | Auth transaction validation | Security | Need clarity for estimating |  | Vital | [6 empty] | Need clarity for estimating |  |  |  | Input from Sasi/Ramesh - Refer mail dtd 25Jun
323 | Auth Service | Auth purpose validation | Security | Need clarity for estimating |  | Vital | [6 empty] | Need clarity for estimating |  |  |  | Input from Sasi/Ramesh - Refer mail dtd 25Jun
324 | Auth Service | Auth registered device L1 validation |  |  |  | Essential | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
325 | Auth Service | Auth with just VID and age greater than or less than or just with VID and parts of address |  |  |  | Essential | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
326 | Auth Service | Independant Auth systems with a simple publisher to refresh data. |  |  |  | Desirable | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
327 | Auth Service | Segregation of ekyc and auth services |  |  |  | Desirable | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
328 | Auth Service | TOTP based auth |  |  |  | Desirable | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
329 | Auth Service | OCSP Stapling |  |  |  | Desirable | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
330 | UIN Recovery Service | Should follow the rules of 1:N match for recovery | Security | Need clarity for estimating |  | Vital | [7 empty] | Need clarity for estimating |  |  | Input from Sasi/Ramesh - Refer mail dtd 25Jun
331 | Security Integration | Integrated Subnet and firewall segregation | Security | Impact on Infrastructure-TBD |  | Vital | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
332 | Security Integration | Integrated url filtering | Security | Impact on Infrastructure-TBD |  | Vital | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
333 | Security Integration | NTP integration on standard | Security | Impact on Infrastructure-TBD |  | Vital | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
334 | Security Integration | A proper inbuilt certification authority |  |  |  | Essential | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
335 | Security Integration | A way to publish the approved certificates to all app |  |  |  | Essential | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
336 | Security Integration | OCSP/CRL |  |  |  | Desirable | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
337 | Security Integration | Zoning & Service segregation | Security | Impact on Infrastructure-TBD |  | Vital | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
338 | Resident portal | Protection against SIM Swap | Security | Need clarity for estimating |  | Vital | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
339 | Resident portal | Protection against OTP SPAM | Security | Need clarity for estimating |  | Vital | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
340 | Data protection | All residents data should be stored in encrypted form | Security | Need clarity for estimating |  | Vital | [6 empty] | Already done, need clarity on the requirement for estimating |  |  |  | Input from Sasi/Ramesh - Refer mail dtd 25Jun
341 | Data protection | All sensitive configuration should be stored in encrypted form | Security | Need clarity for estimating |  | Vital | [6 empty] | DB passwords are encrypted, Need clarity on the requirement for estimating |  |  |  | Input from Sasi/Ramesh - Refer mail dtd 25Jun
342 | Admin portal | Avoid enumeration of data | Security | Need clarity for estimating |  | Vital |  |  | Need more clarification | [7 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
343 | Audit | Audit all changes to the data | Security | Need clarity for estimating |  | Vital | 6 |  | 6 |  |  |  | Already done, need clarity on the requirement for estimating |  |  |  | Input from Sasi/Ramesh - Refer mail dtd 25Jun
344 | Audit | Publicly publishable audits |  |  |  | Essential | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
345 | Audit | Non repudiable with timestamp service |  |  |  | Essential | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
346 | BI | Anonymised publishable data | Security | Need clarity for estimating |  | Vital | [10 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
347 | General | Consolidation of logs from all pods for enhanced debugging | Security |  | Consolidation of logs from all pods for better debugging - eg: today we have reg proc logs one each in each pod for each stage | Vital? | 30
[6 empty] | Total PDs: Vitals | 3707.45

## RoadmapFeatures
MOSIP - Roadmap post 30Jun
S.No. | Feature | Priority | Comments | SK Comments
1 | Refactoring of MOSIP repository - Aligning current MOSIP git repository to the open source one - Others | Vital |  | OK
2 | Real Biometrics Release - Integrating with Reg. devices (Iris, FP,Face) - Auth devices (Iris,FP,Face) - ABIS - One ABIS, multi-modal | Vital |  | Ok
3 | Face ABIS & Auth - what should the plan be, discussion with Vivek and its tangible impact for us to do. | Desirable |  | OK
4 | Multi-partner ABIS - One ABIS per modality | Essential |  | OK
5 | Multiple ABIS with all modalities | Desirable |  | OK, No use case currently.
6 | Automated check by system to identify photo/age/gender matchness, other validations to reject packets at an early stage based on automated checks | Desirable | SI customization | OK, QC module
7 | Manual Adjudication System - For QC results verification, biometrics duplicate verification, others to be identified | Desirable | SI customization | OK, from BSP/ABIS provider
8 | Fraud & Data Analytics | Desirable | SI customization | OK
9 | External Integration - Open CRVS / SIA etc | Desirable | Community contribution | OK, Community Effort
10 | Features which can be considered if there is Usecase / demand | NA |  | OK
11 | Role of Block Chain in MOSIP (where, how) | NA | Community contribution | OK, Community Effort
12 | OCR for document upload check | Desirable | Community contribution | OK, Community Effort
13 | Configurable UI for Pre-reg. & Reg. Client | Vital |  | This is Vital.
14 | UX Enhancements - Pre-reg. | Vital |  | This is Vital.
15 | UX Enhancements - Reg. Client | Vital |  | This is Vital.
16 | Reference UI portal for resident services | Desirable | Community contribution | OK, Community Effort
17 | Make Reg client - a browser based (with local server) solution (moving away from heavy client) - Ramesh can explain more | NA | Community contribution | OK, Community Effort
18 | Installable Dongle for Reg Client. | NA | Community contribution | OK
19 | Device Ecosystem testing & certification Target | NA | Community contribution | OK
20 | Performance testing | Vital |  | OK
21 | Security testing | Vital |  | OK
22 | Separating ID Repo and ID Auth modules…. i.e., exporting ID data to ID Auth | Essential? | Subject to bandwidth | OK
23 | Basic system reporting | Vital | System health monitoring | OK
24 | Integrating all modules with the KeyCloak implementation for authentication and authorization | Vital |  | OK
25 | Offline Verification - QR code with Photo | Vital? | Subject to bandwidth | OK
26 | SPR Seeding for Morocco (HoH requirement) | Essential |  | ok
27 | Device registration - API, Integration with Management server from biometric device vendor | Desirable |  | OK
28 | Registration client sync without running instance or login | Desirable |  | OK
29 | Audit Logging for Product Management Directives | Essential? |  | OK
30 | eKYC Auth Reference App | Desirable |  | OK
31 | Online registration | NA |  | OK
32 | Mosip resident reference App | NA |  | OK
33 | Offline Auth Verification App | NA |  | OK
34 | Browser Support - Support IE | Essential? | Krishnan to determine | OK
35 | Testing: UTC check in APIs, audit and DB entries - Pre-reg, Reg. Client, Reg. Processor, IDA | Vital | Pending testing activities - From Gita | OK
36 | Testing: Audit log checks - Reg. Client, Reg. Processor | Vital | Pending testing activities - From Gita | OK
37 | Testing: Token optimization - Reg. Processor | Vital | Pending testing activities - From Gita | OK
38 | Testing: ID repo pending APIs – fetch identity for UIN and anything else that is not automated - IDA | Vital | Pending testing activities - From Gita | OK
39 | Upload portal for Registraition packets | Vital | sftp channel?
40 | TPM for Windows (initial design is not enough) | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
41 | Device enrollment and validation | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
42 | Protection of local data management | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
43 | Certificate pinning | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
44 | Protection of residents document and receipts | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
45 | No rollback | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
46 | Lockdown the signed jars and launcher so fake jars or older jars can not be used | Essential | Input from Sasi/Ramesh - Refer mail dtd 25Jun
47 | TPM for Android | Essential | Input from Sasi/Ramesh - Refer mail dtd 25Jun
48 | TPM for Linux | Desirable | Input from Sasi/Ramesh - Refer mail dtd 25Jun
49 | All external facing API’s will be digitally signed with domain (segregation of keys by security domain) specific keys | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
50 | All the API’s are validated for JWT | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
51 | JWT token based authorization for all the services. | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
52 | API registration as service so only registered API’s and services are accessible over proxy | Desirable | Input from Sasi/Ramesh - Refer mail dtd 25Jun
53 | All internal API’s will need to be over two way SSL channel | Desirable | Input from Sasi/Ramesh - Refer mail dtd 25Jun
54 | Role engineering & filtering | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
55 | IAM Integration | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
56 | HSM integration | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
57 | CORS settings and optimization | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
58 | CSRF Protection | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
59 | Server configuration to be protected for sensitive data | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
60 | Approval flow for sensitive server configuration | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
61 | JWT Auth Token Renewal | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
62 | Key Management (Auto renewal, auto rotation) | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
63 | Encryption layer moved to hibernate | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
64 | API throttling & DDOS protection | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
65 | Master data should be publish and read not CRUD | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
66 | Domain specific otp messages | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
67 | OCSP Stapling | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
68 | File protection | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
69 | Device management | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
70 | Anti spam/anti bot solutions. | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
71 | VID only Auth | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
72 | Distributed readonly Zero knowledge database | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
73 | Auth message replay protection | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
74 | Auth transaction validation | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
75 | Auth purpose validation | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
76 | Auth registered device L1 validation | Essential | Input from Sasi/Ramesh - Refer mail dtd 25Jun
77 | Auth with just VID and age greater than or less than or just with VID and parts of address | Essential | Input from Sasi/Ramesh - Refer mail dtd 25Jun
78 | Independant Auth systems with a simple publisher to refresh data. | Desirable | Input from Sasi/Ramesh - Refer mail dtd 25Jun
79 | Segregation of ekyc and auth services | Desirable | Input from Sasi/Ramesh - Refer mail dtd 25Jun
80 | TOTP based auth | Desirable | Input from Sasi/Ramesh - Refer mail dtd 25Jun
81 | OCSP Stapling | Desirable | Input from Sasi/Ramesh - Refer mail dtd 25Jun
82 | Should follow the rules of 1:N match for recovery | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
83 | Integrated Subnet and firewall segregation | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
84 | Integrated url filtering | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
85 | NTP integration on standard | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
86 | A proper inbuilt certification authority | Essential | Input from Sasi/Ramesh - Refer mail dtd 25Jun
87 | A way to publish the approved certificates to all app | Essential | Input from Sasi/Ramesh - Refer mail dtd 25Jun
88 | OCSP/CRL | Desirable | Input from Sasi/Ramesh - Refer mail dtd 25Jun
89 | Zoning & Service segregation | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
90 | Protection against SIM Swap | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
91 | Protection against OTP SPAM | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
92 | All residents data should be stored in encrypted form | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
93 | All sensitive configuration should be stored in encrypted form | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
94 | Avoid enumeration of data | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
95 | Audit all changes to the data | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun
96 | Publicly publishable audits | Essential | Input from Sasi/Ramesh - Refer mail dtd 25Jun
97 | Non repudiable with timestamp service | Essential | Input from Sasi/Ramesh - Refer mail dtd 25Jun
98 | Anonymised publishable data | Vital | Input from Sasi/Ramesh - Refer mail dtd 25Jun

## Pre-registration
Story Backlog: Pre-registration
S.No. | Feature | Story Title | Issue key | Requirement Description | Issue Type | Category | Estimates - Incl. Testing (PDs) | Reporter | Comments | SK Comments | Priority | Current Status | Sprint
1 | UX Enhancement - MOSIP | UI Enhancement - IV & V: Provide a Cancel button and Cross button in all dialog boxes across Pre-registration | MOS-24695 | All dialog boxes across Pre-registration application should have a cross "x" button to allow user to navigate out of the dialog box | Story | NA | 0 | Resham.Chugani | Considered as part of MOS-25102 | OK
2 |  | UI Enhancement - IV & V: Fix the header of the Pre-registration UI application once logged in | MOS-24691 | Post login, the header/frame of Pre-registration application should be fixed and not get hidden on scrolling down | Story | NA | 0 | Resham.Chugani | Already fixed in current implementation | OK
3 |  | UI Enhancement - IV & V: Trigger "User Blocked" message in UI if user enters OTP incorrectly x times, as configured | MOS-24679 | On Login, in the event of the user entering the incorrect OTP, the application should render the appropriate functional message equivalent to “USER_BLOCKED” should be displayed in the UI, aligning with the OTP API - Message: “You have crossed the maximum attempts. Please retry after x mins” - Where x is configurable | Story | NA | 0 | Resham.Chugani | Already fixed in current implementation | OK
4 |  | UI Enhancement - IV & V: Provide a warning message prior to logging out a user on click of "Logout" | MOS-24678 | On click of Logout, provide a confirmation message to user to confirm logout action | Story | NA | 0 | Resham.Chugani | Already fixed in current implementation | OK
5 |  | Feedback suggestions from Sprint 9 Demo | MOS-20300 | Includes UX enhancements suggested during Sprint 9 demo: - Functional Change: Allow partial search in center selection page | Story | Desirable | 0 | Vyas.Vemuri | Already fixed in current implementation | OK
| UX Enhancement - MOSIP | padding & alignment of existing UI | MOS-26253 | padding & alignment of existing UI |  | Vital? | 25 |  |  |  | P1 | Development in progress | Sprint 13/14
6 | UX Enhancement - MOSIP | Place Holder for all UX Enhancements deliverable post June 30 Release | MOS-25102 | To accommodate UX revisions based on updated VDs | Story | Vital? | 235.25 | Rounak.Nayak |  | OK | P2 | Requirement pending
7 | UX Enhancement - GoM | NON-MVP: Location Hierarchy changes | MOS-14511 | To accomodate the Location Hierarchy changes as a part of the Demographic form, as per GoM requirement | Story | Vital | 10 | Vyas.Vemuri |  | Desirable, To be decided after GoM interactions | P2 | Requirement pending
8 | Removal of Applicant Type | NON-MVP: Removal of Applicant Type Mapping | MOS-22039 | Currently, documents required to be updated depend on the Applicant Type/Doc Category/Doc Type mapping setup by the admin. This story intends to remove this concept and adopt the process as per Reg. Client (Docs required to be uploaded are driven by fields filled) | Story | Desirable |  | Vyas.Vemuri |  | OK. Currently, functionally delivered as required. This can be accomodated only to bring in consistency in solutioning between Pre-registration & Registration Client
9 | Blacklisted Words Validation | NON-MVP: Blacklisted words Validator Integration | MOS-19541 | Inclusion of blacklisted words validation in both languages for Name and Address fields L1,L2,L3 fields of Demo form: On entry of a Blacklisted word the Individual should be alerted “XXX word(s) are not permitted in the ABC field by the system. Please correct it”. | Story | Desirable |  | Vyas.Vemuri |  | OK
10 | Configurability of Features | NON-MVP: Switching on/off of Features for Pre-Registration | MOS-15474 | Ability to switch on/off a feature | Story | Desirable |  | Vyas.Vemuri | Architects to further discuss | OK
11 | OCR for Document quality check | Non MVP:As the MOSIP Pre-Registration System, I should be able to perform OCR for Document quality check | MOS-13147 | Perform OCR validation on docs uploaded, to evaluate Doc quality, validate data of doc | Story | Desirable |  | Vyas.Vemuri | Architects to further discuss | OK
12 | Group Concept | Non MVP: Group Concept during Pre-registration | MOS-13133 | Include ability to make a group booking, by providing the total number of members in group | Story | NA |  | Resham.Chugani
13 | Reminders to Applicant | Non MVP: As a MOSIP System, I should be able to trigger reminder(s) to an individual prior to the booked appointment, as configured | MOS-13059 | Trigger reminder(s) to an individual, prior to the booked appointment | Story | Desirable |  | Resham.Chugani | Community contribution
14 | Login - With Username & Password | Non MVP: As an Individual, I should be able to login to the pre-registration application by providing the user ID (mobile/email) and password and OTP:UI | MOS-790 | Ability to login with Username & Password Currently - Login is possible only with Mobile/Email id - UI | Story | NA |  | Shwetha.Mruthyunjaya | Community contribution | OK, Community contribution
15 |  | Non MVP: As an Individual, I should be able to login to the pre-registration application by providing the user ID (mobile/email) and password and OTP | MOS-621 | Ability to login with Username & Password Currently - Login is possible only with Mobile/Email id - API | Story | NA |  | Shwetha.Mruthyunjaya | Community contribution | OK, Community contribution
16 | Password Management | Non MVP: As an Individual, I should be able to reset the password for the user ID:UI | MOS-791 | Ability to manage profile and reset password - API | Story | NA |  | Shwetha.Mruthyunjaya | Community contribution | OK, Community contribution
17 |  | Non MVP: As an Individual, I should be able to reset the password for the user ID | MOS-622 | Ability to manage profile and reset password - UI | Story | NA |  | Shwetha.Mruthyunjaya | Community contribution | OK, Community contribution
18 | Login - Include Captcha | Implementing Captcha in Login Screen | MOS-25103 | To accommodate captcha feature on Login page | Story | Vital | 6 | Rounak.Nayak | Task breakdown: For POC, code integration - 3days Unit Test case – 1day Testing in QA and defect fix – 2days | OK | P2 | Detailing pending | Sprint 15
19 | Application Status Enhancement | NON MVP: Pre-Registration Status changes - [Release 1.5] | MOS-19858 | This story is to accommodate change to the various statuses of Pre-registration - To be relevant to its own stage.EG: If docs and/or demo data is updated, the status is still Pending Appointment. Instead, the suggestion was to update it relevant to its respective stage, i.e., Demo Data Updated/Docs Uploaded - To be discussed and evaluated | Story | NA |  | Shwetha.Mruthyunjaya |  | OK
20 | Terminilogy Update | Remove all references to GoM specific terminologies | MOS-27308 | This story is to update the field names in Demographic page and across Pre-registration as below: 1. CNIE/EC Number - Change to “Reference Identity Number” 2. Local Administrative Authority - Change to “Zone” |  | Vital | 8 |  |  |  | P1 | Development in progress | Sprint 13/14
21 | Primary & Secondary Language - System behavior analysis/update | Primary & Secondary Language - System behavior analysis/update | MOS-27436 | Primary & Secondary Language - System behavior analysis/update |  | TBA

## Registration Client
Story Backlog: Registration Client
S.No. | Feature | Story Title | Issue key | Requirement Description | Issue Type | Category | Estimates - Incl. Testing (PDs) | Reporter | Comments | SK Commnets | Priority | Current Status | Sprint
1 | Age/DoB Calculation Display | New Registration - Age/Date of Birth: Display auto calculated value for each when the other is entered | MOS-21861 | New Registration - Age/Date of Birth:If we enter age, the DoB should display 01/Jan/xxxx. If we enter DoB, the age should be auto calculated and displayed. Both fields should remain editable. | Story | Vital | 6 | Akshaya.Rajagopal |  | OK | P1 | Detailing pending | Sprint 14
2 | Parent/Guardian Authentication - Multi factor | NON MVP:UI: As a registration officer, I should be able to authenticate each introducer based registration with their password/biometrics/multi factor elements. | MOS-1175 | Able to authenticate each introducer based registration with their password/biometrics/multi factor elements. | Story | NA |  | Taleev.Aalam |  | OK
3 |  | NON MVP:As the MOSIP registration client, I should enable introducer to authenticate each introducer based registration with password/biometrics/multi factor elements. | MOS-1320 | Enable introducer to authenticate each introducer based registration with password/biometrics/multi factor elements. | Story | NA |  | Taleev.Aalam |  | OK
4 | Biometric Capture - Device Manager Implementation | Device Tech Story - MOSIP Device Manager implementation - Part 1 | MOS-23070 | VDM technical specification to be adhered by the vendor to adopt their devices to the MOSIP platform to capture the biometric data and manipulate the same. | Story | Vital | 0 | Akshaya.Rajagopal | Will be taken care by vendor, hence no estimate provided | ok | P0 | Detailing pending | Sprint 15
5 | Biometric Capture - Device Service Integration | MOSIP device service integration story | MOS-22410 | MOSIP device manager integration story for 3rd party integration. | Story | Vital | 40 | Akshaya.Rajagopal | 15 PDS for development | ok | P0 | Detailing pending | Sprint 15
6 | Biometric Capture - Photo Validations & ICAO Standards check | Validations for photo in Registration client | MOS-23544 | Registration client needs to check for additional validations of the photo. The application must be able to detect if the photo is a live photo or not. Photo of a Passport photo must not be accepted. | Story | NA |  | Akshaya.Rajagopal | Community contribution - What pluggability should we provide? | OK
11 |  | As the MOSIP registration client, I should be able to perform face photograph validation during registration | MOS-16008 | Implement ICAO validations that are not implemented in MOS‌-16008: Plain light-coloured background Close up of the head and top of the shoulders so that the face takes up 70–80% of the photograph | Story | NA |  | Akshaya.Rajagopal | - Based on MDS implementation | OK
7 | Biometric Exceptions - Capture multiple docs/photos per exception type | As a Registration officer , I should be able to capture multiple Biometrics Exception Photos and upload documents to support exceptions | MOS-19011 | Capture Biometrics Exception Photo: 1. Provide ability to capture multiple photos based on each reason and for example, one photo for fingerprint and one photo for iris exception – Either refer or capture different photo for each exception 2. Provide ability to upload documents to support each exception | Story | Desirable |  | Akshaya.Rajagopal |  | OK
8 | Biometric Exceptions - Manually mark exception for low biometrics quality | Device - As the MOSIP Registration Client, I should be able to mark low quality biometrics as exceptions | MOS-15999 | Device story for marking low quality biometrics as exceptions | Story | NA |  | Akshaya.Rajagopal |  | OK
9 | Biometrics exception approval - Configuration if approval is required at one/two levels | Biometrics Exceptions Approval - One or two levels | MOS-13523 | In case of biometric exceptions, provide ability to configure if operator authentication is required at one or two levels | Story | NA |  | Akshaya.Rajagopal | Resham/Shrikant to re-check MOSIP’s ability to turn on/off SPVR authentication vs. GoM requirement on Supervisor authentication a. GoM Requirement: i. As per GoM’s FRS, GoM has two roles - operators and supervisors (collectively referred to as Enrolment Officers or EO). ii. In terms of EO Authentication at the end of each registration, the system should have provision for the capture of biometric of EO as a proof of confirmation of the following: • EO has performed enrolment • EO has verified the information • EO has followed prescribed procedure and guidelines iii. However, as per recent conversations, it was drawn that GoM doesn’t need Supervisor as a role – Hence, Supervisor authentication stage was made configurable b. MOSIP’s current ability to turn on/off SPVR authentication for exceptions: i. This is currently configurable. If turned off, the respective screen doesn’t appear ii. If turned on, the Supervisor auth screen appears – Currently one level of auth by Supervisor | OK
10 | Biometrics- Face capture with additional validations: Liveness check | Face photo capture | MOS-13522 | Requirements for face photo capture: Provide ability to capture live photo (Maybe a short video instead of a photo) Validate photo captured is a live photo - Do not allow Photo of a human photo (EG: Photo of a passport photograph) | Story | NA |  | Akshaya.Rajagopal | Community contribution - What pluggability should we provide? | ok
12 | Device/SDK Integration - Biometrics - Fingerprint quality ranking | Device--As the MOSIP Registration Client, I should provide ranking by fingerprint quality in the registration receipt | MOS-12187 | Device story for providing ranking by fingerprint quality in the registration receipt | Story | Essential? |  | Akshaya.Rajagopal | Subject to bandwidth | Ok
13 |  | Device--As the MOSIP registration client, I should enable capturing an individual's fingerprints as per quality threshold values defined. | MOS-1291 | Device story for capturing an individual's fingerprints as per quality threshold values defined. | Story | Essential? |  | Taleev.Aalam | Subject to bandwidth | OK
14 | Device/SDK Integration - Capture Parent's biometric for Child | Device--As MOSIP registration client, for new registration of child capture any one biometric of the Parent/Guardian | MOS-21701 | If age of the applicant is less than or equal to 5, capture any one biometric-fingerprint, IRIS of the parent/guardian. It could be any Parent/guardian – Same Parent/guardian as during registration or another Parent/guardian) | Story | Vital | 40 | Akshaya.Rajagopal | 20 - all bio type integration. | OK | P0 | Detailing pending | Sprint 15
15 | Device/SDK Integration - Login with Iris/Face | Device--As the MOSIP Registration Client, I should enable login with iris and face | MOS-12185 | During Login, multifactor authentication using username + password and/or OTP, fingerprint, iris. | Story | Vital | 40 | Akshaya.Rajagopal | 20 PDS for development | OK | P0 | Detailing pending | Sprint 15
16 | Scan PRID QR Code | As the MOSIP Registration Client, I should enable scanning a Pre-registration QR code | MOS-13556 | While starting a new registration, the registration client should support scanning a QR code to populate the pre-registration ID on screen | Story | Vital | 60 | Akshaya.Rajagopal | kernel + device dependencies | OK | P2 |  | Sprint 16
17 | Device/SDK Integration - Iris capture | Device--As the MOSIP registration client, I should enable iris capture as per defined specifications. | MOS-1205 | Device--As the MOSIP registration client, I should enable iris capture as per defined specifications. | Story | Vital | 70 | Taleev.Aalam |  | OK | P0 | Detailing pending | Sprint 15
18 | Device/SDK Integration - Lost UIN | Device - As a Registration Officer, I should be able to facilitate retrieving a lost UIN | MOS-18989 | Device story for lost UIN | Story | Vital | 48 | Vivek.Srinivasan |  | OK | P0 | Detailing pending | Sprint 15
19 | Device/SDK Integration - UIN Update | Device- UIN Update | MOS-15998 | Device story for UIN update | Story | Vital | 24 | Akshaya.Rajagopal |  | OK | P0 | Detailing pending | Sprint 15
20 | Device/SDK Integration - Registration Officer and Supervisor on-boarding | Device - As the MOSIP registration client, I should enable capturing an officer's biometrics during onboarding in order to support login, local duplicate checks and registration submission. | MOS-19001 | Enable capturing an officer's biometrics during onboarding in order to support login, local duplicate checks and registration submission. | Story | Vital | 40 | Akshaya.Rajagopal |  | OK | P0 | Detailing pending | Sprint 15
21 |  | Device- Operator On-boarding - Biometrics capture 1: Validate quality before authentication | MOS-22161 | Operator On-boarding - Biometrics capture: | Story | Vital | 10 | Akshaya.Rajagopal |  | OK | P0 | Detailing pending | Sprint 15
22 |  | Operator On-boarding - Photo capture: Remove exception photo capture | MOS-22005 | The exception photo should not be captured | Story | Vital | 4 | Akshaya.Rajagopal |  | OK | P0 | Detailing pending | Sprint 15
23 | Device/SDK Integration - Registration Officer authentication | Device--As the MOSIP Registration Client, I should enable RO to authenticate each registration with biometrics/multi factor elements | MOS-1334 | Enable RO to authenticate each registration with biometrics/multi factor elements | Story | Vital | 60 | Taleev.Aalam |  | OK | P0 | Detailing pending | Sprint 15
24 | Device/SDK Integration - UIN update-Scan QR code | Device- As the MOSIP Registration Client, I should be able to scan a QR code for UIN Update | MOS-19014 | UIN Update: i. Provide ability to scan QR code besides manually entering UIN number - New requirement ii. Additionally, pre-populate data from QR code (if available), based on option selected for update (EG: If address is marked for update, then address to be pre-populated from QR code). Implementation aspects to be discussed - New requirement iii. Evaluate if CNIE/UIN/EC Number Update is required, as if the number captured is incorrect, packet processing would have failed | Story | Desirable |  | Akshaya.Rajagopal |  | Desirable
25 | Device/SDK Integration - Display device status | Device-As the MOSIP Registration Client, I should display the status of each device on the header | MOS-13562 | Display the device statuses on the client as green/red indicators in the header. | Story | NA |  | Akshaya.Rajagopal | To be deleted: Duplicate of MOS-15996
26 | Device/SDK Integration - Local duplicate check for iris and face | Device--As the MOSIP Registration Client, I should perform a local duplicate check for irises and face of an individual against the mapped registration officers' biometrics | MOS-10555 | Perform a local duplicate check for irises and face of an individual against the mapped registration officers' biometrics | Story | Vital | 40 | Akshaya.Rajagopal |  | OK | P0 | Detailing pending | Sprint 15
27 | Stubbed/MDS Implementation - Display device status | Stub - Device status: Display device status on the header | MOS-15996 | This is the proxy (stubbed) implementation of MOS‌-13562 to display the device statuses on the client as green/red indicators in the header. | Story | Essential |  | Akshaya.Rajagopal | If MDS is implemented, this will be implied | OK
28 | Validation Checklist - Ability to validate each field/stage of registration/Update (EG: DoB Verification) | UI: As the Registration Officer, I should be able to mark an individual's date of birth as 'Verified' | MOS-14566 | Mark an individual’s date of birth as ‘Verified’ during new registration or UIN update. | Story | NA |  | Vivek.Srinivasan | Community contribution | OK
29 |  | As the MOSIP Registration Client, I should enable marking an individual's date of birth as 'Verified'. | MOS-14565 | Mark an individual’s date of birth as ‘Verified’ during new registration or UIN update. | Story | NA |  | Vivek.Srinivasan | Community contribution | OK
30 | Introducer attestation (Introducer concept) | NON MVP:Document Upload/Scan - Introducer Attestation (Others) | MOS-5482 | As a client registration officer, I should be able to upload/scan applicable documents of an introducer(Others), during registration of an applicant | Story | Desirable |  | Akshaya.Rajagopal | This is already covered by virtue of having Parent/Guardian introducing a Child - MOSIP in any case doesn't maintain relationships | OK
31 |  | NON MVP:As the MOSIP registration client, I should enable uploading/scanning applicable documents of an introducer (Others) during registration of an individual. | MOS-1382 | Should enable uploading/scanning applicable documents of an introducer (Others) during registration of an individual. | Story | Desirable |  | Vivek.Srinivasan | This is already covered by virtue of having Parent/Guardian introducing a Child - MOSIP in any case doesn't maintain relationships | OK
32 | Geo-location capture using phone | Geo-location Capture using GPS:Usage of phones for GPS | MOS-19006 | Geo-location Capture using GPS:1. Usage of phones for GPS vs. GPS on machine | Story | Desirable |  | Akshaya.Rajagopal | Community contribution | OK
33 | Location Hierarchy Update as per GoM | As the MOSIP Registration Client, I should support the new Location Hierarchy | MOS-16544 | Reflect the new location hierarchy for Morocco | Story | Vital | 40 | Akshaya.Rajagopal | Currently Desirable, Dicussion with GOM can change these. | Currently Desirable, Dicussion with GOM can change these. | P2 |  | Sprint 16
34 | Login/Authentication - Token to authenticate RO | Tech story - Registration Client should send a token to Registration processor, when Officer or Supervisor authenticate themselves during Packet Creation | MOS-21523 | Registration Client should send a Token to Registration processor, when Officer or Supervisor authenticate themselves during Packet Creation | Story | Desirable |  | Akshaya.Rajagopal | Community contribution | OK
35 | Multi factor login - With Biometrics | NON MVP:As the MOSIP registration client, I should enforce multi factor login for Admin/Reg. users | MOS-8368 | Enforce multi factor login for Admin/Reg. users | Story | Desirable |  | Vivek.Srinivasan |  | Desirable
36 | OCR Document upload | NON MVP:OCR as part of Document Upload | MOS-12176 | MOSIP should support OCR as part of quality check of documents during document upload. | Story | Desirable |  | Akshaya.Rajagopal | - Since this is a reference implementation, SI can implement as requried | OK
37 | Operator onboarding - Training content | Operator On-boarding: Placeholder for training content | MOS-21998 | Operator On-boarding: The landing page should have a placeholder for training content. UX team to come up with the design. - Placeholder for Link on Login page/home page to the training content - URL to be made available from Config file | Story | Vital | 30 | Akshaya.Rajagopal |  | OK | P1 | Detailing pending | Sprint 14
38 | Proof of consent document (GoP requirement) | NON MVP: As a Registration Officer, I should be able to capture Proof of Consent Document as required | MOS-18100 | As a Registration Officer, I should be able to capture Proof of Consent Document as required | Story | Desirable |  | Resham.Chugani | SI implementation | SI /community - Dsirable, Proof of concent via Document Categories Master.
39 | Reports | As the MOSIP Registration Client, I should enable generation of end of day reports | MOS-1309 | Include statistics on EoD Approval and Re-registration only | Story | Desirable |  | Taleev.Aalam | SI implementation | OK
40 |  | UI: As a supervisor, I should be able to generate reports. | MOS-1275 | Include statistics on EoD Approval and Re-registration only | Story | Desirable |  | Taleev.Aalam | SI implementation | OK
41 | Supervisor's/an authorized user's ability to unlock a locked account - GoM requirement | <Non MVP>:As a Supervisor, I should be able to unlock a user's account on the Registration Client. | MOS-12199 | Supervisor or Admin to unlock a user’s account that has been locked due to five consecutive unsuccessful login attempts. | Story | Desirable |  | Akshaya.Rajagopal | Community contribution | Desirable, No Use case, Community Contribution, Check with GOM Requirent, else Desirable.
42 | Transliteration in other languages | <NON MVP >UI: As a registration officer, I should be able to view transliterated data - other than French and Arabic | MOS-1288 | Able to view transliterated data - other than French and Arabic | Story | Desirable |  | Taleev.Aalam | - Re-factor for pluggability - Move to UI - Standardize interface | OK
43 |  | <NON MVP>As the MOSIP registration client, I should enable viewing transliterated data. - Other than French and Arabic | MOS-1293 | Enable viewing transliterated data. - Other than French and Arabic | Story | Desirable |  | Taleev.Aalam | - Re-factor for pluggability - Move to UI - Standardize interface | OK
44 | UIN update - VID input to initiate process | As the MOSIP registration client, I should support input of VID during the UIN Update process | MOS-18319 | As a MOSIP registration client, I should support input of VID to initiate UIN Update | Story | Essential? |  | Vivek.Srinivasan | Subject to bandwidth - Reputational impact as per Anadi | ok
45 | UIN update - OTP authentication of UIN holder in real-time (Online mode) | As the MOSIP registration client, I should support OTP authentication of the individual for UIN update | MOS-19739 | Support OTP authentication of the individual for UIN update | Story | Desirable |  | Vivek.Srinivasan |  | OK
46 | UX Enhancement- MOSIP | Home page: News and Updates to be editable from Admin portal | MOS-22011 | The content in the 'news and updates' section should be configurable. The Admin should be able to add text content through the Admin portal, such as news, announcements, links and training material, and sync to display on the reg. client. | Story | Essential | 10 | Akshaya.Rajagopal | Continue with UX VD enhancement track | Can be made essential and moved to SI work
47 | UX Enhancement- MOSIP | EoD Process 3: Optimize Approve and Reject buttons | MOS-22008 | The 'Approve' and 'Reject' actions should be placed closer to the list. Suggestion - provide 'tick' and 'cross' buttons on each row in the list. Buttons will be greyed out by default and become active when the row is selected. | Story | NA | 6 | Akshaya.Rajagopal |  | Covered as part of MOS-26779
48 | UX Enhancement- MOSIP | Proxy Operator On-boarding - Biometrics capture 1: Validate quality before authentication | MOS-22000 | When a biometric is captured, validate that its quality meets the threshold before sending to server for authentication. | Story | Essential | 6 | Akshaya.Rajagopal |  | OK
49 | UX Enhancement- MOSIP | New Registration - Consent: Additional consent attributes | MOS-21924 | Additional attributes for seeking consent. | Story | NA | 0 | Akshaya.Rajagopal |  | Requirement not applicable. To be deleted
50 | UX Enhancement- MOSIP | EoD Process 2: Optimize acknowledgement slip display | MOS-22007 | The acknowledgement slip should be smaller - no scrolling should be required. | Story | Essential | 10 | Akshaya.Rajagopal |  | Can be made Essential and moved to SI work
51 | UX Enhancement- MOSIP | New Registration - all screens 3: RHS progress bar and navigation between screens | MOS-21923 | New Registration - all screens: a. RHS progress bar - can we make them links? Implement if feasible. User should be able to jump to any page using RHS and top navigation links. b. Validations - all validations should happen on the preview page when user tries to submit. Display a consolidated error message highlighting which pages have errors. User should be able to jump to the page having errors, make the changes and jump back to preview | Story | NA | 0 | Akshaya.Rajagopal |  | Covered as part of MOS-26779
52 | UX Enhancement- MOSIP | New Registration - Address spacing to be optimized | MOS-21870 | The address is too spaced out. Utilize the space better. | Story | NA | 0 | Akshaya.Rajagopal |  | Covered as part of MOS-26779
53 | UX Enhancement- MOSIP | Operator On-boarding-Exceptions: Display only iris exceptions for Morocco | MOS-21999 | Operator On-boarding - Exceptions:Morocco screens will capture only irises and not fingerprints. Create a new screen showing iris exceptions aligned at the centre. Similarly if a country captures fingerprints only, the fingerprint exception images should be centre aligned. | Story | NA | 0 | Akshaya.Rajagopal |  | Covered as part of MOS-26779
54 | UX Enhancement- MOSIP | EoD Process: As the MOSIP Registration Client, I should display the EoD process with the first packet selected by default | MOS-22006 | The first packet in the EoD process page should be selected by default so that the number of mouse clicks is reduced. |  | NA | 0 |  |  | Covered as part of MOS-26779
55 | UX Enhancement- MOSIP | Login--UI changes 2: Forgot password should be a link | MOS-21997 | Forgot password should be a link | Story | Vital | 0 | Akshaya.Rajagopal |  | Covered as part of MOS-26779 | P1 | Detailing pending | Sprint 14
56 | UX Enhancement- MOSIP | New Registration - all screens: Optimize scroll bar | MOS-21887 | Optimize the vertical scroll bar and ensure scrolling is kept as minimum as possible. | Story | Essential | 0 | Akshaya.Rajagopal | Continue with UX VD enhancement track | Covered as part of MOS-26779
57 | UX Enhancement- MOSIP | New Registration - Biometric exceptions: Exception marking on same screen as documents | MOS-21888 | New Registration - Biometric exceptions:Explore the option of having the exception marking on the same screen as the document upload. Utilize the space on the right. | Story | NA | 0 | Akshaya.Rajagopal |  | Covered as part of MOS-26779
58 | UX Enhancement- MOSIP | Login--UI changes 1: Forgot username | MOS-21996 | Login:If the RO forgets user name - provide a link to the Admin portal so that the user can retrieve the username | Story | NA | 0 | Akshaya.Rajagopal |  | Covered as part of MOS-26779
59 | UX Enhancement- MOSIP | New Registration - Acknowledgement: Print two copies on a single A4 sheet | MOS-21926 | The acknowledgement printout should fit on half an A4 page. Upon click of print, the acknowledgement should be mirrored and the Registration officer should be able to print two copies on a single A4 sheet. | Story | NA | 20 | Akshaya.Rajagopal |  | SI customization
60 | UX Enhancement- MOSIP | New registration all screens UI changes - links in the top menu should be clickable | MOS-21860 | New registration all screens UI changes - links in the top menu should be clickable | Story | NA | 20 | Akshaya.Rajagopal |  | Covered as part of MOS-26779
61 | UX Enhancement- MOSIP | Place Holder for UX Enhancements deliverable Post June 30 Release | MOS-25101 | This Story is just a Place holder for all the UX Enhancements which would be delivered post-June 30. | Story | NA | Needs estimation | Rounak.Nayak |  | Covered as part of MOS-26779
62 | UX Enhancement- MOSIP | Implementing Captcha in Login Screen | MOS-25104 | Implementing Captcha in Login Screen | Story | Essential | 20 | Rounak.Nayak |  | Can be moved to Security and they can take a call. This is not a enhancement.
63 | UX Enhancement- MOSIP | New Registration - Biometric screens 3: Redesign 'Scan' and 'Start Over' buttons | MOS-21922 | a. 'Start Over/Reset' buttons: what happens on click? Revisit the flow.b. 'Scan' button - instead of having the button at the bottom, provide a scan icon on the slap image itself for each biometric. | Story | NA | 20 | Akshaya.Rajagopal |  | Covered as part of MOS-26779
| UX Enhancement- MOSIP | New Registration - Biometric screens 2: Navigate through the screens in any order | MOS-21921 | New Registration - all screens: RO should be able to go back and forth between demographic, document and biometric screens. Retain the captured data in each screen. For biometrics - retain data whenever possible i.e. for those biometrics not marked as exceptions. | Story | NA | 60 |  |  | Covered as part of MOS-26779
| UX Enhancement- MOSIP | Padding and alignment related changes | MOS-25989 | Padding and alignment related changes | Vital | Vital/NA? | 30 |  |  | TF to log as bug - To be deleted from here & consolidated sheet. | P1 | Detailing pending | Sprint 14
64 | UX Enhancement- MOSIP | ux Enhancement- Additional enhancements based on revised VDs | MOS-26779 | Enhancement- Additional enhancements based on revised VDs | Story | Vital | 400 | Akshaya.Rajagopal |  | What is this for, where are the details. | TBD | Detailing pending | Sprint 15
65 | UX Enhancement- MOSIP | New Registration - Transliteration: Virtual keyboard icon placement to be optimized | MOS-21863 | New Registration - Transliteration: The virtual keyboard icon is repeated three times. Can we make it appear in just one place? The keyboard should be available for both Primary and Secondary language. Placement of the keyboard icons can be driven by the UX team (EG: A common icon/placement of cursor to define the language) | Story | NA | 20 | Akshaya.Rajagopal |  | Covered as part of MOS-26779
66 | UX Enhancement- MOSIP | New Registration - Biometric exceptions 3: Exception page to display irises only | MOS-21920 | Exception page to display irises only | Story | NA | 8 | Akshaya.Rajagopal |  | Covered as part of MOS-26779
67 | UX Enhancement- MOSIP | New Registration - Biometric exceptions 2: Exception finger marking should not colour the entire finger | MOS-21897 | Exception finger marking should not colour the entire finger | Story | NA | 6 | Akshaya.Rajagopal |  | Covered as part of MOS-26779
68 | UX Enhancement- MOSIP | New Registration - Demographic fields: Optimize numeric and master data fields that are displayed twice | MOS-21873 | New Registration - Demographic fields: Optimize numeric and master data fields that are displayed twice | Story | NA | 12 | Akshaya.Rajagopal |  | Covered as part of MOS-26779
69 | UX Enhancement- MOSIP | Upload packet 2: Reduce table width | MOS-22013 | Upload packet:The width of the table should be reduced and not run across the entire page. | Story | NA | 10 | Akshaya.Rajagopal |  | Covered as part of MOS-26779
70 | UX Enhancement- MOSIP | Enhancement- Save to device UI | MOS-26151 | Save to device: The UI should be enhanced such that it is clear for the RO that save to device cannot be done for selected packets | Story | NA | 20 |  |  | Covered as part of MOS-26779
70
71 | VID management - Allow input of VID for UIN services rendered at Registration Center | As a MOSIP registration client, I should support VID management | MOS-18483 | VID management - Reference Shrikant: - Ability to provide resident services featrues through Reg. Centre (Revoke VID etc) The use of Reg client is inherently inconvenient, since it involves person to come to a centre and should be used where BIOMETRICS is mandatorily being worked with. VID is only a text data, thus it should be handled only through a public portal interface. The public portal will always need some form of OTP authentication. Thus a mobile/email mandatory comes into a requirement. Thus we can issue VID without mobile, but managing VID lifecycle will need Mobile (for OTP). Not having a mobile as a reason should not be used to consider VID management via reg client. If we are moving to a advanced concepts like VID, expectation of Mobile as mandatory is only practical reality. Review this logic at suitable time, incase VID management via Reg client is contemplated in future versions. An exception to above thinking, which can asked is why is MOBILE No (demographic data) update recommended via Reg Client or with biometric - (a). Mobile is gateway to many services and loss of unlocked mobile can lead to many subsequent losses (including identity theft) thus mobile update is always recommended via Biometric auth. Intermediate STOP point (b) OTP based mobile updated can easily move one lost mobile to another unlown mobile (c) Many such scenarios. | Story | Desirable |  | Akshaya.Rajagopal |  | OK
72 | Windows Installation script | Windows Installation Script for Registration Client Installation | MOS-22423 | Windows Installation Script for Registration Client Installation - Batch script | Story | Desirable | 100 | Amandeep.Khanuja |  | OK
73 | Download pdf option | Enhancement- Download pdf option in Reg client | MOS-26354 | Able to download acknowledgement as a pdf using “Download pdf” button |  | Essential
74 | Terminology Update | Remove all references to GoM specific terminologies | MOS-27321 | This story is to update the field names in Demographic page and across Registration Client as below: 1. CNIE/EC Number - Change to “Reference Identity Number” 2. Local Administrative Authority - Change to “Zone” |  | Vital |  |  |  |  | P1 | Detailing pending | Sprint 14
75 | Disk space check should be done on Reg Client before registering a user | Disk space check should be done on Reg Client before registering a user | MOS-27238 |  |  | Vital |  |  |  |  | P1 | Detailing pending | Sprint 14
76 | Primary & Secondary Language - System behavior analysis/update | Primary & Secondary Language - System behavior analysis/update | MOS-27437 | Primary & Secondary Language - System behavior analysis/update |  | TBA

## Registration Processor
Story Backlog: Registration Processor
S.No. | Feature | Story Title | Issue key | Requirement Description | Issue Type | Category | Estimates - Incl. Testing (PDs) | Reporter | SK Comments | Mindtree Comments for Effort Estimation | Priority | Current Status | Sprint
1 | Resident Services Dependency | As Registration Processor, I should be able to find a LOST UIN/RID when requested from Resident Portal | MOS-24767 | Retriving a LOST UIN/RID when requested from Resident Services | Story | Vital | 76 | Rounak.Nayak | ok | Task Breakdown 1. Development due to batabase changes to hold email, mobile 2. Impact on the existing flows due to new fields 3. API development 4. Integration efforts for all scenerios 5. Security 6. Logging & Auditing | P1 | Story approved | Sprint 15
2 | Resident Services Dependency | As Registration Processor, I should be able to receive the UIN/VID and provide the e-UIN as response | MOS-24108 | Retriving a E-UIN Card using UIN/VID when requested from Resident Services | Story | Vital | 24 | Rounak.Nayak | ok | Task Breakdown 1. API development 2. Integration with ID repo to get response 3. Security 4. Logging & Auditing Dependency ID Repo to Provide ID Object from VID | P1 | Story approved | Sprint 15
3 | Resident Services Dependency | As Registration Processor, I should be able to get the Status of a UIN based on a RID for Resident Services | MOS-24107 | Retriving Status of Packet using RID when requested from Resident Services | Story | Vital | 0 | Rounak.Nayak | ok | No Development Needed - Feature Already Exists | NA | Story approved
4 | Resident Services Dependency | As Registration Processor, I should be able to process Update Packet coming from Resident Services | MOS-24106 | Update Individual's Demographics when requested from Resident Services | Story | Vital | 40 | Rounak.Nayak | ok | Task Breakdown 1. Configuration to identify fields to be edited 2. Validation based on the configuration 3. API development 4. Camel configuration 5. Security 6. Logging & Auditing | P1 | Story approved | Sprint 15
5 | Resident Services Dependency | As Registration Processor, I should be able to Receive and Process a Re-Print Request for a UIN from Resident Services | MOS-24104 | Sending UIN Card for Printing using UIN when requested from Residnet Services | Story | Vital | 56 | Rounak.Nayak | ok | Task Breakdown 1. API for print request 2. Camel flow configuration 3. Update validation logic 4. Integration testing 5. Security 6. Logging & Auditing | P1 | Story approved | Sprint 14
6 | Resident Services Dependency | As Registration Processor, I should be able to provide a Resident an External Link to Download a Password Protected UIN Card | MOS-24943 | Reg Proc should be able to provide an external link so that Resident should be able to download a Password protected UIN card | Story | Vital | 76 | Rounak.Nayak | ok | Task Breakdown 1. 2 API development 2. Encription, Decription of URL data 3. Fetch data from ID repo 4. Security implementation 5. Security 6. Logging & Auditing | P1 | Story approved | Sprint 15
7 | Admin Requirement | Send Packet Status History of a Packet Using RID | MOS-23848 - Gap and basis of estimate to be rechecked | Send Packet Status history of a Packet using RID when requested from Admin | Story | Vital | 44 | Rounak.Nayak | ok | Task Breakdown 1. API development 2. Configuration to hold message id and message (language specific) 3. Messages to be send in primary language 4. Service and DAO to fetch records 5. Security 6. Logging & Auditing | P1 | Story approved | Sprint 14
8 | Enhancement | Password Protected UIN Card to be Sent for Printing and Text File should have Password | MOS-23306 | Send Password Protected UIN Card to Printing Queue. In Current implementation UIN Card is not password protected. | Story | Essential | 12 | Rounak.Nayak | Description updated - This was an internal observation from Security perspective - To password protect the pdfs sent to Print & postal queue | Task Breakdown 1. Security 2. Logging & Auditing 3. Service to add password protected security Dependency Kernel to Provide Password in PDF
9 | Bio-dedupe for Parent/Guardian instead of Auth | Implementing Bio-Dedupe for Parent or Guardian Authentication | MOS-22034 | For Authentication of Introducer - Bio Dedupe could be used instead of IDA because Child registration would fail if Officer captures wrong UIN/RID of Introducer or Introducer UIN generation has failed. | Story | Desirable |  | Rounak.Nayak | ok
10 | Token to authenticate Operator during packet creation | Implementing Officer Supervisor Token for Officer Supervisor Validation | MOS-22032 | A Token can be used to Authenticate Officer and Supervisor in Registration Processor when they use OTP or Password based authentication in Reg Client when they create a Packet. | Story | Desirable |  | Rounak.Nayak | ok
11 | On-Hold scenarios implementation | Implementing On-Hold Scenarios for Registration Processor | MOS-22030 | If a packet validation fails then instead of rejecting the packet registration processor should flag the packet and process it. Just before UIN allocation - these flaged packets should be verified by a manual intervention and UIN should get allocated based on the verifier's decision. | Story | NA |  | Rounak.Nayak | OK - Community contribution
12 | GoM requirement - Update Request from External System: Combine Two Packets and Create a Third Packet - Perform Check Sum Validation | As Registration Processor, I should be able to Combine Two Packets and Create a Third Packet and I should be able to Perform Check Sum Validation on the Merged Packet using Two Other Packets | MOS-21755 | Reg Proc should be able to Merge two Packets and create a third packet. After merging the packet, reg proc should calculate the check of the merged packet using the check sum of the initial packets. | Story | Vital | 110 | Rounak.Nayak | ok | Task Breakdown 1. Security 2. Logging & Auditing 3. Dummy system to generate external packet, encryption & description 4. Validation of external packet 5. Virous scan and upload of packet in HDFS 6. Merging of external packet and create new merged packet 7. Check sum validation of merged packet 8. Validate and Store merged packet in HDFS 9. Interface to get merged packets from all stages Need More Clarity On 1. Data to be Considered as part of External Packet 2. Clarity on failure scenerio, when to fetch external packet, scenerio for update, activate-deactivate | P3 | Detailing pending
13 | SDK Integration - Minutiae extraction | Tech Story - Integrating with Actual SDK for Minutiae Extraction | MOS-17805 | Reg proc should be able to intergate with an actual device to extract minutiae of a Fingerprint Image File | Story | Vital | 2 | Rounak.Nayak | ok |  | De-scoped | NA
14 | SDK Integration - Biometric quality score | Tech Story - Integrating with Actual SDK for Quality Check | MOS-17610 | Reg Proc should be able to integrate with an actual device to get the quality score of a biometric image file. | Story | Vital | 2 | Rounak.Nayak | ok |  | P2 | Tech story
15 | SDK Integration - Real Finger valiadtion | Implement Finger Print Quality Checks to categorize FP as Real Finger, Finger of Same Person | MOS-8460 | Reg Proc should be able to integrate with SDKs that perform validations to check if captured biometrics is of a Real Finger and Finger of the Same person | Story | Vital | 40 | Rounak.Nayak | ok | Need More Clarity 1. Does sdk provide this functionality? 2. No dependent story in ID repo, Reg. Client as same validatio need to be done in client 3. Need more clarity on SDK. 4. Reestimated once get more details on SDK | P3 | Detailing pending
16 | SDK Integration - Photo/Age/Gender validation | Implementing Automated Age/Gender/Photo Validation | MOS-1082 | Reg Proc should be able to integrate with a SDK to perform Photo/Age/Gender validations | Story | Desirable |  | Rounak.Nayak | SI customization
17 | ABIS - One ABIS, multi-modal | Implementing ABIS - One ABIS, multiple-modalities | MOS-26088 | Integrating with the ABIS Vendor who Supports Multiple Modalities i.e. Face, Finger and Iris | Story | Vital | 84 |  | ok | Task Breakdown 1. Security 2. Logging & Auditing 3. XSD validation based on version 2 4. ISO image validation 5. Integration with ABIS vendor 6. Finalize CBEFF structure 7. Update existing code once CBEFF strcture is finalized Add On Points 1. Estimation done based on assumption. The requirement is not clear. 2. Schame validation, iso image validation, design changes on insert /identify is in scope? 3. There will be changes in ID repo and Reg. Clinet which are also need to be estimated | P1 | Tech story | Sprint 14
18 | Multi-partner ABIS - One ABIS per modality | Implementing Multiple ABIS for MOSIP | MOS-1097 | Reg Proc should be able to integrate with Actual as well as multiple ABISs | Story | Essential |  | Rounak.Nayak | ok
19 | Multiple ABIS with all modalities |  |  |  |  | Desirable |  |  | ok
20 | Auto-deactivation of UIN | As the MOSIP System, I should be able to automatically deactivate UIN as required/configured | MOS-1085 | Reg Proc should be Auto Deactivate UINs | Story | NA |  | Rounak.Nayak | SI customization
21 | OCR Implementation for Doc quality check | Implement OCR Validation in ID Object for Quality Check | MOS-1081 | Reg Proc should be able to integrate with a SDK to perform OCR Validation of ID Object Fields using Documents | Story | Desirable |  | Rounak.Nayak | OK
22 | Integrating with Universal ID Schema Validator | Tech Story - Integrating with Universal ID Schema Validator | MOS-24944 | Reg Proc should be able to integrate with ID Schema Validator | Story | Done |  | Rounak.Nayak | To be deleted
23 | Archival of rejected packet | As Registration Processor, I should archive a packet which is Marked as rejected by the Supervisor | MOS-25374 | Reg Proc should be able to process a Packet rejected by Supervisor | Story | Desirable |  | Rounak.Nayak | Requirement Clarity required between title and Description. Chck if its already done
24 | Extract Bio-metric Data and Store it IDA Database for Authentication | As Registration Processor, I should be able to Extract Bio-metric Data and Store it IDA Database for Authentication | MOS-21733 | Reg Proc should be able to seed UIN/VID/ID Object and Biometric data of an individual to IDA after UIN Generation, Data Updation in ID Repo. | Story | Essential |  | Rounak.Nayak | OK
25 | Data maintainance in DB for Analytics & Reporting and Audit Log Changes/Storage | Inserting Meta Data in DB which are Required for Analytics & Reporting and facilitate Audit logging/storage/changes | MOS-18400 - Need discussion with Ramesh on approach | - Data maintenance in DB for Analytics & Reporting - Reg Proc should be able to store meta data in DB for sending it for analytics - Audit Changes - Reg. Proc. should be able to make changes to Audit implementation if there are any changes to Audit Fields - Audit log storage - Reg Proc should be able to store audit logs of a Packet received from Registration Client, in Audit table - Audit data to Analytics system - Weak/Strong Mobile Identification - Reg proc should be able seed audit data to an Analytics system to identify a Weak or Strong Mobile Number | Story | Vital | Need More Clarity | Rounak.Nayak | OK | Need More Clarity as the requierment is not clear 1. Save audit log from reg client 2. Save metadata in table 3. add new record in audit table | P2 | Detailing pending
26 | Audit changes | Tech Story - | MOS-15521 | Reg Proc should be able to make changes to Audit implementation if there is any changes to Audit Fields | Story | NA |  | Rounak.Nayak | Merged with to MOS-18400. To be addressed together
27 | Audit log storage | As Registration Processor, I should be able to store the Audit Logs of a Packet received from Registration Client | MOS-25375 | Reg Proc should be able to store audit logs of a Packet received from Registration Client, in Audit table. | Story | NA |  | Rounak.Nayak | Merged with to MOS-18400. To be addressed together
28 | Audit data to Analytics system - Weak/Strong Mobile Identification | As Registration Processor, I should be able to send audit data to a Analytics system to identify Weak or Strong Mobile Number | MOS-25648 | Reg proc should be able seed audit data to an Analytics system to identify a Weak or Strong Mobile Number | Story | NA |  |  | Merged with to MOS-18400. To be addressed together
29 | First user registration | As Registration Processor, I should be able to register the First User in MOSIP System | MOS-25398 | Reg Proc should be able to register the 1st User in MOSIP without any Supervisor and Officer validation | Story | Essential |  | Rounak.Nayak | OK
30 | Remove notification to Reg. Client to inform individual to re-register, when Reg. processor in any case triggers notification to individual | Non-MVP: Packet Processing Flow Change - Remove notification to Reg. Client to inform individual to re-register | MOS-26406 | Non-MVP: Packet Processing Flow Change - Remove notification to Reg. Client to inform individual to re-register, when Reg. processor in any case triggers notification to individual |  | Desirable |  |  | Refernce mail from Shrikant on 26Jun - PF review feedback mail
31 | Configurability to include/exclude VID Issuance for every UIN | Non-MVP: Configurability to include/exclude VID Issuance for every UIN | MOS-26743 | Country should be able to flag to include/exclude VID issuance on generation of each UIN. Currently - VID issuance for every UIN is hard coded. |  | Desirable |  |  | Reference mail from Sasi/Ramesh on 02Jul - SUB: RE: UIN privacy policy
32 | UIN Card | Include Perpetual VID in UIN Card | MOS-26758 | VID Should be displayed in UIN Card | Story | Vital? | 16 |  |  | Task Breakdown 1) Code Changes to read the Perpetual VID from ID Response 2) Changes in Template 3) Audit Logging 4) Security Dependency IDA to provide Perpetual VID for a RID/UIN | P1 | Tech story | Sprint 15
33 | Refactoring of MOSIP repository | NA | NA | Refactoring of MOSIP repository | Task | Vital | 10 |  |  |  | NA | Done
34 | Upload Portal for Registration packets | NA | NA | Includes disabling "Save to Device" option until the upload portal is provided | Task | Vital | Need More Clarity |  |  | Need More Clarity | P3 | Detailing pending
35 | ABIS Integration | Tech Story - Adding Reference URL in ABIS Identify Request | MOS-27241 | Adding Reference URL in ABIS Identify Request | Story | Vital | 3 |  |  |  | P1 | Tech story | Sprint 14
36 | ABIS Integration | Tech Story - Integrate with ABIS 1:1 Authentication API | MOS-27242 | Integrate with ABIS 1:1 Authentication API | Story | Vital | Need More Clarity |  |  | Yet to analyze for estimates | P1 | Tech story | Sprint 15
37 | UIN Card | Tech Story - Print UIN Card with Masked UIN | MOS-27274 | Print UIN Card with Masked UIN | Story | Vital | 0 |  |  | Will be taken Care in Re-Printing | P1 | Tech story | Sprint 15
38 | Printing and Postal Service | Tech Story - Send RID with UIN Card to Printing and Postal Service Provider | MOS-27328 | Send RID with UIN Card to Printing and Postal Service Provider | Story | Vital | 3 |  |  |  | P1 | Tech story | Sprint 14
39 | Termininology Update in ID Object | Tech Story - Terminology Change for CNIE/EC Number and Local Administrative Authority | MOS-27342 | Terminology Change for CNIE/EC Number and Local Administrative Authority | Story | Vital | 3 |  |  |  | P1 | Tech story | Sprint 15
40 | Packet Generator | Tech Story - Move Packet Generator to Secure Zone | MOS-27343 | Move Packet Generator to Secure Zone | Story | Vital | 5 |  |  |  | P1 | Tech story | Sprint 14
41 | Activate/De-Activate | Remove Additional Validation for Activate and De-Activate Packets in Packet Validator Stage | MOS-27987 | Remove Additional Validation for Activate and De-Activate Packets in Packet Validator Stage | Story | Vital | 2 |  |  |  | P1 | Tech story | Sprint 14
42 | Camel Bridge | Update Camel Route Condition for Internal Error - FALSE for sending notification for all stages | MOS-27988 | Update Camel Route Condition for Internal Error - FALSE for sending notification for all stages | Story | Vital | 1 |  |  |  | P1 | Tech story | Sprint 14
43 | Update Flow | Validate if UIN is Active before performing any Update Operation on the UIN | MOS-27818 | Validate if UIN is Active before performing any Update Operation on the UIN | Story | Vital | 1 |  |  |  | P1 | Tech story | Sprint 14

## ID-Authentication
Story Backlog: ID-Authentication
S.No. | Feature | Story Title | Issue key | Requirement Description | Issue Type | Category | Estimates - Incl. Testing (PDs) | Reporter | Comments | SK Comments | Prioritisation on <07 15> | Current Status | Sprint
1 | Analytics Module Feature - UINs for Auth Failure | As the MOSIP System, I should be able to provide hashed UINs for repeated auth failures to analytics system | MOS-25615 | To provide Analytics module the hashed UINs of successive authentication failures- statement the audit log | Story | Vital | 0 | Taleev.Aalam |  | OK | P2 | Detailing Pending Analytics Module Not Available
2 | Audit Enhancement | Integrate with Audit Error Code identified for each audit event | MOS-23840 | To enhance auditing to include error and exceptions for each audit event | Story | Vital | 6 | Hemaprabha.Sridharan |  | OK | P2 | Dev in progress | Sprint 14/15
3 | Biometric Authentication - Best Finger Detection | [non-MVP]As the MOSIP system, I should be able to detect the Best Finger of a Individual during Authentication | MOS-1120 | Best Finger for Authentication to be implemented for IDA. The quality of fingerprints may wear out with time. BFD during authentication will help in identifying Best Finger after registartion | Story | NA | 12 | Hemaprabha.Sridharan | Addressed as part of analytics | OK | NA | NA | NA
4 | Biometric Authentication - Fingerprint Image based Authentication | As the MOSIP system, I should be able to support Fingerprint authentication by using Fingerprint Image | MOS-12165 | In addition to the Fingrprint Minutiae based authentication already implemented, Fingerprint Image based authentication has to be implemented | Story | Vital | 12 | Hemaprabha.Sridharan |  | OK | P1 | Done | Sprint 13
5 | Biometric Authentication - Integration with devices and SDK | SDK Analysis | MOS-27361 | SDK Analysis |  | Vital | 15 |  |  | OK | P0 | Dev in progress | Sprint 14
6 | Biometric Authentication - Integration with devices and SDK | Tech Task: Analyze Biometric SDK | MOS26646 | Tech Task: Analyze Biometric SDK |  | Vital | 8 |  |  | OK | P0 | Dev in progress | Sprint 14
7 |  | Devices - Tech Story: Internal API to add FIR - Fingerprint Image Record | MOS-22416 | To integrate with devices and SDK for biometric authentication requests from Registration Client and Registration Supervisor | Story | Vital | 6 | Hemaprabha.Sridharan |  | OK | P0 - high priority, once dep is meet need to take it up asap | Tech Story
8 |  | Admin Related Requirements for Biometric devices from the perspective of IDA | MOS-21758 | To integrate with PM/Admin for Device Related Requirements like Device Registration and Device Provider Registration | Story | Vital | 20 | Hemaprabha.Sridharan |  | OK | P2 Note: Admin high priority | Dependency on Admin
9 |  | There will be one MOSIP Device Service spec, which will be one unified service spec for registration and authentication devices: | MOS-18214 | To integrate with MDS for receiving valid biometric attributes in input in Auth API | Story | Vital | 20 | Hemaprabha.Sridharan |  | OK | Requires Discussion on Test Authentication Client <07 16> Updated the description | Dependency on MDS
10 |  | Tech Story: As the MOSIP System, I should be able to integrate with Face SDK and generate match score | MOS-12073 | When the devices and SDK are available, to integrate with SDK for face match score generation | Story | Vital | 14 | Hemaprabha.Sridharan |  | OK | P0 - high priority, once dep is meet need to take it up asap | Tech Story
11 |  | Tech Story: As the MOSIP System, I should be able to integrate with Fingerprint scanner and generate match score | MOS-12072 | When the devices and SDK are available, to integrate with SDK for fingerprint match score generation | Story | Vital | 28 | Hemaprabha.Sridharan |  | OK | P0 - high priority, once dep is meet need to take it up asap | Tech Story
12 |  | Tech Story: As the MOSIP System, I should be able to integrate with SDK to provide the composite match score for two finger/IRIS authentication | MOS-10831 | When the devices and SDK are available, to integrate with SDK for biometric match score for composite fingerprint/IRIS | Story | Vital | 28 | Hemaprabha.Sridharan |  | OK | P0 - high priority, once dep is meet need to take it up asap | Tech Story
13 |  | Tech Story: As the MOSIP System, I should be able to integrate with IRIS scanner and generate match score | MOS-10308 | When the devices and SDK are available, to integrate with SDK for IRIS match score generation | Story | Vital | 14 | Hemaprabha.Sridharan |  | OK | P0 - high priority, once dep is meet need to take it up asap | Tech Story
14 |  | Tech Story: As the MOSIP System, I should be able to integrate and deliver all the dependent services for Biometric Authentication | MOS-1150 | Master story for Biometric implementation to be implemented once the devices and SDK are available | Story | Vital | 6 | Resham.Chugani |  | OK | P0 - high priority, once dep is meet need to take it up asap | Tech Story
15 | Biometric Authentication - Redesign biometric authentication independent of biometric type/provider | Update Biometric Authentication design independent of the biometric provider/Type | MOS-20783 | Need more clarity to understand the requirement - MOSIP should identify biometric type and pass on the CBEFF from auth client to SDK - Agnostic of biometric type | Story | Essential | 6 | Hemaprabha.Sridharan |  | OK |  | Tech Story
16 | Biometric Authentication - send signed biometrics to Reg Client | As the MOSIP system, I should be able to authenticate an Individual's biometrics received from Reg. Client and if successful, send back signed biometrics | MOS-22937 | Need additional details on the 'Signed Biometrics' to understand the requirement | Story | NA | 10 | Hemaprabha.Sridharan | As a policy, MOSIP should not send out biometrics - Refer discussion with Vivek | OK | NA | NA | NA
17 | Biometric Authentication - Notify Individual to Update Biometrics due to poor quality | As the MOSIP system, I should be able to to intimate a resident to update their biometrics if quality of the biometrics is below threshold | MOS-13190 | After successive failure in authentication due to quality issue, individual to be intimated to update biometrics | Story | NA | 5 | Hemaprabha.Sridharan | Addressed as part of analytics | OK | NA | NA | NA
18 | Demographic Authentication - Morocco Address mapping | Mapping of platform address attributes in IDA based on Morrocco Address Structure | MOS-21585 | To support Morrocco specific address attributes for Demo authentication based on full address and address line items | Story | Vital | 6 | Hemaprabha.Sridharan |  | TBD | P2 - To be decided in the next sprint based on the location hierarchy decision from other modules | Requierment Pending
19 | Demographic Authentication - Phonetics and Partial Match | As the MOSIP system, I should be able to support phonetics/partial match for Demo Authentication | MOS-12166 | In the demo authentication implementation, in addition to the exact match, partial and phonetics based match has to be implemented | Story | Desirable | 5 | Hemaprabha.Sridharan |  | OK |  | Requierment Pending
20 | KYC Service - Morocco HoH API | As the MOSIP system, I should be able to support return additional eKYC data to social protection system | MOS-13161 | To support for an additional eKYC api for Morrocco, to retrieve data of a family/child on consent to the head of family | Story | NA | 6 | Hemaprabha.Sridharan | This should be handled as part of Consent provided during Registration and as part of Reg. Proc. during integration | TBD |  | Requierment Pending
21 | Multi-factor Authentication | As the MOSIP system, I should be able to authenticate a Individual using multi-factor authentication during authentication process | MOS-1124 | Master story for Multi-factor implementation to be implemented once the devices and SDK are available | Story | Vital | 6 | Taleev.Aalam |  | ok | P0 - high priority, once dep is meet need to take it up asap | Tech Story
22 | NFR | NFR Questions of ID -Authentication and Morroco Specific NFRs | MOS-9128 | Performance related NFRS of IDA to be tested | Story | Vital | 0 | Hemaprabha.Sridharan | These will not be considered. Only Perfromance Testing will be accommodated, which is a separate line item in the Consolidated sheet under Testing bucket | ok | NA | NA | NA
23 |  | As MOSIP system, I should be able to honor API requests only from authorized Clients | MOS-1156 | Validate NFR when integration with Partner Management Service is complete | Story | NA | 5 | Hemaprabha.Sridharan | To be deleted |  | NA | NA | NA
24 |  | Ability to Synchronize across DCs: As MOSIP system, I should be able to synchronize data change across data centres | MOS-1136 | Verify the NFR once multiple DCs are configured - High availability | Story | Vital | 0 | Hemaprabha.Sridharan |  | ok | NA | NA | NA
25 |  | Address Verification Performance: As MOSIP system, I should be able to support address verification authentication performance as per pre-defined standard | MOS-1126 | Disaster Recovery | Story | Vital | 0 | Hemaprabha.Sridharan |  | ok | NA | NA | NA
26 |  | Tech Story: As MOSIP system, I should be able to partition data across servers and DCs | MOS-1121 | Verify the NFR once the identity details is available in IDA DB | Story | NA | 16 | Taleev.Aalam | To be deleted |  | NA | NA | NA
27 |  | Tech Story: As MOSIP system, I should be able to support horizontal scalability as per pre-defined standard | MOS-1143 | Verify once Horizontal scaling is available in IDA - Auto scale | Story | Vital | 0 | Taleev.Aalam |  | ok | NA | NA | NA
28 | OTP Authentication - Integrate with Kernel for OTP Validator fix | As the MOSIP system - IDA, I should be able to integrate once correct format of OTP Validator errors is implemented | MOS-24077 | Integrate with corrected format of error codes and messages of kernel OTP validator | Story | Vital | 6 | Taleev.Aalam |  | ok | P2 - dependency on kernel | Kernel to Complete by Sprint 14 - Can be taken Up in Sprint 15 | Sprint 16
29 | Partners Authentication and Authorization - Integration with Kernel for Digital Signature | Integrate with the certificate based Digital Signature from Kernel | MOS-23836 | Integrate with kernel Digital Signature service once Digital Signature is generated using Digital Certificate | Story | Vital | 8 | Hemaprabha.Sridharan |  | ok | P2. Dependency task to be added based on Ramesh mail on PM pending tasks | Kernel to take in Sprint 15 (Post Demo) | Sprint 16
30 | Partners Authentication and Authorization - Integration with PM | As the MOSIP System(IDA), I should be able to integrate with PM for retrieving Public Key of partners | MOS-24115 | Integrate with PM to retrive partner public keys to encrpt eKYC request | Story | Vital? | 16 | Hemaprabha.Sridharan |  | ok | P2 | Requierment Pending
31 |  | As the MOSIP system, I should be able to integrate with PM for PartnerID Validation | MOS-13157 | To integrate with PM to validate Partner ID in the auth/eKYC request and retrive the policy corresponding to a partnerID and partner key | Story | Vital? | 16 | Taleev.Aalam |  | ok | P2 | Requierment Pending
32 |  | As the MOSIP system, I should be able to integrate with PM for MISP Liense Key Validation | MOS-13156 | To integrate with PM to validate MISP License Key | Story | Vital? | 8 | Hemaprabha.Sridharan |  | ok | P2 | Requierment Pending
33 |  | As the MOSIP System(IDA), I should be able to integrate with PM for Certificate Validation | MOS-1099 | Integrate with PM services, to validate the partner's Digital certificate used in signing auth/eKYC request | Story | Vital? | 16 | Hemaprabha.Sridharan |  | ok | P2 | Requierment Pending
34 | Resident Services Feature - Auth Transaction History | As the MOSIP System, I should be able to provide Authentication Transaction History for a UIN or VID_Part 2 | MOS-27360 | To provide authentication history for an individual for all associated id types - UIN and VID |  | Vital | 16 |  | Estimates are based on data model change and includes testing. Revised from 16 to 24. This includes: 1. SALT generator job for hashing and encrypting UIN | OK | P1 | Done | Sprint 13/14
35 | Resident Services Feature - Auth Transaction History | As the MOSIP System, I should be able to provide Authentication Transaction History for a UIN or VID_Part 1 | MOS-24680 - Refer Comments for effort inclusions | To provide authentication history for an individual for all associated id types - UIN and VID | Story | Vital | 8 | Hemaprabha.Sridharan | Estimates are based on data model change and includes testing. Revised from 16 to 24. This includes: 1. SALT generator job for hashing and encrypting UIN | ok | P1 | Dev in progress | Sprint 13
36 | Security - Integration with kernel Cryptomanager fix (To accommodate key index based encryption/decryption) | Integrate with the fix- Key expiry error in CryptoManager | MOS-23741 | - IDA receives Key index in input, which is to be used to decrypt the auth request, by calling Kernel Cryptomanager Current implementation of Cryptomanager doesn't support it. - Also when the associated public keys are expired, IDA needs to inform partner with the relevant error message | Story | Vital | 6 | Hemaprabha.Sridharan | Verified with Gurpreet | ok | P2 | Dependency on Kernel
37 | Technical - Docker Signing | Tech Story - Docker Signing | MOS-17514 | Verify once Dockers are signed | Story | Vital | 0 | Taleev.Aalam | Core team to implement | ok | P3 | Dependency on Core Team
38 | Technical - Integrate with upgraded CBEFF | Tech Story: Integrate with CBEFF XSD 2.0 | MOS-24840 | When CBEFF XSD is upgraded to 2.0, IDA to integrate with upgraded CBEFF | Story | Vital | 10 | Hemaprabha.Sridharan |  | ok | P1 | Done | Sprint 14
39 | Technical - Integration with Kernel on removal of 500 http status | Verify Kernel API integration for 500 http status | MOS-24598 | When 500 http status is removed from kernel apis, IDA needs to verify if the integration to all kernel services are working as expected | Story | Vital | 6 | Hemaprabha.Sridharan |  | ok | P2 | Dependency on Kernel
40 | Technical - Synchronise IDA DB, Secured UIN storage | Design Change of IDA based on Security review by Sasi/Ramesh | MOS-21584 | Sychronise ID Repo DB with IDA DB, UIN should be securedly stored in IDA | Story | Essential |  | Hemaprabha.Sridharan |  | ok |  | Requierment Pending
41 |  | Ability to Synchronize changes from Registration DB: As MOSIP system, I should be able to synchronize data changes from Registration DB to auth server | MOS-1141 | Sychronize ID Repo DB with IDA DB, UIN should be securedly stored in IDA | Story | Essential |  | Hemaprabha.Sridharan |  | ok |  | Requierment Pending
42 |  | As the MOSIP System, I should be able to synchronize Identity data from ID Repo DB to Authentication DB | MOS-25377 | To sync ID Repo DB data to IDA DB | Story | Essential |  | Taleev.Aalam |  | ok |  | Requierment Pending
43 | Lock/Unlock AuthType | As the MOSIP system, I should be able to maintain lock/unlock auth policy for an UIN | MOS-24732 | To maintain auth-type lock/unlock policy in ID Repo based on the request from Resident Services. The policy is to be validated before any authentication request is processed | Vital | Vital | 20 | DB changes, Policy to be creaated, create and update API to be created | DB changes, Policy to be creaated, create and update API to be created | ok | P1 | Dev in progress | Sprint 14/15
44 | Lock/Unlock AuthType | As IDA, I should be able to Send all the Auth Type and Status to Resident Services | MOS-26742 | Retrieve status of Auth Types for Individual | Vital | Vital | 10 |  |  |  | P2 | Dev in progress | Sprint 14/15
45 | Lock/Unlock AuthType | Tech Story - Validate if Auth Type is Unlocked Before Performing Authentication | MOS-26641 | Authenticate an Individual based on input Authentication Type only when it is unlocked for an Individual | Vital | Vital | 6 |  |  |  | P1 | Dev in progress | Sprint 14/15
46 | Internal Auth | As IDA, I should be able to Provide an OTP to Resident Services when Requested for a UIN/VID | MOS-26647 | To enable Individual request for an OTP via Resident Services | Vital | Vital | 8 |  |  |  | P1 | Dev in progress | Sprint 13
47 |  | Tech Story - Implement OTP Authentication as part of Internal Authentication API | MOS-26649 | To enable authenticate an Individual via Resident Services | Vital | Vital | 6 |  |  |  | P1 | Dev in progress | Sprint 13
48 | VID Policy | Admin Related configuration for VID policy | MOS-27272 | To set up the recommended VID policy for a country |  | Vital |  |  |  |  | P2 | Dev in progress | Sprint 14/15
49 | Partner Management | Internal API by IDA to validate Partner ID/API key and retrieve policy | MOS-27758 | To set up a policy in IDA to validate Partner ID/API key and retrieve policy which will ultimately be part of Partner Management | [7 empty] | Requierment Pending | Sprint 15/16
50 | Partner Management | Temporary Auth policy creation by IDA | MOS-27759 | To set up a policy in IDA which will ultimately part of Partner Management | [7 empty] | Requierment Pending | Sprint 15/16
51 | Authentication | Remove FMR based Authentication from Auth APIs | MOS-27996 | Remove FMR based Authentication from Auth APIs |  | Vital |  |  |  |  | P1 | Tech Story | Sprint 15/16
Note on D9: Gurpreet: This is already available, need more information on this.
Note on D39: Gurpreet: This is a cross-cutting feature, Core-team can provide estimate on this. Please add in consolidated sheet

## ID-Repository
Story Backlog: ID-Repository
S.No. | Feature | Story Title | Issue key | Requirement Description | Issue Type | Category | Estimates - Incl. Testing (PDs) | Reporter | Comments | SK Comments | Prioritisation on <07 15> | Current Status | Sprint
1 | Audit Enhancement | Integrate with Audit Error Code identified for each audit event | MOS-26745 | To enhance auditing to include error code for each audit event | Story | Vital | 4 | Hemaprabha.Sridharan |  | OK | P2 | Dev in progress | Sprint 14/15
2 | VID Service | As the MOSIP system, I should be able to re-activate all the VIDs associated to an UIN based on the policy | MOS-24761 | To re-activate all VIDs associated to a reactivated UIN. This UIN is reactivating a deactivated UIN | Story | Vital | 12 |  |  | ok | P1 | Dev in progress | Sprint 13
3 | VID Service | As the MOSIP system, I should be able to de-activate all the VIDs associated to an UIN | MOS-24760 | To de-activate all VIDs associated to a deactivated UIN | Story | Vital | 12 |  |  | ok | P1 | Dev in progress | Sprint 13
4 | Identity Service Enhancement | Retrieve RID for input UIN | MOS-26747 | To retrieve RID for a given UIN |  | Vital | 3 |  | Required for Registration Processor |  | De-Scoped | NA | NA
5 | Technical - Integrate with upgraded CBEFF | Integrate with CBEFF XSD 2.0 | MOS-26748 | When CBEFF XSD is upgraded to 2.0, IDRepo to integrate with upgraded CBEFF |  | Vital | 10 |  |  |  | P1 | Dev in progress | Sprint 14
6 | ID Object Schema and ID Object Validator | Tech Story - Remove Dependency on Attributes – CNIE and LocalAdministrativeAuthority from ID Object | MOS-27303 | Remove GoM specific terminologies from ID Object. |  | Vital | 6 |  | Requiered for all Modules |  | P1 | Dev in progress | Sprint 14/15
7 | Re-Activate and De-Activate UIN API Changes for Admin Module | Re-Activate and De-Activate UIN API Changes | MOS-27942 | Re-Activate and De-Activate UIN API Changes |  | Vital | [5 empty] | Tech Story | Sprint 15

## Kernel
Story Backlog: Kernel
S.No. | Feature | Story Title | Issue key | Requirement Description | Issue Type | Category | Estimates - Incl. Testing (PDs) | Reporter | Comments | SK Comments | Priority | Current Status | Sprint
1 | SMS/EmailNotification | Non-MVP: SMS/Email Notification - Add interface for Delivery Reports | MOS-23810 | Adding an interface to support capturing of delivery reports sent by thrid party Email/SMS Vendor | Story | Essential |  | Amandeep.Khanuja |  | Essential |  | On Hold due to Bootcamp Demo
2 | Crypto Management | Non MVP: Crypto Manager - As the MOSIP system, I should be able to decrypt using Key Index | MOS-23599 | Ability to decrypt data using Key Index instead of Timestamp in IDA | Story | Vital |  | Amandeep.Khanuja | Need clarification from John |  | P1 | Customer Approval Pending | Sprint 15
3 | Audit Management | Non MVP: Enable data loss prevention in Audit | MOS-23263 | Tech Story - Implementing Kafka as message queue to prevent data loss during Audit Logging | Story | Vital | 15 | Amandeep.Khanuja | Architects to further discuss | Vital | P3 | In Progress | Sprint 14
4 | Sync Data | Non MVP: Changes in Sync data as per new location hierarchy | MOS-22655 | Change in Sync data response based on the Morocco Location Hierarcy | Story | Vital | 15 | Amandeep.Khanuja | Architects to further discuss with DB Team | TBD | P2 | Requirement pending
5 | License Key Validation | Non MVP: As the MOSIP system, I should be able to perform License Key pattern validation against a defined License Key generation policy | MOS-22446 | Perfroming a Pattern and Length validation on License Key | Story | Vital | 4 | Amandeep.Khanuja |  | OK | P2 | De-scoped from Kernel. Part of Partner Management
6 | Parter ID Validation | Non MVP: As the MOSIP system, I should be able to perform Partner ID validation against a defined Partner ID policy | MOS-22445 | Perfroming data type and Length validation on Partner ID | Story | Vital | 4 | Amandeep.Khanuja |  | ok | P2 | De-scoped from Kernel. Part of Partner Management
7 | Pre-registration Dependency: Partial Search on Location | Non MVP: Partial Search on Location for Pre_reg | MOS-22038 | Adding support/query to search and fetch location data based on a partial search on pre-registration | Story | Desirable | 5 | Amandeep.Khanuja | Subject to bandwidth | ok | P2 | Requirement pending
8 | OTP Management | Non MVP: As the MOSIP system, I should be able have multiple OTP active for a single UIN | MOS-21931 | Ability to have multiple OTPs active for a single UIN - Inclusive of mapping each active OTP to a transaction | Story | Desirable |  | Amandeep.Khanuja |  | ok |  | On Hold due to Bootcamp Demo
9 | Moving to hardware HSM | Moving to hardware HSM | MOS-26254 | TBD |  | Vital | 8 |  | Estimates covers only the code change. Pre-Requirtes is HSM should beavilable for usage |  | P2 | In Progress | Sprint 14
10 | Technical - Integration with Kernel on removal of 500 http status | Verify Kernel API integration for 500 http status | MOS-26255 | - 500 http status to be removed from kernel apis |  | Vital | 3 |  |  | ok | P2 | On Hold due to Bootcamp Demo
11 | (Resident Service Dependency) Password Protected PDF - | As the MOSIP System, I should be able to generate Password Protected PDF | MOS-27221 | As the MOSIP System, I should be able to generate Password Protected PDF |  | Vital | 12 |  | This inclused the Paswword using PKI |  | P2 | In Progress | Sprint 14
12 | (IDA Dependency) Key Expiry Error In Crypto-Manager | As the MOSIP System, I should be able to respond with an error if a Key is expired | MOS-27307 | As the MOSIP System, I should be able to respond with an error if a Key is expired |  | Vital | 8 |  |  |  | P1 | On Hold due to dependency on Item no. 2 | Sprint 15
13 | (IDA Dependency) Fix error messages - OTP Validator | Tech Story: Fix error messages format in OTP Validator Component | MOS-24012 | Fix error messages format in OTP Validator Component |  | Vital | 2 |  |  |  | P1 | In Progress | Sprint 14
14 | Termininology Update in Location | Tech Story: Update the Masterdata for Location Hierarcy | MOS-27310 | Update the Masterdata for Location Hierarcy |  | Vital | 1 |  |  |  | P1 | In Progress | Sprint 14
15 | Digital Certificate Manager | Implement Digital Certificate Manager to have Certificate based Digital Signature | MOS-27314 | Implement Digital Certificate Manager to have Certificate based Digital Signature |  | Vital |  |  | Need for design analysis for estimation |  | P1 | In Progress | Sprint 14

## Resident Services
Story Backlog: Resident Services
S.No. | Feature | Summary | Issue key | Requirement Description | Issue Type | Priority | Estimates - Incl. Testing (PDs) | Reporter | Comments
1 | Address Validation Letter | Non-MVP: Address Validation Letter | MOS-24702 | Address Validation Letter is letter which is sent to the Address Verifier’s address. The letter will contain a secret code sent for validation after the Address Verifier consents to the use of his/her address by the requesting resident. | Story | Desirable |  | Samrat.Sengupta
2 | Authentication with non-registered mobile | Non-MVP: Service to authenticate with non registered mobile number on which the OTP can be received | MOS-24701 | Resident Service should be able to validate a user on a different mobile number other than the registered mobile number. | Story | Desirable |  | Samrat.Sengupta
3 | Weak Mobile Identification | Non-MVP: Weak Mobile Identification | MOS-25624 | Resident Service should be able to call an API which can determine if a mobile number as weak based on multiple associations to UIN's for that mobile number. | Story | Desirable
4 | Retrieve VID | Non-MVP: Retrieve VID | MOS-25600 | An individual should have the provision to retrieve the existing valid Virtual Identity for the resident by taking PIN and OTP as input. | Story | Desirable
5 | Track UIN Reprint Status | Non-MVP: Track UIN Reprint Status: As the MOSIP system, I should be able to process a Reprint UIN Status check request | MOS-26651 | An individual can track the status of Reprint UIN by providing a Request ID(RID). |  | Desirable
6 | VID Revocation notification story | Non-MVP: VID Revocation notification story As the MOSIP system, I should be able to notify a user for automatic generation of a new VID in case of auto revocation of existing VID | MOS-27145 | An individual should be notified if his/her VID gets auto revoked due to an event and also notified about the new VID generated due to auto-revocation event. |  | Desirable
7 | View Auth History | As the MOSIP system, I should be able to process a request to view Authentication requests history for a specific UIN/VID | MOS-23863 | An individual can view authentication- requests history for a specific UIN/VID. The system will fetch unarchived data and show it in a paginated format to user. | Story | Vital | 6 | Vyas.Vemuri | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
8 | Download e-UIN | As the MOSIP system, I should be able to enable download of e-UIN | MOS-23862 | An individual can raise a request to download his/her e-UIN by providing the UIN/VID, full name, postal code, and security code. | Story | Vital | 6 | Vyas.Vemuri | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
9 | Track UIN Generation Status | As the MOSIP system, I should be able to process UIN Generation status check request | MOS-23861 | An individual can track the stats of UIN generation by providing a Registration ID(RID). | Story | Vital | 6 | Vyas.Vemuri | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
10 | Track UIN Update Request | As the MOSIP system, I should be able to process a UIN Update Status check request | MOS-23860 | An individual can track the status related to UIN updates based on a registration ID.An individual provides the Registration ID for which he/she wants to track the status of UIN updates. | Story | Vital | 6 | Vyas.Vemuri | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
11 | UIN Update | As the MOSIP system, I should be able to process a UIN Update request | MOS-23859 | MOSIP allows an individual to process a request to update the demographic data of the UIN. An individual provides the UIN/VID for which he/she wants to update. | Story | Desirable | 6 | Vyas.Vemuri | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
12 | Retrieve Lost UIN | As the MOSIP system, I should be able to process a request to retrieve lost UIN | MOS-23858 | MOSIP allows an individual to initiate a request to retrieve the Registration ID by providing the Full Name, Mobile Number/E-Mail ID, Postal Code | Story | Desirable | 6 | Vyas.Vemuri | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
13 | Retrieve Lost RID | As the MOSIP system, I should be able to process a request to retrieve lost RID | MOS-23856 | An individual can retrieve the RID by providing the Full Name, Mobile Number/E-Mail ID, Postal Code. | Story | Desirable | 6 | Vyas.Vemuri | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
14 | Reprint UIN | As the MOSIP system, I should be able to process a request to re-print UIN | MOS-23746 | MOSIP allows an individual to raise a reprint request for their UIN. The individual provides the UIN/VID for which he/she wants to reprint. | Story | Vital | 6 | Vyas.Vemuri | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
15 | Lock/Unlock AUTH | As the MOSIP system, I should be able to process a request to unlock UIN/VID for a specific authentication type | MOS-23745 | MOSIP allows an individual to unlock the authentication type(s) (Demographic, Biometrics (FP/Iris/Face/All)) associated with the UIN/VID. Only the unlocked authentication type(s) of demographic and biometric (FP/Iris/Face/All) can be used for any required authentication purpose | Story | Vital | 6 | Vyas.Vemuri | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
16 |  | As the MOSIP system, I should be able to process a request to lock UIN/VID for a specific authentication type | MOS-23744 | MOSIP allows an individual to lock the authentication type(s) (Demographic, Biometrics (FP/Iris/Face/All)) associated with the UIN/VID. Only the locked authentication type(s) cannot be used for any authentication purpose | Story | Vital | 6 | Samrat.Sengupta | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
17 | Generate VID | As a system, I should be able to generate VID for a user who requests for it so that he/she may be able to mask his/her UIN using the VID | MOS-25580 | Upon receiving a VID generation and storage request with the parameters: UIN, ver, requestTime, vidType, the system performs steps to create VID in the defined policy. | Story | Vital | 6 |  | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
18 | Revoke VID | As a system, I should be able to revoke a VID for a user who requests for it | MOS-25583 | Upon receiving a request with the parameter: VID, ver to revoke a VID based on the type, the system performs steps to revoke a VID based on the type. | Story | Vital | 6 |  | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort

## Admin
Story Backlog: Admin
S.No. | Feature | Story Title | Issue key | Requirement Description | Issue Type | Priority | Estimates - Incl. Testing (PDs) | Reporter | Sprint | Comments
1 | Account Unlock | UI: As the MOSIP Administrator, I should be able to unlock my locked account | MOS-23691 |  | Story | Desirable | 2.6 | Amandeep.Khanuja |  | Key Cloak Feature
2 | Account Unlock | API: As the MOSIP Admin Application, I should enable functionality to unlock a locked account | MOS-23690 |  | Story | Desirable | 2.6 | Amandeep.Khanuja |  | Key Cloak Feature
3 | Approvals | UI: As the MOSIP Administrator, I should be able to approve created Centers, Machine, Devices, Users and Masterdata | MOS-24132 |  | Story | Desirable | 0 | Amandeep.Khanuja |  | Need more clarifiaction on Requirements and Design
4 | Approvals | Tech Story - API: Create an Approval Framework | MOS-23791 |  | Story | Desirable | 0 | Amandeep.Khanuja |  | Need more clarifiaction on Requirements and Design
5 | Auto Logout | UI: As the MOSIP Admin Application, I should be able to Auto-Logout a logged in user | MOS-23606 |  | Story | Desirable | 5.2 | Amandeep.Khanuja |  | Key Cloak Feature
6 | Balcklisted Word Create | UI: As the MOSIP Administrator, I should be able to create a Blacklisted Word | MOS-23667 |  | Story | Desirable | 3.9 | Amandeep.Khanuja
7 | Balcklisted Word Create | API: As the MOSIP Admin Application, I should enable functionality to create a Blacklisted Word | MOS-23666 |  | Story | Vital | 3.9 | Amandeep.Khanuja | MOS Sprint 12
8 | Blacklisted Word Activate/Deactivate | UI: As the MOSIP Administrator, I should be able to Activate and Deactivate a Blacklisted Word | MOS-23670 |  | Story | Desirable | 3.9 | Amandeep.Khanuja
9 | Blacklisted Word Update | API: As the MOSIP Admin Application, I should enable functionality to update a Blacklisted Word | MOS-23671 |  | Story | Vital | 3.9 | Amandeep.Khanuja | MOS Sprint 12
10 | Blacklisted Word Update | UI: As the MOSIP Administrator, I should be able to update a Blacklisted Word | MOS-23668 |  | Story | Desirable | 3.9 | Amandeep.Khanuja
11 | Cener History Storage | API: As the MOSIP Admin Application, I should enable functionality to store history of Creations and Updation of Registration Centers | MOS-24829 |  | Story | Vital | 2.6 | Amandeep.Khanuja
12 | Center Activate/Deactivate | UI: As the MOSIP Administrator, I should be able to Activate/Deactivate a Registration Center | MOS-23635 |  | Story | Desirable | 3.9 | Amandeep.Khanuja
13 | Center Activate/Deactivate | API: As the MOSIP Admin Application, I should enable functionality to activate or deactivate a Registration Center | MOS-25634 |  | Story | Vital | 3.9
14 | Center Create | UI: As the MOSIP Administrator, I should be able to create a Registration Center | MOS-23631 |  | Story | Desirable | 5.2 | Amandeep.Khanuja
15 | Center Create | API: As the MOSIP Admin Application, I should enable functionality to create a Registration Center | MOS-23630 |  | Story | Vital | 3.9 | Amandeep.Khanuja | MOS Sprint 12
16 | Center Create | API: As the MOSIP Admin Application, I should not allow creation of a Registration Center if data is not received in all configured languages | MOS-25629 |  | Story | Vital | 3.9
17 | Device View | API: Implementation of Registration Search API | MOS-24950 |  | Story | Vital | 5.85 | Amandeep.Khanuja | MOS FIT 5
18 | Center Decommission | API: As the MOSIP Admin Application, I should enable functionality to decommission a Registration Center | MOS-25261 |  | Story | Vital | 5.2
19 | Center Decommission | UI: As the MOSIP Administrator, I should be able to Decommission a Registration Center | MOS-25368 |  | Story | Desirable | 3.9
20 | Center Detail View | UI: As the MOSIP Administrator, I should be able to view complete details of a Registration Center | MOS-23619 |  | Story | Vital | 2.6 | Amandeep.Khanuja
21 | Center List View | UI: As the MOSIP Administrator, I should be able to view list of Registration Centers | MOS-23617 |  | Story | Vital | 2.6 | Amandeep.Khanuja
22 | Center List View | API: As the MOSIP Admin Application, I should enable functionality to view list of Registration Centers | MOS-23616 |  | Story | Vital | 4.55 | Amandeep.Khanuja | MOS Sprint 12
23 | Center List View Machine List View Device List View | API: As the MOSIP Admin Application, I should be able to fetch columns to be displayed on Center/Machine/Device view page from Configurations | MOS-25638 |  | Story | Vital | 2.6
24 | Center Update | UI: As the MOSIP Administrator, I should be able to Update details of a Registration Center | MOS-23633 |  | Story | Desirable | 2.6 | Amandeep.Khanuja
25 | Center Update | API: As the MOSIP Admin Application, I should enable functionality to Update details of a Registration Center | MOS-23632 |  | Story | Vital | 3.9 | Amandeep.Khanuja | MOS Sprint 12
26 | Center Update | API: As the MOSIP Admin Application, I should not allow updation of a Registration Center if data is not received in all configured languages | MOS-25630 |  | Story | Vital | 3.9
27 | Center-Device Mapping Create | UI: As the MOSIP Administrator, I should be able to map Devices to a Registration Center | MOS-23628 |  | Story | Desirable | 3.9 | Amandeep.Khanuja
28 | Center-Device Mapping Create | API: As the MOSIP Admin Application, I should enable functionality to map/re-map a Device to a Registration Center | MOS-23627 |  | Story | Vital | 3.9 | Amandeep.Khanuja
29 | Center-Device Mapping History Storage | API: As the MOSIP Admin Application, I should enable functionality to store history of Creations and Updation of Registration Center - Device Mapping | MOS-24837 |  | Story | Vital | 2.6 | Amandeep.Khanuja
30 | Center-Device Unmap | UI: As the MOSIP Administrator, I should be able to Un-Map Devices from a Registration Center | MOS-23677 |  | Story | Desirable | 3.9 | Amandeep.Khanuja
31 | Center-Device Unmap | API: As the MOSIP Admin Application, I should enable functionality to Un-Map a Device from a Registration Center | MOS-23676 |  | Story | Vital | 3.9 | Amandeep.Khanuja
32 | Center-Machine Mapping Create | UI: As the MOSIP Administrator, I should be able to map Machines to a Registration Center | MOS-23625 |  | Story | Desirable | 3.9 | Amandeep.Khanuja
33 | Center-Machine Mapping Create | API: As the MOSIP Admin Application, I should enable functionality to map/re-map of a Machine to a Registration Center | MOS-23624 |  | Story | Vital | 3.9 | Amandeep.Khanuja
34 | Location Update | API: As the MOSIP Admin Application, I should enable functionality to update details of a Location_Part2 | MOS-25217 |  | Story | Vital | 5.2
35 | Center-Machine Mapping History Storage | API: As the MOSIP Admin Application, I should enable functionality to store history of Creations and Updation of Registration Center - Machine Mapping | MOS-24836 |  | Story | Vital | 2.6 | Amandeep.Khanuja
36 | Center-Machine Unmap | UI: As the MOSIP Administrator, I should be able to Un-Map Machines from a Registration Center | MOS-23675 |  | Story | Desirable | 3.9 | Amandeep.Khanuja
37 | Center-Machine Unmap | API: As the MOSIP Admin Application, I should enable functionality to Un-Map a Machine from a Registration Center | MOS-23674 |  | Story | Vital | 3.9 | Amandeep.Khanuja
38 | Center-User Mapping Create | UI: As the MOSIP Administrator, I should be able to map Users to a Registration Center | MOS-23621 |  | Story | Desirable | 5.2 | Amandeep.Khanuja
39 | Center-User Mapping Create | API: As the MOSIP Admin Application, I should enable functionality to map/re-map a User to a Registration Center | MOS-23620 |  | Story | Vital | 5.2 | Amandeep.Khanuja
40 | Center-User Mapping History Storage | API: As the MOSIP Admin Application, I should enable functionality to store history of Creations and Updation of Registration Center - User Mapping | MOS-24835 |  | Story | Vital | 2.6 | Amandeep.Khanuja
41 | Center-User Unmap | UI: As the MOSIP Administrator, I should be able to Un-Map Users from a Registration Center | MOS-23673 |  | Story | Desirable | 3.9 | Amandeep.Khanuja
42 | Center-User Unmap | API: As the MOSIP Admin Application, I should enable functionality to Un-Map a User from a Registration Center | MOS-23672 |  | Story | Vital | 5.2 | Amandeep.Khanuja
43 | Change Password | UI: As the MOSIP Administrator, I should be able to change my password | MOS-23611 |  | Story | Desirable | 3.9 | Amandeep.Khanuja |  | Key Cloak Feature
44 | Change Password | API: As the MOSIP Admin Application, I should enable functionality to change password | MOS-23610 |  | Story | Desirable | 2.6 | Amandeep.Khanuja | MOS Sprint 12 | Key Cloak Feature
45 | Device Activate/Deactivate | UI: As the MOSIP Administrator, I should be able to Activate/Deactivate a Device | MOS-23647 |  | Story | Desirable | 3.9 | Amandeep.Khanuja
46 | Device Activate/Deactivate | API: As the MOSIP Admin Application, I should enable functionality to activate or deactivate a Device | MOS-25636 |  | Story | Vital | 3.9
47 | Device Create | UI: As the MOSIP Administrator, I should be able to create a Device | MOS-23643 |  | Story | Desirable | 3.9 | Amandeep.Khanuja
48 | Device Create | API: As the MOSIP Admin Application, I should enable functionality to create a Device | MOS-23642 |  | Story | Vital | 3.9 | Amandeep.Khanuja | MOS Sprint 12
49 | Device Decommission | API: As the MOSIP Admin Application, I should enable functionality to decommission a Device | MOS-25263 |  | Story | Vital | 3.9
50 | Device Decommission | UI: As the MOSIP Administrator, I should be able to Decommission a Device | MOS-25372 |  | Story | Desirable | 3.9
51 | Device History Storage | API: As the MOSIP Admin Application, I should enable functionality to store history of Creations and Updation of Devices | MOS-24831 |  | Story | Vital | 2.6 | Amandeep.Khanuja
52 | Device List View | UI: As the MOSIP Administrator, I should be able to view list of Devices | MOS-23629 |  | Story | Vital | 2.6 | Amandeep.Khanuja
53 | Device List View | API: As the MOSIP Admin Application, I should enable functionality to view list of Devices | MOS-23626 |  | Story | Vital | 3.9 | Amandeep.Khanuja | MOS Sprint 12
54 | Device List View | UI: As the MOSIP system, I should be able to view associated Devices for a Registration Center | MOS-25373 |  | Story | Desirable | 6.5
55 | Device Update | UI: As the MOSIP Administrator, I should be able to Update details of a Device | MOS-23645 |  | Story | Desirable | 3.9 | Amandeep.Khanuja
56 | Device Update | API: As the MOSIP Admin Application, I should enable functionality to Update details of a Device | MOS-23644 |  | Story | Vital | 3.9 | Amandeep.Khanuja | MOS Sprint 12
57 | Device View | UI: As the MOSIP Administrator, I should be able to view complete details of a Device | MOS-23785 |  | Story | Vital | 3.9 | Amandeep.Khanuja
58 | Document Type Activate/Deactivate | UI: As the MOSIP Administrator, I should be able to Activate and Deactivate a Document type | MOS-23653 |  | Story | Desirable | 2.6 | Amandeep.Khanuja
59 | Document Type Create | UI: As the MOSIP Administrator, I should be able to create a Document Type | MOS-23649 |  | Story | Desirable | 3.9 | Amandeep.Khanuja
60 | Document Type Create | API: As the MOSIP Admin Application, I should enable functionality to create a Document Type | MOS-23648 |  | Story | Vital | 2.6 | Amandeep.Khanuja | MOS Sprint 12
61 | Document Type Update | UI: As the MOSIP Administrator, I should be able to update details of a Document Type | MOS-23651 |  | Story | Desirable | 3.9 | Amandeep.Khanuja
62 | Document Type Update | API: As the MOSIP Admin Application, I should enable functionality to update details of a Document Type | MOS-23650 |  | Story | Vital | 3.9 | Amandeep.Khanuja | MOS Sprint 12
63 | Document Type-Category Mapping Activate/Deactivate | UI: As the MOSIP Administrator, I should be able to Activate and Deactivate a mapping of a Document Type and Document Category | MOS-23659 |  | Story | Desirable | 3.9 | Amandeep.Khanuja
64 | Document Type-Category Mapping Create | UI: As the MOSIP Administrator, I should be able to map Document Types to a Document Category | MOS-23655 |  | Story | Desirable | 3.9 | Amandeep.Khanuja
65 | Document Type-Category Mapping Create | As the MOSIP Admin Application, I should enable functionality to map Document Types to a Document Category | MOS-23654 |  | Story | Vital | 5.2 | Amandeep.Khanuja
66 | Document Type-Category Mapping Update | UI: As the MOSIP Administrator, I should be able to update Document Types mapped to a Document Category | MOS-23657 |  | Story | Desirable | 3.9 | Amandeep.Khanuja
67 | Document Type-Category Mapping Update | API: As the MOSIP Admin Application, I should enable functionality to update Document Types mapped to a Document Category | MOS-23656 |  | Story | Vital | 3.9 | Amandeep.Khanuja
68 | Dssign | Design for "Admin" - Sprint 12 stories | MOS-24134 |  | Story | Vital | 7 | Amandeep.Khanuja
69 | Edit Personal Details | UI: As the MOSIP Administrator, I should be able to edit my personal details under "Profile Management" option | MOS-23609 |  | Story | Desirable | 13 | Amandeep.Khanuja |  | Key Cloak Feature
70 | Edit Personal Details | API: As the MOSIP Admin Application, I should enable functionality to edit user details | MOS-23608 |  | Story | Vital | 6.5 | Amandeep.Khanuja |  | Key Cloak Feature
71 | Export data (CSV) | UI: As the MOSIP Administrator, I should be able to export displayed data on a List view page to a CSV file | MOS-25370 |  | Story | Desirable | 5.2
72 | Forgot Username | UI: As the MOSIP Administrator, I should be able to retrieve my Username | MOS-23685 |  | Story | Desirable | 3.9 | Amandeep.Khanuja |  | Key Cloak Feature
73 | Forgot Username | API: As the MOSIP Admin Application, I should enable functionality to retrieve Username | MOS-23684 |  | Story | Desirable | 3.25 | Amandeep.Khanuja
74 | Home Page | UI: As the MOSIP Administrator, I should be able to view and navigate on Admin Application Home Page | MOS-23607 |  | Story | Vital | 2.6 | Amandeep.Khanuja
75 | Location Data Activate/Deactivate | UI: As the MOSIP Administrator, I should be able to Activate and Deactivate a Location | MOS-23665 |  | Story | Desirable | 5.2 | Amandeep.Khanuja
76 | Location Data Create | UI: As the MOSIP Administrator, I should be able to create a Location | MOS-23661 |  | Story | Desirable | 5.2 | Amandeep.Khanuja
77 | Location Data Create | API: As the MOSIP Admin Application, I should enable functionality to create a Location | MOS-23660 |  | Story | Vital | 6.5 | Amandeep.Khanuja | MOS Sprint 12
78 | Location Data Update | UI: As the MOSIP Administrator, I should be able to update details of a Location | MOS-23663 |  | Story | Desirable | 5.2 | Amandeep.Khanuja
79 | Location Data Update | API: As the MOSIP Admin Application, I should enable functionality to update details of a Location | MOS-23662 |  | Story | Vital | 5.2 | Amandeep.Khanuja | MOS Sprint 12
80 | Login | API: As the MOSIP Admin Application, I should fetch the security policy based on a username | MOS-23788 |  | Story | Vital | 3.9 | Amandeep.Khanuja
81 | Login | UI: As the MOSIP Administrator, I should be able to login to the admin portal with Username and Password | MOS-23223 |  | Story | Vital | 2.6 | Resham.Chugani |  | Key Cloak Feature
82 | Login | API: As the MOSIP Admin Application, I should enable login to the admin portal | MOS-23168 |  | Story | Vital | 2.6 | Resham.Chugani
83 | Login | API: As the MOSIP Admin Application, I should be able to enable login to Admin Portal _ Part 2 | MOS-25637 |  | Story | Vital | De-scoped
84 | Login - Captcha | Implementing Captcha in Login Screen | MOS-25105 |  | Story | Desirable | 3.9 | Rounak.Nayak |  | We will only use KeyCloak Captcha Feature
85 | Logout | API: As the MOSIP Admin Application, I should be able to log-out a user | MOS-23855 |  | Story | Vital | 2.6 | Amandeep.Khanuja
86 | Logout | UI: As the MOSIP Administrator, I should be able to logout of the Admin portal | MOS-23248 |  | Story | Vital | 2.6 | Resham.Chugani |  | Key Cloak Feature
87 | Machine Activate/Deactivate | UI: As the MOSIP Administrator, I should be able to Activate/Deactivate a Machine | MOS-23641 |  | Story | Desirable | 3.9 | Amandeep.Khanuja
88 | Machine Activate/Deactivate | API: As the MOSIP Admin Application, I should be able to update the number of Kiosk for a Registration Center for every deactivation of the assigned machine | MOS-25212 |  | Story | Vital | 3.9
89 | Machine Activate/Deactivate | API: As the MOSIP Admin Application, I should enable functionality to activate or deactivate a Machine | MOS-25635 |  | Story | Vital | 3.9
90 | Machine Create | UI: As the MOSIP Administrator, I should be able to create a Machine | MOS-23637 |  | Story | Desirable | 3.9 | Amandeep.Khanuja
91 | Machine Create | API: As the MOSIP Admin Application, I should enable functionality to create a Machine | MOS-23636 |  | Story | Vital | 3.9 | Amandeep.Khanuja | MOS Sprint 12
92 | Machine Decommission | API: As the MOSIP Admin Application, I should enable functionality to decommission a Machine | MOS-25262 |  | Story | Vital | 3.9
93 | Machine Decommission | UI: As the MOSIP Administrator, I should be able to Decommission a Machine | MOS-25371 |  | Story | Desirable | 3.9
94 | Machine History Storage | API: As the MOSIP Admin Application, I should enable functionality to store history of Creations and Updation of Machines | MOS-24830 |  | Story | Vital | 3.25 | Amandeep.Khanuja
95 | Machine List View | UI: As the MOSIP Administrator, I should be able to view list of Machines | MOS-23623 |  | Story | Vital | 2.6 | Amandeep.Khanuja
96 | Machine List View | API: As the MOSIP Admin Application, I should enable functionality to view list of Machines | MOS-23622 |  | Story | Vital | 3.9 | Amandeep.Khanuja | MOS Sprint 12
97 | Machine List View | UI: As the MOSIP system, I should be able to view associated Machines for a Registration Center | MOS-25369 |  | Story | Desirable | 6.5
98 | Machine Update | UI: As the MOSIP Administrator, I should be able to Update details of a Machine | MOS-23639 |  | Story | Desirable | 3.9 | Amandeep.Khanuja
99 | Machine Update | API: As the MOSIP Admin Application, I should enable functionality to Update details of a Machine | MOS-23638 |  | Story | Vital | 2.6 | Amandeep.Khanuja | MOS Sprint 12
100 | Machine View | UI: As the MOSIP Administrator, I should be able to view complete details of a Machine | MOS-23784 |  | Story | Vital | 4.55 | Amandeep.Khanuja
101 | Masterdata View | UI: As the MOSIP Administrator, I should be able to view list of Masterdata Types | MOS-23896 |  | Story | Vital | 3.9 | Amandeep.Khanuja
102 | Masterdata View | API: As the MOSIP Admin Application, I should be able to fetch list of Masterdata Types in all the languages | MOS-23787 |  | Story | Vital | 3.9 | Amandeep.Khanuja
103 | Masterdata View | UI: As the MOSIP Administrator, I should be able view List of Masterdata for each Masterdata Type | MOS-23613 |  | Story | Vital | 5.2 | Amandeep.Khanuja
104 | Masterdata View | API: As the MOSIP Admin Application, I should enable functionality to view Masterdata | MOS-23612 |  | Story | Vital | 6.5 | Amandeep.Khanuja | MOS Sprint 12
105 | Mobile Number Validation | API: As the MOSIP Admin Application, I should be able to validate if a Mobile Number is registered in User Database | MOS-23897 |  | Story | Desirable | 3.25 | Amandeep.Khanuja | MOS Sprint 12 | Key Cloak Feature
106 | Navigation | UI: As the MOSIP Administrator, I should be able to view profile management functionalities under Profile Management Option | MOS-25362 |  | Story | Vital | 5.2 |  |  | Key Cloak Feature
107 | Navigation | UI: As the MOSIP Administrator, I should have a left Navigation menu with options to access required functionalities | MOS-25363 |  | Story | Vital | 3.9
108 | Machine Update | API: As the MOSIP Admin Application, I should enable functionality to update a Machine_Part 2 | MOS-24947 |  | Story | Vital | 3.9 | Amandeep.Khanuja
109 | Location Create | API: As the MOSIP Admin Application, I should enable functionality to create a Location_Part2 | MOS-24833 |  | Story | Vital | 5.2 | Amandeep.Khanuja
110 | Requirement Detailing | Requirements detailing for "Admin" - API stories | MOS-24172 |  | Story | Vital | 11 | Amandeep.Khanuja
111 | Reset Password | UI: As the MOSIP Administrator, I should be able to reset my User Password | MOS-23689 |  | Story | Desirable | 3.9 | Amandeep.Khanuja |  | Key Cloak Feature
112 | Reset Password | API: As the MOSIP Admin Application, I should enable functionality to reset User Password | MOS-23688 |  | Story | Desirable | 5.2 | Amandeep.Khanuja |  | Key Cloak Feature
113 | Sort/Filter/Search | UI: As the MOSIP Administrator, I should be able to Sort/Filter/Search on a column when in a List view page on Admin Portal | MOS-25367 |  | Story | Vital | 7.8
114 | Tech Story | Tech Story - Setup LDAP | MOS-25625 |  | Story | Vital | 2.6
115 | Tech Story | Tech Story - Create Jenkins Pipeline | MOS-25626 |  | Story | Vital | 5.2
116 | Tech Story | Tech Story - Create a separate environment for Admin | MOS-25627 |  | Story | Vital | 5.2
117 | Tech Story | Tech Story - Restructure UI Project Structure | MOS-25628 |  | Story | Vital | 2.6
118 | UIN Activation/Deactivation | UI: As the MOSIP Administrator, I should be able to Deactivate/Activate a UIN | MOS-23694 |  | Story | Desirable | 5.2 | Amandeep.Khanuja
119 | UIN Activation/Deactivation | API: As the MOSIP Admin Application, I should enable functionality to Deactivate/Activate a UIN | MOS-23693 |  | Story | Desirable | 9.1 | Amandeep.Khanuja
120 | UIN Activation/Deactivation | UI: As the MOSIP Administrator, I should be able to Activate and Deactivate a MOSIP Administrator | MOS-23683 |  | Story | Desirable | 2.6 | Amandeep.Khanuja |  | Key Cloak Feature
121 | User Blacklist | UI: As the MOSIP Administrator, I should be able to Blacklist and Whitelist a MOSIP Administrator | MOS-23687 |  | Story | Desirable | 3.9 | Amandeep.Khanuja |  | Key Cloak Feature
122 | User Creation | Tech Story - Modify code for Ldap | MOS-24834 |  | Story | Vital | 3.9 | Amandeep.Khanuja
123 | User Creation | API: As the MOSIP Admin Application, I should enable functionality to Add Password and RID against a Username | MOS-24723 |  | Story | Desirable | 2.6 | Amandeep.Khanuja
124 | User Creation | Tech Story - API - Change the existing Auth (LDAP) code | MOS-24722 |  | Story | Vital | 5.2 | Amandeep.Khanuja | MOS Sprint 12
125 | User Creation | UI: As the potential MOSIP Administrator, I should be able to complete my Registration into MOSIP | MOS-23681 |  | Story | Desirable | 2.6 | Amandeep.Khanuja |  | Key Cloak Feature
126 | User Creation | UI: As the MOSIP Administrator, I should be able create a MOSIP Administrator | MOS-23679 |  | Story | Desirable | 5.2 | Amandeep.Khanuja |  | Key Cloak Feature
127 | User Creation | API: As the MOSIP Admin Application, I should enable functionality to create a MOSIP User | MOS-23678 |  | Story | Vital | 6.5 | Amandeep.Khanuja |  | Key Cloak Feature
128 | User History Storage | API: As the MOSIP Admin Application, I should enable functionality to store history of Creations and Updation of Users | MOS-24832 |  | Story | Vital | 2.6 | Amandeep.Khanuja
129 | User List View | UI: As the MOSIP Administrator, I should be able to view list of Users | MOS-23615 |  | Story | Vital | 2.6 | Amandeep.Khanuja |  | Key Cloak Feature
130 | User List View | API: As the MOSIP Admin Application, I should enable functionality to view list of Users | MOS-23614 |  | Story | Vital | 2.6 | Amandeep.Khanuja | MOS Sprint 12
131 | User Update | UI: As the MOSIP Administrator, I should be able to edit a User Details | MOS-23682 |  | Story | Desirable | 3.9 | Amandeep.Khanuja |  | Key Cloak Feature
132 | User View | UI: As the MOSIP Administrator, I should be able to view complete details of a User | MOS-23786 |  | Story | Vital | 2.6 | Amandeep.Khanuja
133 | Username Validation | API: As the MOSIP Admin Application, I should be able to validate if a Username is registered in User Database | MOS-23898 |  | Story | Desirable | 2.6 | Amandeep.Khanuja | MOS Sprint 12
134 | Validate ID Schema | API: As the MOSIP Admin Application, I should be able to validate the ID Schema | MOS-23790 |  | Story | Desirable | 7.8 | Amandeep.Khanuja
135 | Validate Process Flow Config | API: As the MOSIP Admin Application, I should be able to validate Document Upload rule in Process Flow Configurations | MOS-23692 |  | Story | Desirable | 5.2 | Amandeep.Khanuja
136 | View Packet Status | UI: As the MOSIP Administrator, I should be able to check UIN Generation status against a given RID | MOS-23696 |  | Story | Desirable | 5.2 | Amandeep.Khanuja
137 | View Packet Status | API: As the MOSIP Admin Application, I should enable functionality to check UIN Generation status against a given RID | MOS-23695 |  | Story | Desirable | 6.5 | Amandeep.Khanuja
138 | Document Category-Type Mapping View | API: Implementation for Document Category-Type Mapping Search | MOS-26636 |  | Story | Vital | 5.2 |  | MOS FIT 5
139 | Titles View | API: Implementation for Titles Search | MOS-26173 |  | Story | Vital | 3.9 |  | MOS FIT 5
140 | Templates View | API: Implementation for Templates Search | MOS-26172 |  | Story | Vital | 3.9 |  | MOS FIT 5
141 | Location Data View | API: Implementation for Location Data Search | MOS-26171 |  | Story | Vital | 5.2 |  | MOS FIT 5
142 | Holidays View | API: Implementation for Holidays Search | MOS-26170 |  | Story | Vital | 3.9 |  | MOS FIT 5
143 | Individual Types View | API: Implementation for Individual Types Search | MOS-26169 |  | Story | Vital | 3.9 |  | MOS FIT 5
144 | Genders View | API: Implementation for Genders Search | MOS-26168 |  | Story | Vital | 3.9 |  | MOS FIT 5
145 | Document Types View | API: Implementation for Document Types Search | MOS-26167 |  | Story | Vital | 5.2 |  | MOS FIT 5
146 | Document Category View | API: Implementation for Document Category Search | MOS-26166 |  | Story | Vital | 5.2 |  | MOS FIT 5
147 | Center Types View | API: Implementation for Center Types Search | MOS-26165 |  | Story | Vital | 3.9 |  | MOS FIT 5
148 | Machine Specifications View | API: Implementation for Machine Specifications Search | MOS-26164 |  | Story | Vital | 3.9 |  | MOS FIT 5
149 | Machine Types View | API: Implementation for Machine Types Search | MOS-26163 |  | Story | Vital | 5.2 |  | MOS FIT 5
150 | Device Specifications View | API: Implementation for Device Specifications Search | MOS-26162 |  | Story | Vital | 5.2 |  | MOS FIT 5
151 | Device Types View | API: Implementation for Device Types Search | MOS-26161 |  | Story | Vital | 5.2 |  | MOS FIT 5
152 | Blacklisted Word View | API: Implementation for Blacklisted Word Search | MOS-26160 |  | Story | Vital | 5.2 |  | MOS FIT 5
153 | Machine View | API: Implementation for Machine Search | MOS-26156 |  | Story | Vital | 5.2 |  | MOS FIT 5
154 | Device View | API: Implementation for Device Search | MOS-26106 |  | Story | Vital | 5.2 |  | MOS FIT 5
155 | Search Utility | API: As the MOSIP Admin Application, I should be able to support Look Ahead filter and Wildcard search | MOS-25831 |  | Story | Vital | 6.5 |  | MOS FIT 5
156 | Login | UI: As the MOSIP Administration, I should be able to login into Admin Application using Key-Cloak UI by providing Username and Password | MOS-25710 |  | Story | Vital | 14.3 |  | MOS FIT 5
157 | Ui Template - Detail View | UI: As the MOSIP Admin Application, I should be able to provide a UI template screen for Detail view of a record for an entity in multiple languages | MOS-25705 |  | Story | Vital | 5.2 |  | MOS FIT 5
158 | Ui Template - List View | UI: As the MOSIP Admin Application, I should be able to provide a UI template screen for List view of entities | MOS-25703 |  | Story | Vital | 6.5 |  | MOS FIT 5
159 | Document Type Update | API: As the MOSIP Admin Application, I should not allow update of a Document Type if all the mandatory data is not received in all the country supported languages | MOS-26656 |  | Story | Vital | 3.9
160 | Document Type Create | API: As the MOSIP Admin Application, I should not allow create of a Document Type if all the mandatory data is not received in all the country supported languages | MOS-26655 |  | Story | Vital | 3.9
161 | Center Update | UI: Updation of Registration Center - Add Zone as a drop-down field and replace Stubbed values by Configurable Values | MOS-26654 |  | Story | Desirable | 6.5
162 | Center Create | UI: Creation of Registration Center - Add Zone as a drop-down field and replace Stubbed values by Configurable Values | MOS-26653 |  | Story | Desirable | 6.5
163 | Center Update | API: As the MOSIP Admin Application, I should only allow updation of Registration Center belonging to the Zone of the Administrator | MOS-26652 |  | Story | Vital | 3.9
164 | Center Create | API: As the MOSIP Admin Application, I should enable creation of Registration Center only to the Zone of the Administrator | MOS-26643 |  | Story | Vital | 3.9
165 | Center View | UI: As the MOSIP Administrator, I should only be able to see Registration Centers assigned only to my Zone | MOS-26640 |  | Story | Vital | 3.9
166 | Device Update | API: As the MOSIP Admin Application, I should enable functionality to update a Device_Part 2 | MOS-26637 |  | Story | Vital | 3.9
167 | Device Create | API: As the MOSIP Admin Application, I should enable functionality to create a Device_Part 2 | MOS-26408 |  | Story | Vital | 3.9
168 | Machine Create | API: As the MOSIP Admin Application, I should enable functionality to create a Machine_Part 2 | MOS-25719 |  | Story | Vital | 3.9
169 | Location Clone | UI: As the MOSIP Administration, I should be able to clone a Location data so that I can create a new Location | MOS-26393 |  | Story | Desirable | 3.9
170 | UIN Activation/Deactivation | UI: As the MOSIP Admin Application, I should support maker-checker process for UIN Deactivation/Activation | MOS-26392 |  | Story | Desirable | 3.9 |  |  | More Clarification Needed
171 | Center-Device View | UI: As the MOSIP Administrator, I should be able to view list of all Devices from the List of Registration Centers | MOS-25640 |  | Story | Desirable | 3.9
172 | Center-Machine View | UI: As the MOSIP Administrator, I should be able to view list of all Machines from the List of Registration Centers | MOS-25639 |  | Story | Desirable | 3.9
173 | Ui Template - Detail View | UI: As the MOSIP Admin Application, I should be able to provide a UI template screen for Detail view of a record for an entity in Single language | MOS-25709 |  | Story | Desirable | De-scoped
174 | Masterdata Detail View | UI: As the MOSIP Administrator, I should be able to view complete details of a particular entity for any Masterdata Types | MOS-23784 |  | Story | Vital | 18.2 |  | Sprint 13
175 | Masterdata List View | UI: As the MOSIP Administrator, I should be able to view list of any Masterdata Type | MOS-23623 |  | Story | Vital | 6.5 |  | Sprint 13
176 | Machine List View | API: Update Implementation for Machine Search API | MOS-27021 |  | Story | Vital | 2.6 |  | Sprint 13
177 | Device List View | API: Update Implementation for Devices Search API | MOS-27022 |  | Story | Vital | 2.6 |  | Sprint 13
178 | Center List View | API: Update Implementation for Registration Center Search API | MOS-27020 |  | Story | Vital | 5.2 |  | Sprint 13
179 | Capture User Zone | API: Implement Utility to capture zone for a User | MOS-27017 |  | Story | Vital | 3.9 |  | Sprint 13
180 | List view Filter | API: Support search by a "Text" value in the Filter API | MOS-27019 |  | Story | Vital | 2.6 |  | Sprint 13
181 | Device Provider Management | API: Implementation of Device Provider Management | MOS-27315 |  | Story | Vital |  |  |  | Yet to be analyzed for estimates

## Partner Management
Story Backlog: Partner Management
S.No. | Feature | Summary | Issue key | Requirement Description | Issue Type | Priority | Estimates - Incl. Testing (PDs) | Reporter | Comments
1 | Digital Certificate Signing/Resigning | As the MOSIP system, I should be able to Validate and Re-Issue the Digital Certificate provided by a Partner | MOS-24500 |  |  | Vital | 10.4 |  | Sharing the Digital Certificate to Partners and Partners Uploading their certificates
2 |  | As the MOSIP system - PM, I should be able to integrate with kernel for Partner Certificate signing and resigning | MOS-24068 |  |  | Vital | 9.1
3 | ID/Key Generation and Validation | Tech Story - Integrate with kernel for MISP License Key Generation | MOS-24069 |  |  | Vital | 6.5 |  | Kernel to encrypt/De-crypt MISP LK
4 |  | As the MOSIP system I should be able to validate Partner api key pattern | MOS-26025 |  |  | Vital | 6.5 |  | Kernel to validate paatern, encryption and decryption
5 |  | As the MOSIP system, I should be able to generate Partner api key | MOS-26024 |  |  | Vital | 6.5
6 |  | As the MOSIP system , I should be able to generate Partner Manager ID | MOS-26023 |  |  | Vital | 6.5
7 |  | As the MOSIP system, I should be able to generate Policy Manager ID | MOS-26022 |  |  | Vital | 6.5
8 |  | As the MOSIP system, I should be able to generate MISP ID | MOS-26021 |  |  | Vital | 6.5
9 |  | As the MOSIP system- PM, I should be able to integrate with kernel to integrate kernel dependencies [To be deleted] | MOS-24504 |  |  | Vital | 0
10 |  | As the MOSIP system , I should be able to accomodate key Management related features - key Generation, key Validation and Key Re-generation | MOS-24072 |  |  | Vital | 7.8
11 |  | As the MOSIP system, I should be able to validate MISP License Key Pattern | MOS-24071 |  |  | Vital | 5.85
12 |  | Tech Story - Integrate with kernel for MISP ID Generation [To be deleted] | MOS-24070 |  |  | Vital | 5.2 |  | Now a part of Partner Mgmt
13 |  | As the MOSIP system, I should be able to validate Partner ID pattern | MOS-24067 |  |  | Vital | 6.5 |  | Now a part of Partner Mgmt
14 |  | As the MOSIP system, I should be able to generate Partner ID | MOS-24066 |  |  | Vital | 6.5 |  | Now a part of Partner Mgmt
15 | Integration with IDA for PM | As the MOSIP system- PM, I should be able to integrate with IDA to provide IDA requested services | MOS-24503 |  |  | Vital | 7.8
16 | Master Data Management | As the MOSIP system, I should be able to define the master data for PM services | MOS-24481 |  |  | Vital | 11.7
17 | MISP Self-Service | As the MOSIP system, I should be able to regenerate license keys | MOS-24479 |  |  | Vital | 7.8
18 | NFR | As the MOSIP system - PM, I should be able to implement the NFR requirements | MOS-24505 |  |  | Essential | 33.8 |  | This would cover Logging, Tracing, Performance, Load, Availability, Security, Config
19 | Partner API key Issuance/Management | As the partner Manager, I should be able to update Partner api key to Policy Mappings | MOS-26026 |  |  | Vital | 6.5
20 |  | As the Partner Manager, I should be able to activate/deactivate Partner api key based on 'policy group' | MOS-26020 |  |  | Vital | 6.5
21 |  | As the Partner Manager, I should be able to approve/reject Partner api key requests based on 'policy group' | MOS-26019 |  |  | Vital | 6.5
22 |  | As the Partner Manager, I should be able to view Partner api key requests based on 'policy group' | MOS-26018 |  |  | Vital | 5.85
23 |  | As the Partner Manger, I should be able to retrieve Partner API key to Policy Mappings | MOS-24492 |  |  | Vital | 6.5
24 |  | As the Partner Manager, I should be able to Create Partner API key to Policy Mappings | MOS-24491 |  |  | Vital | 6.5
25 | Partner Authentication | As the MOSIP system, I should be able to check status of a Partner | MOS-24490 |  |  | Vital | 6.5
26 |  | As the MOSIP system - IDA, I should be able to retrive policy of a partner with partner-ID and partner api key | MOS-24478 |  |  | Vital | 7.8
27 | Partner Management | As the Partner Manager, I should be able to view Auth/E-KYC Partners | MOS-26017 |  |  | Vital | 6.5
28 |  | As the Partner Manager, I should be able to deactivate Auth/E-KYC Partners | MOS-24489 |  |  | Vital | 6.5
29 | Partner Self-Service | As the Partners, I should be able to View Partner api key request status | MOS-26016 |  |  | Vital | 6.5
30 |  | As the Partners, I should be able to submit Partner api key request | MOS-26015 |  |  | Vital | 6.5
31 |  | As the Partners, I should be able to update Auth/E-KYC Partners | MOS-24488 |  |  | Vital | 6.5
32 |  | As the Partners, I should be able to retrieve Auth/E-KYC Partners | MOS-24487 |  |  | Vital | 6.5
33 |  | As the Partners, I should be able to Create Auth/E-KYC Partners | MOS-24486 |  |  | Vital | 6.5
34 | Policy Management | As the MOSIP system, I should be able to deactivate Auth/E-KYC Policy | MOS-26014 |  |  | Vital | 7.8
35 |  | As the MOSIP system, I should be able to update Auth/E-KYC Policy | MOS-26013 |  |  | Vital | 7.8
36 |  | As the Policy Manger, I should be able to retrieve Auth/E-KYC Policy | MOS-24483 |  |  | Vital | 5.2
37 |  | As the Policy Manager, I should be able to Create Auth/E-KYC Policy | MOS-24482 |  |  | Vital | 6.5
38 | Public Key Management | As the MOSIP system, I should be able to retrieve Public key from Partners for encryption of e-kyc response | MOS-24502 |  |  | Vital | 7.8
39 |  | As the MOSIP system, I should be able to distribute Public Key to Partners for Encryption of auth/KYC Request | MOS-24501 |  |  | Vital | 7.8
40 | Role Management | Tech Story - integrate with Kernel (IAM) for Role Mangement for PM services | MOS-24473 |  |  | Vital | 10.4
41 | User Management - Admin | As the MOSIP Admin, I should be able to deactivate Partner Managers | MOS-26012 |  |  | Vital | 6.5
42 |  | As the MOSIP Admin, I should be able to update Partner Managers | MOS-26011 |  |  | Vital | 6.5
43 |  | As the MOSIP Admin, I should be able to retrieve Partner Managers | MOS-26010 |  |  | Vital | 6.5
44 |  | As the MOSIP Admin, I should be able to Create Partner Managers | MOS-26009 |  |  | Vital | 0 |  | Part of IAM
45 |  | As the MOSIP Admin, I should be able to deactivate Policy Managers | MOS-26008 |  |  | Vital | 7.8
46 |  | As the MOSIP Admin, I should be able to update Policy Manager | MOS-26007 |  |  | Vital | 7.8
47 |  | As the MOSIP Admin, I should be able to retrieve Policy Managers | MOS-26005 |  |  | Vital | 6.5
48 |  | As the MOSIP Admin, I should be able to Create Policy Managers | MOS-26003 |  |  | Vital | 0 |  | Part of IAM
49 |  | As the MOSIP Admin, I should be able to deactivate/suspend MISPs (update MISP License Key Status) | MOS-24477 |  |  | Vital | 9.1
50 |  | As the MOSIP Admin, I should be able to update MISPs | MOS-24476 |  |  | Vital | 7.8
51 |  | As the MOSIP Admin, I should be able to retrieve MISPs | MOS-24475 |  |  | Vital | 5.85
52 |  | As the MOSIP Admin, I should be able to Create MISPs (MOSIP Infrastructure Service Provider) | MOS-24474 |  |  | Vital | 6.5
373.75