## Planning
Category | (Multiple Items)
Current Status | (Multiple Items)
Sum of Estimates | Column Labels
Row Labels | Admin | ID-Authentication | ID-Repository | Kernel | Pre-registration | Registration Client | Registration Processor | Testing | Grand Total
Real Biometrics Release - Additional | 89.7 | 70 | 48 | 63 | 23 | 170 | 52 | 70 | 585.7
Real Biometrics Release - Integration |  | 148 | 20 |  |  | 582 | 85 |  | 835
Grand Total | 89.7 | 218 | 68 | 63 | 23 | 752 | 137 | 70 | 1420.7

## Consolidated
MOSIP - Consolidated Roadmap post 30Jun
S. No. | Module/Area | Feature | Release Category | Story Title | JIRA IDs | Description | Category | Priority: P1/P2 | Current Status | Sprint | Dependency | Estimates - Incl. Testing (PDs) | Estimates - Kernel | Estimates - Admin | Estimates - Pre-registration | Estimates - Registration client | Estimates - Registration Processor | Estimates - ID Authentication | Estimates - ID Repository | Estimates - Partner Management | Estimates - Resident Services | Comments | SK Comments | Priority | Priority | Ramesh's Comments
1 | General | Refactoring of MOSIP repository | Additional |  |  | 1. Aligning current MOSIP git repository to the open source one 2. Others if any | Vital |  |  |  |  | 10 |  |  |  |  | 10
2 | Registration Processor | Resident Services Requirement | Additional | As Registration Processor, I should be able to find a LOST UIN/RID when requested from Resident Portal | MOS-24767 | Retriving a LOST UIN/RID when requested from Resident Services | Vital | P1 | Story approved |  |  | 76 | [9 empty] | Task Breakdown 1. Development due to batabase changes to hold email, mobile 2. Impact on the existing flows due to new fields 3. API development 4. Integration efforts for all scenerios 5. Security 6. Logging & Auditing
3 | Registration Processor | Resident Services Requirement | Additional | As Registration Processor, I should be able to receive the UIN/VID and provide the e-UIN as response | MOS-24108 | Retriving a E-UIN Card using UIN/VID when requested from Resident Services | Vital | P1 | Story approved |  |  | 24 | [9 empty] | Task Breakdown 1. API development 2. Integration with ID repo to get response 3. Security 4. Logging & Auditing Dependency Kernel to Provide Password in PDF
4 | Registration Processor | Resident Services Requirement | Additional | As Registration Processor, I should be able to get the Status of a UIN based on a RID for Resident Services | MOS-24107 | Retriving Status of Packet using RID when requested from Resident Services | Vital | NA | Development Completed | NA |  | 0 | [9 empty] | No Development Needed - Feature Already Exists
5 | Registration Processor | Resident Services Requirement | Additional | As Registration Processor, I should be able to process Update Packet coming from Resident Services | MOS-24106 | Update Individual's Demographics when requested from Resident Services | Vital | P1 | Story approved |  |  | 40 | [9 empty] | Task Breakdown 1. Configuration to identify fields to be edited 2. Validation based on the configuration 3. API development 4. Camel configuration 5. Security 6. Logging & Auditing
6 | Registration Processor | Resident Services Requirement | Additional | As Registration Processor, I should be able to Receive and Process a Re-Print Request for a UIN from Resident Services | MOS-24104 | Sending UIN Card for Printing using UIN when requested from Residnet Services | Vital | P1 | Development Completed | Sprint 14 |  | 56 | [9 empty] | Task Breakdown 1. API for print request 2. Camel flow configuration 3. Update validation logic 4. Integration testing 5. Security 6. Logging & Auditing
7 | Registration Processor | Resident Services Requirement | Additional | As Registration Processor, I should be able to provide a Resident an External Link to Download a Password Protected UIN Card | MOS-24943 | Reg Proc should be able to provide an external link so that Resident should be able to download a Password protected UIN card | Vital | P1 | Story approved |  |  | 76 | [9 empty] | Task Breakdown 1. 2 API development 2. Encription, Decription of URL data 3. Fetch data from ID repo 4. Security implementation 5. Security 6. Logging & Auditing
8 | Registration Processor | Admin Requirement | Additional | Send Packet Status History of a Packet Using RID | MOS-23848 - Gap and basis of estimate to be rechecked | Send Packet Status history of a Packet using RID when requested from Admin | Vital | P1 | Development Completed | Sprint 14 |  | 44 | [9 empty] | Task Breakdown 1. API development 2. Configuration to hold message id and message (language specific) 3. Messages to be send in primary language 4. Service and DAO to fetch records 5. Security 6. Logging & Auditing
9 | Registration Processor | Enhancement - Password protected UIN | Additional | Password Protected UIN Card to be Sent for Printing and Text File should have Password | MOS-23306 | Send Password Protected UIN Card to Printing Queue. In Current implementation UIN Card is not password protected. | Essential |  | Requirement Pending |  |  | 12 | [9 empty] | Q. Do we need to Send Password Protected PDF to Printing and Postal Queue? | Description updated - This was an internal observation from Security perspective - To password protect the pdfs sent to Print & postal queue
10 | Registration Processor | Automated check by system to identify photo/age/gender matchness, other validations to reject packets at an early stage based on automated checks | Additional | Automated check by system to identify photo/age/gender matchness, other validations to reject packets at an early stage based on automated checks |  | QC module | Desirable |  | Requirement Pending | [12 empty] | SI customization
11 | Registration Processor | Manual Adjudication System | Additional | Manual Adjudication System |  | Manual Adjudication System/framework - For QC results verification, biometrics duplicate verification, others to be identified | Desirable |  | Requirement Pending | [12 empty] | SI customization
12 | General | Fraud & Data Analytics | Additional | Fraud & Data Analytics |  |  | Desirable |  | Requirement Pending | [12 empty] | SI customization
13 | General | External Integration - Open CRVS / SIA etc | Additional | External Integration - Open CRVS / SIA etc |  |  | Desirable |  | Requirement Pending | [12 empty] | Community contribution
14 | General | Features which can be considered if there is Usecase / demand | Additional | Features which can be considered if there is Usecase / demand |  |  | Desirable |  | Requirement Pending
15 | General | Role of Block Chain in MOSIP (where, how) | Additional | Role of Block Chain in MOSIP (where, how) |  |  | Desirable |  | Requirement Pending | [12 empty] | Community contribution
16 | Pre-registration/Reg. Client | Configurable UI for Pre-reg. & Reg. Client | Additional |  |  | Need clarity for estimating | Vital
17 | Registration Client | Make Reg client - a browser based (with local server) solution (moving away from heavy client) | Additional |  |  | Ramesh can explain more | Desirable | [14 empty] | Community contribution
18 | Registration Client | Installable Dongle for Reg Client. | Additional |  |  |  | Desirable | [14 empty] | Community contribution
19 | Testing | Device Ecosystem testing & certification Target | 0.9.5 - Additional |  |  |  | Vital |  | NA | [12 empty] | Community contribution
20 | Testing | Performance Testing | 0.9.5 - Additional |  |  |  | Vital |  | Not Started
21 | Testing | Security Testing | 0.9.5 - Additional |  |  |  | Vital |  | Not Started
22 | ID-Authentication | Separating ID Repo and ID Auth modules…. i.e., exporting ID data to ID Auth | Additional | Separating ID Repo and ID Auth modules…. i.e., exporting ID data to ID Auth |  |  | Essential? |  | Requirement pending | [12 empty] | Subject to bandwidth
23 | Reporting | Basic system reporting | Additional |  | Need clarity for estimating | System health monitoring reports | Vital
24 | IDA/Resident Services | Offline Verification - QR code with Photo | Additional |  |  | MOSIP to have the ability to consume UIN/VID as input, authenticate the individual with OTP and further generate a document with digitally signed QR code bearing demographic data [Name, Address, Photo, Gender, DOB, registered Phone Number (hashed) and registered Email Address (hashed)] | Vital? |  |  |  |  | 8 | [9 empty] | Subject to bandwidth
25 | ID-Authentication | SPR Seeding for Morocco (HoH requirement) | Additional | SPR Seeding for Morocco (HoH requirement) |  |  | Essential |  | Requirement pending
26 | Registration Client | Registration client sync without running instance or login | Additional |  |  |  | Desirable
27 | General | Audit Logging for Product Management Directives | Additional |  |  |  | Essential?
28 | ID-Authentication | eKYC Auth - Reference App | Additional | eKYC Auth - Reference App |  | eKYC Auth Reference App for Partners | Desirable |  | Requirement pending
29 | Registration Client | Online registration | Additional |  |  |  | Desirable
30 | ID-Authentication | Offline Auth Verification App | Additional | Offline Auth Verification App |  |  | Desirable |  | Requirement pending
31 | General | Browser Support - Support IE | Additional |  |  |  | Essential? | [14 empty] | Krishnan to determine
32 | Testing | Testing: UTC check in APIs, audit and DB entries - Pre-reg, Reg. Client, Reg. Processor, IDA | 0.9.5 - Additional |  |  | UTC check in APIs, audit and DB entries - Pre-reg, Reg. Client, Reg. Processor, IDA | Vital |  | Not Started |  |  | 50 | [9 empty] | Pending testing activities - From Gita
33 | Testing | Testing: Audit log checks - Reg. Client, Reg. Processor | 0.9.5 - Additional |  |  | Audit log checks - Reg. Client, Reg. Processor | Vital |  | Not Started |  |  | 20 | [9 empty] | Pending testing activities - From Gita
34 | Registration Client | Upload Portal for Registration packets | Additional |  |  | Implementation of PacketUpload portal | Vital? |  | Not started |  |  | 100 | [9 empty] | Web application to upload packets
35 | Pre-registration | UX Enhancement - MOSIP | Additional | UI Enhancement - IV & V: Provide a Cancel button and Cross button in all dialog boxes across Pre-registration | MOS-24695 | All dialog boxes across Pre-registration application should have a cross "x" button to allow user to navigate out of the dialog box | Vital |  | NA | [12 empty] | Considered as part of MOS-25102
36 | Pre-registration | UX Enhancement - MOSIP | Additional | UI Enhancement - IV & V: Fix the header of the Pre-registration UI application once logged in | MOS-24691 | Post login, the header/frame of Pre-registration application should be fixed and not get hidden on scrolling down | Vital |  | Development completed | [12 empty] | Already fixed in current implementation
37 | Pre-registration | UX Enhancement - MOSIP | Additional | UI Enhancement - IV & V: Trigger "User Blocked" message in UI if user enters OTP incorrectly x times, as configured | MOS-24679 | On Login, in the event of the user entering the incorrect OTP, the application should render the appropriate functional message equivalent to “USER_BLOCKED” should be displayed in the UI, aligning with the OTP API - Message: “You have crossed the maximum attempts. Please retry after x mins” - Where x is configurable | Vital |  | Development completed | [12 empty] | Already fixed in current implementation
38 | Pre-registration | UX Enhancement - MOSIP | Additional | UI Enhancement - IV & V: Provide a warning message prior to logging out a user on click of "Logout" | MOS-24678 | On click of Logout, provide a confirmation message to user to confirm logout action | Vital |  | Development completed | [12 empty] | Already fixed in current implementation
39 | Pre-registration | UX Enhancement - MOSIP | Additional | Feedback suggestions from Sprint 9 Demo | MOS-20300 | Includes UX enhancements suggested during Sprint 9 demo: - Functional Change: Allow partial search in center selection page | Desirable |  | Development completed | [12 empty] | Already fixed in current implementation
40 | Pre-registration | UX Enhancement - MOSIP | Additional | padding & alignment of existing UI | MOS-26253 | padding & alignment of existing UI | Vital? | P1 | Development In-Progress | Sprint 14/15 |  | 25
41 | Pre-registration | UX Enhancement - MOSIP | Additional | Place Holder for all UX Enhancements deliverable post June 30 Release | MOS-25102 | To accommodate UX revisions based on updated VDs | Vital? | P2 | Requirement pending |  |  | 235.25
42 | Pre-registration | UX Enhancement - GoM | Additional | To accomodate the Location Hierarchy changes as a part of the Demographic form, as per GoM requirement | MOS-14511 | To accomodate the Location Hierarchy changes as a part of the Demographic form, as per GoM requirement | Vital |  | Requirement pending |  |  | 10 | [10 empty] | Desirable, To be decided after GoM interactions
43 | Pre-registration | Removal of Applicant Type | Additional | Currently, documents required to be updated depend on the Applicant Type/Doc Category/Doc Type mapping setup by the admin. This story intends to remove this concept and adopt the process as per Reg. Client (Docs required to be uploaded are driven by fields filled) | MOS-22039 | Currently, documents required to be updated depend on the Applicant Type/Doc Category/Doc Type mapping setup by the admin. This story intends to remove this concept and adopt the process as per Reg. Client (Docs required to be uploaded are driven by fields filled) | Desirable |  | Not started | [13 empty] | OK. Currently, functionally delivered as required. This can be accomodated only to bring in consistency in solutioning between Pre-registration & Registration Client
44 | Pre-registration | Blacklisted Words Validation | Additional | NON-MVP: Blacklisted words Validator Integration | MOS-19541 | Inclusion of blacklisted words validation in both languages for Name and Address fields L1,L2,L3 fields of Demo form: On entry of a Blacklisted word the Individual should be alerted “XXX word(s) are not permitted in the ABC field by the system. Please correct it”. | Desirable |  | Not started
45 | Pre-registration | Configurability of Features | Additional | NON-MVP: Switching on/off of Features for Pre-Registration | MOS-15474 | Ability to switch on/off a feature | Desirable |  | Not started | [12 empty] | Architects to further discuss
46 | Pre-registration | OCR for Document quality check | Additional | Non MVP:As the MOSIP Pre-Registration System, I should be able to perform OCR for Document quality check | MOS-13147 | Perform OCR validation on docs uploaded, to evaluate Doc quality, validate data of doc | Desirable |  | Not started | [12 empty] | Community contribution
47 | Pre-registration | Group Concept | Additional | Non MVP: Group Concept during Pre-registration | MOS-13133 | Include ability to make a group booking, by providing the total number of members in group | Desirable |  | Not started
48 | Pre-registration | Reminders to Applicant | Additional | Non MVP: As a MOSIP System, I should be able to trigger reminder(s) to an individual prior to the booked appointment, as configured | MOS-13059 | Trigger reminder(s) to an individual, prior to the booked appointment | Desirable |  | Not started | [12 empty] | Community contribution
49 | Pre-registration | Login - With Username & Password | Additional | Non MVP: As an Individual, I should be able to login to the pre-registration application by providing the user ID (mobile/email) and password and OTP:UI | MOS-790 | Ability to login with Username & Password Currently - Login is possible only with Mobile/Email id - UI | Desirable |  | Not started | [12 empty] | Community contribution | OK, Community contribution
50 | Pre-registration | Login - With Username & Password | Additional | Non MVP: As an Individual, I should be able to login to the pre-registration application by providing the user ID (mobile/email) and password and OTP | MOS-621 | Ability to login with Username & Password Currently - Login is possible only with Mobile/Email id - API | Desirable |  | Not started | [12 empty] | Community contribution | OK, Community contribution
51 | Pre-registration | Password Management | Additional | Non MVP: As an Individual, I should be able to reset the password for the user ID:UI | MOS-791 | Ability to manage profile and reset password - API | Desirable |  | Not started | [12 empty] | Community contribution | OK, Community contribution
52 | Pre-registration | Password Management | Additional | Non MVP: As an Individual, I should be able to reset the password for the user ID | MOS-622 | Ability to manage profile and reset password - UI | Desirable |  | Not started | [12 empty] | Community contribution | OK, Community contribution
53 | Pre-registration | Login - Include Captcha | 0.9.5 - Additional | Implementing Captcha in Login Screen | MOS-25103 | To accommodate captcha feature on Login page | Vital | P2 | Development In-Progress | Sprint 15 |  | 6 | [9 empty] | Task breakdown: For POC, code integration - 3days Unit Test case – 1day Testing in QA and defect fix – 2days |  | P2 |  | Not Priority for 0.9.5 release
54 | Pre-registration | Application Status Enhancement | 0.9.5 - Additional | NON MVP: Pre-Registration Status changes - [Release 1.5] | MOS-19858 | This story is to accommodate change to the various statuses of Pre-registration - To be relevant to its own stage.EG: If docs and/or demo data is updated, the status is still Pending Appointment. Instead, the suggestion was to update it relevant to its respective stage, i.e., Demo Data Updated/Docs Uploaded - To be discussed and evaluated | Desirable |  | NA
55 | Pre-registration | Terminilogy Update | 0.9.5 - Additional | Remove all references to GoM specific terminologies | MOS-27308 | This story is to update the field names in Demographic page and across Pre-registration as below: 1. CNIE/EC Number - Change to “Reference Identity Number” 2. Local Administrative Authority - Change to “Zone” | Vital | P1 | Development completed | Sprint 14
56 | Pre-registration | Primary & Secondary Language - System behavior analysis/update | Additional | Primary & Secondary Language - System behavior analysis/update | MOS-27436 | This story will define the revised System behavior: - When Primary and Secondary language is set to the same parameter _ When Primary and/or Secondary language is not set at all | Vital? |  | Not started |  |  | 5
57 | Pre-registration | Accessibility to Pre-registration portal | Additional | Accessibility to Pre-registration portal | MOS-28049 | Pre-registration portal to Support Color blindness, partial/complete blindness, during Pre-registration | Vital? |  | Not started | [12 empty] | This is external interface Probably External SDK to be implemented. Requirement not clear.
58 | Pre-registration | Cancel appointments for change in Working Hours | 0.9.5 - Additional | Implement Working hours change for a Registration Center | MOS-28249 | Pre-registration portal to Support cancellation of appointments if working hours are changed for a Registration Centre | Vital | P1 | Internal Analysis Pending | Sprint 15 | Admin | 10 | [9 empty] | Backend code-change . Construction of new API or restructuring existing api and bad job, interaction with admin console.
59 | Pre-registration | KeyCloak Integration | 0.9.5 - Additional | As MOSIP pre registration, I should be able to intergate with KeyCloak for API Authentication |  | Integration with KeyCloak for User as well as API Authentication | Vital | P1 | Not started |  |  | 7 | [9 empty] | Replacing auth adapater with Keycloak Code change in Pre-Reg API changes Unit test cases |  | P1 | Small | As KeyCloak is implemented for Admin it should be implemented for all Modules
60 | Pre-registration | Documentation | 0.9.5 - Documentation | Documentation for Real Biometrics Release |  | Covers documentation for all features released as part of Real biometrics release | Vital | P1 | Not started |  |  | 10 | [11 empty] | P1 | Small
61 | Registration Client | Age/DoB Calculation Display | Additional | New Registration - Age/Date of Birth: Display auto calculated value for each when the other is entered | MOS-21861 | New Registration - Age/Date of Birth:If we enter age, the DoB should display 01/Jan/xxxx. If we enter DoB, the age should be auto calculated and displayed. Both fields should remain editable. | Vital |  | Development completed | Sprint 14 |  | 6
62 | Registration Client | Parent/Guardian Authentication - Multi factor | Additional | NON MVP:UI: As a registration officer, I should be able to authenticate each introducer based registration with their password/biometrics/multi factor elements. | MOS-1175 | Able to authenticate each introducer based registration with their password/biometrics/multi factor elements. | Desirable
63 | Registration Client | Parent/Guardian Authentication - Multi factor | Additional | NON MVP:As the MOSIP registration client, I should enable introducer to authenticate each introducer based registration with password/biometrics/multi factor elements. | MOS-1320 | Enable introducer to authenticate each introducer based registration with password/biometrics/multi factor elements. | Desirable
64 | Registration Client | Biometric Capture - Device Service Integration | 0.9.5 - Integration | As Registration Client I should be able to Integrate with Biometric SDKs for various local operations | MOS-22410 | MOSIP device manager integration - 3rd party integration. | Vital | P2 | Approved by client |  | SyncByte - SDK | 40 | [9 empty] | Registration Client is not able to integrate with Biometric SDK as it only works in Linux machine. |  | P2 |  | Local operation like Local Dedupe and Operator Auth can be taken later
65 | Registration Client | Biometric Capture - Photo Validations & ICAO Standards check | Additional | Validations for photo in Registration client | MOS-23544 | Registration client needs to check for additional validations of the photo. The application must be able to detect if the photo is a live photo or not. Photo of a Passport photo must not be accepted. | Desirable | [14 empty] | > Community contribution - What pluggability should we provide? > Based on MDS implementation
66 | Registration Client | Biometric Capture - Photo Validations & ICAO Standards check | Additional | As the MOSIP registration client, I should be able to perform face photograph validation during registration | MOS-16008 | Implement ICAO validations that are not implemented in MOS‌-16008: Plain light-coloured background Close up of the head and top of the shoulders so that the face takes up 70–80% of the photograph | Desirable | [14 empty] | > Community contribution - What pluggability should we provide? > Based on MDS implementation
67 | Registration Client | Biometrics- Face capture with additional validations: Liveness check | Additional | Face photo capture | MOS-13522 | Requirements for face photo capture: Provide ability to capture live photo (Maybe a short video instead of a photo) Validate photo captured is a live photo - Do not allow Photo of a human photo (EG: Photo of a passport photograph) | Desirable | [14 empty] | > Community contribution
68 | Registration Client | Biometric Exceptions - Capture multiple docs/photos per exception type | Additional | As a Registration officer , I should be able to capture multiple Biometrics Exception Photos and upload documents to support exceptions | MOS-19011 | Capture Biometrics Exception Photo: 1. Provide ability to capture multiple photos based on each reason and for example, one photo for fingerprint and one photo for iris exception – Either refer or capture different photo for each exception 2. Provide ability to upload documents to support each exception | Desirable
69 | Registration Client | Biometric Exceptions - Manually mark exception for low biometrics quality | Additional | Device - As the MOSIP Registration Client, I should be able to mark low quality biometrics as exceptions | MOS-15999 | Device story for marking low quality biometrics as exceptions | Desirable
70 | Registration Client | Biometrics exception approval - Configuration if approval is required at one/two levels | Additional | Biometrics Exceptions Approval - One or two levels | MOS-13523 | In case of biometric exceptions, provide ability to configure if operator authentication is required at one or two levels | Desirable | [14 empty] | Resham/Shrikant to re-check MOSIP’s ability to turn on/off SPVR authentication vs. GoM requirement on Supervisor authentication a. GoM Requirement: i. As per GoM’s FRS, GoM has two roles - operators and supervisors (collectively referred to as Enrolment Officers or EO). ii. In terms of EO Authentication at the end of each registration, the system should have provision for the capture of biometric of EO as a proof of confirmation of the following: • EO has performed enrolment • EO has verified the information • EO has followed prescribed procedure and guidelines iii. However, as per recent conversations, it was drawn that GoM doesn’t need Supervisor as a role – Hence, Supervisor authentication stage was made configurable b. MOSIP’s current ability to turn on/off SPVR authentication for exceptions: i. This is currently configurable. If turned off, the respective screen doesn’t appear ii. If turned on, the Supervisor auth screen appears – Currently one level of auth by Supervisor
71 | Registration Client | Device/SDK Integration - Biometrics - Fingerprint quality ranking | 0.9.5 - Integration | Device--As the MOSIP Registration Client, I should provide ranking by fingerprint quality in the registration receipt | MOS-12187 | Device story for providing ranking by fingerprint quality in the registration receipt | Essential? | [14 empty] | Subject to bandwidth
72 | Registration Client | Device/SDK Integration - Biometrics - Fingerprint quality ranking | 0.9.5 - Integration | Device--As the MOSIP registration client, I should enable capturing an individual's fingerprints as per quality threshold values defined. | MOS-1291 | Device story for capturing an individual's fingerprints as per quality threshold values defined. | Essential? | [14 empty] | Subject to bandwidth
73 | Registration Client | Device/SDK Integration - Capture Parent's biometric for Child | 0.9.5 - Integration | As MOSIP Registration Client, for new registration of child capture any one biometric of the Parent/Guardian | MOS-21701 | If age of the applicant is less than or equal to 5, capture any one biometric-fingerprint, IRIS of the parent/guardian. In case of Update - It could be any Parent/guardian – Same Parent/guardian as during registration or another Parent/guardian) | Vital | P1 | Approved by client |  | SyncByte - SDK | 20 | [9 empty] | 20 - all bio type integration. |  | P1
74 | Registration Client | Device/SDK Integration - Login with Iris/Face | 0.9.5 - Integration | As the MOSIP Registration Client, I should enable login with Finger Print, Iris and Face | MOS-12185 | During Login for Officer MOSIP should provide multifactor authentication (using username + password and/or OTP, fingerprint, iris). | Vital | P2 | Approved by client |  | SyncByte - SDK | 40 | [9 empty] | 20 - all bio type integration. Dependency on Story - MOS-22410 |  | P2 |  | Duplicate of 64
75 | Registration Client | Device/SDK Integration - Scan PRID QR Code | 0.9.5 - Additional | As the MOSIP Registration Client, I should enable scanning a Pre-registration QR code | MOS-13556 | While starting a new registration, the registration client should support scanning a QR code to populate the pre-registration ID on screen | Vital | P2 | Approval Pending - Device Dependent |  | Device | 60 | [9 empty] | kernel + device dependencies |  | P2
76 | Registration Client | Device/SDK Integration - Iris capture | 0.9.5 - Integration | As the MOSIP registration client, I should enable iris capture as per defined specifications. | MOS-1205 | As the MOSIP registration client, I should enable iris capture as per defined specifications | Vital | NA | Development completed |  |  | 70 | [9 empty] | To be closed in JIRA
77 | Registration Client | Device/SDK Integration - Lost UIN | 0.9.5 - Integration | As a Registration Officer, I should be able to facilitate retrieving a lost UIN | MOS-18989 | Device story for Lost UIN | Vital | P1 | Approved by client | Sprint 16 | Device | 10 | [9 empty] | Integration with Devices for Lost UIN biometrics capture |  | P1 | Small
78 | Registration Client | Device/SDK Integration - UIN Update | 0.9.5 - Integration | As a Registration Officer, I should be able to facilitate Update of a resident's UIN data | MOS-15998 | Device story for UIN update | Vital | P1 | Approved by client | Sprint 16 | Device | 10 | [9 empty] | Integration with Devices for UIN Update biometrics capture |  | P1 | Small
79 | Registration Client | Device/SDK Integration - Registration Officer and Supervisor Onboarding - Capture biometrics | 0.9.5 - Integration | As the MOSIP registration client, I should enable capturing an officer's biometrics during onboarding in order to support login, local duplicate checks and registration submission | MOS-19001 | Enable capturing an officer's biometrics during onboarding in order to support login, local duplicate checks and registration submission | Vital | NA | Development completed |  | - | 40 | [9 empty] | To be closed in JIRA Capture of Officer Biometrics is Development completed
80 | Registration Client | Device/SDK Integration - Registration Officer and Supervisor Onboarding - Authenticate biometrics | 0.9.5 - Integration | As the MOSIP registration client, I should be able to authenticate the Officer's Biometrics before On-boarding the Officer | MOS-22161 | Operator On-boarding - Biometrics Verification via. IDA Internal API | Vital | P1 | Approved by client | Sprint 16 | IDA | 10 | [9 empty] | Intergration with IDA Internal API |  | P1 | Small
81 | Registration Client | Device/SDK Integration - Registration Officer authentication | 0.9.5 - Integration | As the MOSIP Registration Client, I should enable RO to authenticate each registration with biometrics/multi factor elements | MOS-1334 | Enable RO to authenticate each registration with biometrics/multi factor elements | Vital | P2 | Approved by client |  | SyncByte - SDK | 60 | [9 empty] | Dependency on Story - MOS-22410 |  | P2 |  | Duplicate of 64
82 | Registration Client | Device/SDK Integration - UIN update-Scan QR code | Additional | Device- As the MOSIP Registration Client, I should be able to scan a QR code for UIN Update | MOS-19014 | UIN Update: i. Provide ability to scan QR code besides manually entering UIN number - New requirement ii. Additionally, pre-populate data from QR code (if available), based on option selected for update (EG: If address is marked for update, then address to be pre-populated from QR code). Implementation aspects to be discussed - New requirement iii. Evaluate if CNIE/UIN/EC Number Update is required, as if the number captured is incorrect, packet processing would have failed | Desirable | [15 empty] | Desirable
83 | Registration Client | Device/SDK Integration - Local duplicate check for iris and face | 0.9.5 - Integration | As the MOSIP Registration Client, I should perform a local duplicate check for finger print, irises and face of an individual against the mapped registration officers' biometrics | MOS-10555 | Perform a local duplicate check for irises and face of an individual against the mapped registration officers' biometrics | Vital | P2 | Approved by client |  | SyncByte - SDK | 40 | [9 empty] | Dependency on Story - MOS-22410 |  | P2 |  | Duplicate of 64
84 | Registration Client | Stubbed/MDS Implementation - Display device status | Additional | Stub - Device status: Display device status on the header | MOS-15996 | This is the proxy (stubbed) implementation of MOS‌-13562 to display the device statuses on the client as green/red indicators in the header. | Essential | [14 empty] | If MDS is implemented, this will be implied
85 | Registration Client | Validation Checklist - Ability to validate each field/stage of registration/Update (EG: DoB Verification) | Additional | UI: As the Registration Officer, I should be able to mark an individual's date of birth as 'Verified' | MOS-14566 | Mark an individual’s date of birth as ‘Verified’ during new registration or UIN update. | Desirable | [14 empty] | Community contribution
86 | Registration Client |  | Additional | As the MOSIP Registration Client, I should enable marking an individual's date of birth as 'Verified'. | MOS-14565 | Mark an individual’s date of birth as ‘Verified’ during new registration or UIN update. | Desirable | [14 empty] | Community contribution
87 | Registration Client | Introducer attestation (Introducer concept) | Additional | NON MVP:UI - Document Upload/Scan - Introducer Attestation (Others) | MOS-5482 | As a client registration officer, I should be able to upload/scan applicable documents of an introducer(Others), during registration of an applicant | Desirable | [14 empty] | This is already covered by virtue of having Parent/Guardian introducing a Child - MOSIP in any case doesn't maintain relationships
88 | Registration Client | Introducer attestation (Introducer concept) | Additional | NON MVP:As the MOSIP registration client, I should enable uploading/scanning applicable documents of an introducer (Others) during registration of an individual. | MOS-1382 | Should enable uploading/scanning applicable documents of an introducer (Others) during registration of an individual. | Desirable | [14 empty] | This is already covered by virtue of having Parent/Guardian introducing a Child - MOSIP in any case doesn't maintain relationships
89 | Registration Client | Geo-location capture using phone | Additional | Geo-location Capture using GPS:Usage of phones for GPS | MOS-19006 | Geo-location Capture using GPS:1. Usage of phones for GPS vs. GPS on machine | Desirable | [14 empty] | Community contribution
90 | Registration Client | Location Hierarchy Update as per GoM | Additional | As the MOSIP Registration Client, I should support the new Location Hierarchy | MOS-16544 | Reflect the new location hierarchy for Morocco | Vital | P2 | Requierment Pending |  |  | 40 | [9 empty] | Currently Desirable, Dicussion with GOM can change these. | Currently Desirable, Dicussion with GOM can change these.
91 | Registration Client | Login/Authentication - Token to authenticate RO | Additional | Tech story - Registration Client should send a token to Registration processor, when Officer or Supervisor authenticate themselves during Packet Creation | MOS-21523 | Registration Client should send a Token to Registration processor, when Officer or Supervisor authenticate themselves during Packet Creation | Desirable | [14 empty] | Community contribution
92 | Registration Client | Multi factor login - With Biometrics | Additional | NON MVP:As the MOSIP registration client, I should enforce multi factor login for Admin/Reg. users | MOS-8368 | Enforce multi factor login for Admin/Reg. users | Desirable
93 | Registration Client | OCR Document upload | Additional | NON MVP:OCR as part of Document Upload | MOS-12176 | MOSIP should support OCR as part of quality check of documents during document upload. | Desirable | [14 empty] | - Since this is a reference implementation, SI can implement as requried
94 | Registration Client | Operator onboarding - Training content | 0.9.5 - Additional | Operator On-boarding: Placeholder for training content | MOS-21998 | Operator On-boarding: The landing page should have a placeholder for training content. UX team to come up with the design. - Placeholder for Link on Login page/home page to the training content - URL to be made available from Config file | Vital | NA | Development completed | Sprint 14 |  | 30
95 | Registration Client | Proof of consent document (GoP requirement) | Additional | NON MVP: As a Registration Officer, I should be able to capture Proof of Consent Document as required | MOS-18100 | As a Registration Officer, I should be able to capture Proof of Consent Document as required | Desirable | [14 empty] | SI implementation | SI /community - Dsirable, Proof of concent via Document Categories Master.
96 | Registration Client | Reports | Additional | As the MOSIP Registration Client, I should enable generation of end of day reports | MOS-1309 | Include statistics on EoD Approval and Re-registration only | Desirable | [14 empty] | SI implementation
97 | Registration Client | Reports | Additional | UI: As a supervisor, I should be able to generate reports | MOS-1275 | Include statistics on EoD Approval and Re-registration only | Desirable | [14 empty] | SI implementation
98 | Registration Client | Supervisor's/an authorized user's ability to unlock a locked account - GoM requirement | Additional | <Non MVP>:As a Supervisor, I should be able to unlock a user's account on the Registration Client. | MOS-12199 | Supervisor or Admin to unlock a user’s account that has been locked due to five consecutive unsuccessful login attempts. | Desirable | [14 empty] | Community contribution | Desirable, No Use case, Community Contribution, Check with GOM Requirent, else Desirable.
99 | Registration Client | Transliteration in other languages | Additional | <NON MVP >UI: As a registration officer, I should be able to view transliterated data - other than French and Arabic | MOS-1288 | Able to view transliterated data - other than French and Arabic | Desirable | [14 empty] | - Re-factor for pluggability - Move to UI - Standardize interface
100 | Registration Client | Transliteration in other languages | Additional | <NON MVP>As the MOSIP registration client, I should enable viewing transliterated data. - Other than French and Arabic | MOS-1293 | Enable viewing transliterated data. - Other than French and Arabic | Desirable | [14 empty] | - Re-factor for pluggability - Move to UI - Standardize interface
101 | Registration Client | UIN update - VID input to initiate process | Additional | As the MOSIP registration client, I should support input of VID during the UIN Update process | MOS-18319 | As a MOSIP registration client, I should support input of VID to initiate UIN Update | Essential? | [14 empty] | Subject to bandwidth - Reputational impact as per Anadi
102 | Registration Client | UIN update - OTP authentication of UIN holder in real-time (Online mode) | Additional | As the MOSIP registration client, I should support OTP authentication of the individual for UIN update | MOS-19739 | Support OTP authentication of the individual for UIN update | Desirable
103 | Registration Client | UX Enhancement- MOSIP | Additional | Home page: News and Updates to be editable from Admin portal | MOS-22011 | The content in the 'news and updates' section should be configurable. The Admin should be able to add text content through the Admin portal, such as news, announcements, links and training material, and sync to display on the reg. client. | Essential |  |  |  |  | 10 | [9 empty] | Continue with UX VD enhancement track | Can be made essential and moved to SI work
104 | Registration Client | UX Enhancement- MOSIP | Additional | EoD Process 3: Optimize Approve and Reject buttons | MOS-22008 | The 'Approve' and 'Reject' actions should be placed closer to the list. Suggestion - provide 'tick' and 'cross' buttons on each row in the list. Buttons will be greyed out by default and become active when the row is selected. | Desirable |  |  |  |  | 6 | [9 empty] | Continue with UX VD enhancement track | Covered as part of MOS-26779
105 | Registration Client | UX Enhancement- MOSIP | Additional | Proxy Operator On-boarding - Biometrics capture 1: Validate quality before authentication | MOS-22000 | When a biometric is captured, validate that its quality meets the threshold before sending to server for authentication. | Essential |  |  |  |  | 6 | [9 empty] | Continue with UX VD enhancement track | OK
106 | Registration Client | UX Enhancement- MOSIP | Additional | New Registration - Consent: Additional consent attributes | MOS-21924 | Additional attributes for seeking consent. | Desirable |  |  |  |  | 0 | [9 empty] | Continue with UX VD enhancement track | Requirement not applicable. To be deleted
107 | Registration Client | UX Enhancement- MOSIP | Additional | EoD Process 2: Optimize acknowledgement slip display | MOS-22007 | The acknowledgement slip should be smaller - no scrolling should be required. | Essential |  |  |  |  | 10 | [9 empty] | Continue with UX VD enhancement track | Can be made Essential and moved to SI work
108 | Registration Client | UX Enhancement- MOSIP | Additional | New Registration - all screens 3: RHS progress bar and navigation between screens | MOS-21923 | New Registration - all screens: a. RHS progress bar - can we make them links? Implement if feasible. User should be able to jump to any page using RHS and top navigation links. b. Validations - all validations should happen on the preview page when user tries to submit. Display a consolidated error message highlighting which pages have errors. User should be able to jump to the page having errors, make the changes and jump back to preview | Desirable |  |  |  |  | 0 | [9 empty] | Continue with UX VD enhancement track | Covered as part of MOS-26779
109 | Registration Client | UX Enhancement- MOSIP | Additional | New Registration - Address spacing to be optimized | MOS-21870 | The address is too spaced out. Utilize the space better. | Desirable |  |  |  |  | 0 | [9 empty] | Continue with UX VD enhancement track | Covered as part of MOS-26779
110 | Registration Client | UX Enhancement- MOSIP | Additional | Operator On-boarding-Exceptions: Display only iris exceptions for Morocco | MOS-21999 | Operator On-boarding - Exceptions:Morocco screens will capture only irises and not fingerprints. Create a new screen showing iris exceptions aligned at the centre. Similarly if a country captures fingerprints only, the fingerprint exception images should be centre aligned. | Desirable |  |  |  |  | 0 | [9 empty] | Continue with UX VD enhancement track | Covered as part of MOS-26779
111 | Registration Client | UX Enhancement- MOSIP | Additional | EoD Process: As the MOSIP Registration Client, I should display the EoD process with the first packet selected by default | MOS-22006 | The first packet in the EoD process page should be selected by default so that the number of mouse clicks is reduced. | Desirable |  |  |  |  | 0 | [9 empty] | Continue with UX VD enhancement track | Covered as part of MOS-26779
112 | Registration Client | UX Enhancement- MOSIP | 0.9.5 - Additional | Login--UI changes 2: Forgot password should be a link | MOS-21997 | Forgot password should be a link | Vital | P1 | Development completed | Sprint 14 |  | 0 | [9 empty] | Continue with UX VD enhancement track | Covered as part of MOS-26779
113 | Registration Client | UX Enhancement- MOSIP | Additional | New Registration - all screens: Optimize scroll bar | MOS-21887 | Optimize the vertical scroll bar and ensure scrolling is kept as minimum as possible. | Essential |  |  |  |  | 0 | [9 empty] | Continue with UX VD enhancement track | Covered as part of MOS-26779
114 | Registration Client | UX Enhancement- MOSIP | Additional | New Registration - Biometric exceptions: Exception marking on same screen as documents | MOS-21888 | New Registration - Biometric exceptions:Explore the option of having the exception marking on the same screen as the document upload. Utilize the space on the right. | Desirable |  |  |  |  | 0 | [9 empty] | Continue with UX VD enhancement track | Covered as part of MOS-26779
115 | Registration Client | UX Enhancement- MOSIP | Additional | Login--UI changes 1: Forgot username | MOS-21996 | Login:If the RO forgets user name - provide a link to the Admin portal so that the user can retrieve the username | Desirable |  |  |  |  | 0 | [9 empty] | Continue with UX VD enhancement track | Covered as part of MOS-26779
116 | Registration Client | UX Enhancement- MOSIP | Additional | New Registration - Acknowledgement: Print two copies on a single A4 sheet | MOS-21926 | The acknowledgement printout should fit on half an A4 page. Upon click of print, the acknowledgement should be mirrored and the Registration officer should be able to print two copies on a single A4 sheet. | Desirable |  |  |  |  | 20 | [9 empty] | Continue with UX VD enhancement track | SI customization
117 | Registration Client | UX Enhancement- MOSIP | Additional | New registration all screens UI changes - links in the top menu should be clickable | MOS-21860 | New registration all screens UI changes - links in the top menu should be clickable | Desirable |  |  |  |  | 20 | [9 empty] | Continue with UX VD enhancement track | Covered as part of MOS-26779
118 | Registration Client | UX Enhancement- MOSIP | Additional | Place Holder for UX Enhancements deliverable Post June 30 Release | MOS-25101 | This Story is just a Place holder for all the UX Enhancements which would be delivered post-June 30. | Desirable | [14 empty] | Continue with UX VD enhancement track | Covered as part of MOS-26779
119 | Registration Client | UX Enhancement- MOSIP | Additional | Implementing Captcha in Login Screen | MOS-25104 | Implementing Captcha in Login Screen | Essential |  |  |  |  | 20 | [9 empty] | Continue with UX VD enhancement track | Can be moved to Security and they can take a call. This is not a enhancement.
120 | Registration Client | UX Enhancement- MOSIP | Additional | New Registration - Biometric screens 3: Redesign 'Scan' and 'Start Over' buttons | MOS-21922 | a. 'Start Over/Reset' buttons: what happens on click? Revisit the flow.b. 'Scan' button - instead of having the button at the bottom, provide a scan icon on the slap image itself for each biometric. | Desirable |  |  |  |  | 20 | [9 empty] | Continue with UX VD enhancement track | Covered as part of MOS-26779
121 | Registration Client | UX Enhancement- MOSIP | Additional | New Registration - Biometric screens 2: Navigate through the screens in any order | MOS-21921 | New Registration - all screens: RO should be able to go back and forth between demographic, document and biometric screens. Retain the captured data in each screen. For biometrics - retain data whenever possible i.e. for those biometrics not marked as exceptions. | Desirable |  |  |  |  | 60 | [9 empty] | Continue with UX VD enhancement track | Covered as part of MOS-26779
122 | Registration Client | UX Enhancement- MOSIP | Additional | Padding and alignment related changes | MOS-25989 | Padding and alignment related changes | Vital | P1 | Development completed | Sprint 14 |  | 30 | [9 empty] | Continue with UX VD enhancement track | TF to log as bug - To be deleted from here & consolidated sheet.
123 | Registration Client | UX Enhancement- MOSIP | Additional | Additional UX Enhancement- Based on revised VDs | MOS-26779 | Enhancement- Additional enhancements based on revised VDs | Vital? |  | Approval Pending |  |  | 400 | [9 empty] | Continue with UX VD enhancement track | What is this for, where are the details.
124 | Registration Client | UX Enhancement- MOSIP | Additional | New Registration - Transliteration: Virtual keyboard icon placement to be optimized | MOS-21863 | New Registration - Transliteration: The virtual keyboard icon is repeated three times. Can we make it appear in just one place? The keyboard should be available for both Primary and Secondary language. Placement of the keyboard icons can be driven by the UX team (EG: A common icon/placement of cursor to define the language) | Desirable |  |  |  |  | 20 | [9 empty] | Continue with UX VD enhancement track | Covered as part of MOS-26779
125 | Registration Client | UX Enhancement- MOSIP | Additional | New Registration - Biometric exceptions 3: Exception page to display irises only | MOS-21920 | Exception page to display irises only | Desirable |  |  |  |  | 8 | [9 empty] | Continue with UX VD enhancement track | Covered as part of MOS-26779
126 | Registration Client | UX Enhancement- MOSIP | Additional | New Registration - Biometric exceptions 2: Exception finger marking should not colour the entire finger | MOS-21897 | Exception finger marking should not colour the entire finger | Desirable |  |  |  |  | 6 | [9 empty] | Continue with UX VD enhancement track | Covered as part of MOS-26779
127 | Registration Client | UX Enhancement- MOSIP | Additional | New Registration - Demographic fields: Optimize numeric and master data fields that are displayed twice | MOS-21873 | New Registration - Demographic fields: Optimize numeric and master data fields that are displayed twice | Desirable |  |  |  |  | 12 | [9 empty] | Continue with UX VD enhancement track | Covered as part of MOS-26779
128 | Registration Client | UX Enhancement- MOSIP | Additional | Upload packet 2: Reduce table width | MOS-22013 | Upload packet:The width of the table should be reduced and not run across the entire page. | Desirable |  |  |  |  | 10 | [9 empty] | Continue with UX VD enhancement track | Covered as part of MOS-26779
129 | Registration Client | UX Enhancement- MOSIP | Additional | "Save to device" option to be un-hidden with revised UI | MOS-26151 | Save to device option should be hidden until the Upload portal is developed - As per communication from Shrikant. Once the packet upload portal is developed, Save to device option should be made available, with revised UI as per below requirement: The UI should be enhanced such that it is clear for the RO that save to device cannot be Development completed for selected packets. | Vital? |  | Not Started |  |  | 20 | [9 empty] | Continue with UX VD enhancement track | Covered as part of MOS-26779
130 | Registration Client | VID management | Additional | As a MOSIP registration client, I should support VID management | MOS-18483 | VID management - Reference Shrikant: - Ability to provide resident services featrues through Reg. Centre (Revoke VID etc) The use of Reg client is inherently inconvenient, since it involves person to come to a centre and should be used where BIOMETRICS is mandatorily being worked with. VID is only a text data, thus it should be handled only through a public portal interface. The public portal will always need some form of OTP authentication. Thus a mobile/email mandatory comes into a requirement. Thus we can issue VID without mobile, but managing VID lifecycle will need Mobile (for OTP). Not having a mobile as a reason should not be used to consider VID management via reg client. If we are moving to a advanced concepts like VID, expectation of Mobile as mandatory is only practical reality. Review this logic at suitable time, incase VID management via Reg client is contemplated in future versions. An exception to above thinking, which can asked is why is MOBILE No (demographic data) update recommended via Reg Client or with biometric - (a). Mobile is gateway to many services and loss of unlocked mobile can lead to many subsequent losses (including identity theft) thus mobile update is always recommended via Biometric auth. Intermediate STOP point (b) OTP based mobile updated can easily move one lost mobile to another unlown mobile (c) Many such scenarios. | Desirable
131 | Registration Client | Windows Installation script | Additional | Windows Installation Script for Registration Client Installation | MOS-22423 | Windows Installation Script for Registration Client Installation - Batch script | Desirable |  |  |  |  | 100
132 | Registration Client | Download pdf option | Additional | Enhancement- Download pdf option in Reg client | MOS-26354 | Able to download acknowledgement as a pdf using “Download pdf” button | Essential
133 | Registration Client | Terminology Update | 0.9.5 - Additional | Remove all references to GoM specific terminologies | MOS-27321 | This story is to update the field names in Demographic page and across Registration Client as below: 1. CNIE/EC Number - Change to “Reference Identity Number” 2. Local Administrative Authority - Change to “Zone” | Vital | P1 | Development completed | Sprint 14 |  | 10
134 | Registration Client | Primary & Secondary Language - System behavior analysis/update | Additional | Primary & Secondary Language - System behavior analysis/update | MOS-27437 | Primary & Secondary Language - System behavior analysis/update | Desirable | P1
135 | Registration Client | Disk space check should be Development completed on Reg Client before registering a user | 0.9.5 - Additional | Disk space check should be Development completed on Reg Client before registering a user | MOS-27238 |  | Vital | NA | Development completed | Sprint 14 |  | 10
136 | Registration Client | Service side validation | Additional | Registration client service side validation support | MOS-28145 MOS-28144 MOS-28143 MOS-28142 MOS-28141 MOS-28140 MOS-28139 MOS-28138 MOS-28137 MOS-28136 MOS-28135 MOS-28131 MOS-28132 | Registration client service side validation support | Vital | P1 | Development In-Progress | Sprint 15
137 | Registration Client | Quality Check | 0.9.5 - Integration | As the MOSIP registration client I should be able to capture biometrics if it crosses the configured threshold |  | Biometrics should be captured if the quality threshold exceeds the configured value | Vital | P2 | Not Started |  | SyncByte - SDK | 30 | [9 empty] | Modification from Device vendor is needed |  | P2 |  | Quality Check to be done Using SDK not MDS
138 | Registration Client | KeyCloak Integration | 0.9.5 - Additional | As MOSIP registration client, I should be able to intergate with KeyCloak for User & API Authentication |  | Integration with KeyCloak for User as well as API Authentication | Vital | P1 | Not Started |  | Kernel | 5 | [11 empty] | P1 | Small | As KeyCloak is implemented for Admin it should be implemented for all Modules
139 | Registration Client | Document Capture - Send Doc code in ID Object ISO Doc name | 0.9.5 - Additional | As MOSIP registration client, I should be able to send the document code captured during registration as part of ID Object | MOS-28476 | Document Code should be sent in ID Object instead of Document Name | Vital | P1 | Not Started |  |  | 20 | [9 empty] | Currently Document Name is being sent which is causing issuss in Registration Processor for Document validation |  | P1 | Small | This should be a priority as it is a Bug Fix
140 | Registration Client | Holiday Validation | 0.9.5 - Additional | As MOSIP registration client, I should not allow the registration client to perform Registration on a Holiday |  | Admin should send Holiday List as Master Data. Registration Client should implement the validation (Registration should not be Development completed on a Holiday) | Vital | NA | Not Started |  | Admin | 20 | [9 empty] | Currently Holiday Validation is Happening in Registration Processor but not in Registration Client |  |  |  | Not Required
141 | Registration Client | Device Validation | 0.9.5 - Integration | As MOSIP registration client, I should be able to use only registered device for Biometric data capture and send the same details in Packet for validation in Registration Processor |  | Data capture should be Development completed only by using registered devices. Same validation should be Development completed in registration processor. | Vital | P2 | Not Started |  | Admin | 20 | [11 empty] | P2 |  | Can be taken latter
142 | Registration Client | Validations | 0.9.5 - Additional | As MOSIP registration client, I should be able to perform the same validation which are Development completed in registration processor before generating a Packet |  | Packet Validation in Registration Client should be same as Packet Validation in Registration Processor | Vital | P3 | Not Started |  | Registration Processor | 20 | [9 empty] | This req. is needed as packet validation should not fail in registration processor. |  | P3 |  | Can be analyzed latter
143 | Registration Client | First User Registration | 0.9.5 - Integration | As MOSIP registration client, I should be able to register the first user in MOSIP ecosystem |  | First User registration in MOSIP ecosystem - Default Operator - Special Provision using Admin where On-Boarding is not requiered | Vital | P2 | Not Started | [12 empty] | To be determined the procedure for this. |  | P2
144 | Registration Client | Open JDK Integration | 0.9.5 - Integration | Open JDK Integration |  |  | Vital? | P2 | Not Started |  |  | 200 | [9 empty] | Open JDK is not contians all modules. Need to do the R&D. |  | P2
145 | Registration Client | Quality Threshold Validation to be provided by SDK | 0.9.5 - Integration | Quality Threshold Validation to be provided by SDK |  |  | Vital? | P2 | Not Started |  | Sync Byte - SDK | 30 | [11 empty] | P2 |  | Duplicate of 137
146 | Registration Client | Documentation | 0.9.5 - Documentation | Documentation for Real Biometrics Release |  | Covers documentation for all features released as part of Real biometrics release 1. Documentation for Capturing Biomertics (MOS-1205) 2. Documentation for Bio Threshods 3. Reg Client - Packet Visibility and Deletion | Vital | P1 | Not started |  |  | 0 | [11 empty] | P1 | Small
147 | Registration Processor | Bio-dedupe for Parent/Guardian instead of Auth | Additional | Implementing Bio-Dedupe for Parent or Guardian Authentication | MOS-22034 | For Authentication of Introducer - Bio Dedupe could be used instead of IDA because Child registration would fail if Officer captures wrong UIN/RID of Introducer or Introducer UIN generation has failed. | Desirable |  | Requirement Pending
148 | Registration Processor | Token to authenticate Operator during packet creation | Additional | Implementing Officer Supervisor Token for Officer Supervisor Validation | MOS-22032 | A Token can be used to Authenticate Officer and Supervisor in Registration Processor when they use OTP or Password based authentication in Reg Client when they create a Packet. | Desirable |  | Requirement Pending
149 | Registration Processor | On-Hold scenarios implementation | Additional | Implementing On-Hold Scenarios for Registration Processor | MOS-22030 | If a packet validation fails then instead of rejecting the packet registration processor should flag the packet and process it. Just before UIN allocation - these flaged packets should be verified by a manual intervention and UIN should get allocated based on the verifier's decision. | Desirable |  | Requirement Pending | [12 empty] | OK - Community contribution
150 | Registration Processor | GoM requirement - Update Request from External System: Combine Two Packets and Create a Third Packet - Perform Check Sum Validation | Additional | As Registration Processor, I should be able to Combine Two Packets and Create a Third Packet and I should be able to Perform Check Sum Validation on the Merged Packet using Two Other Packets (CNIE) | MOS-21755 | Reg Proc should be able to Merge two Packets and create a third packet. After merging the packet, reg proc should calculate the check of the merged packet using the check sum of the initial packets. | Vital |  | Requirement Pending |  |  | 110 | [9 empty] | Task Breakdown 1. Security 2. Logging & Auditing 3. Dummy system to generate external packet, encryption & description 4. Validation of external packet 5. Virous scan and upload of packet in HDFS 6. Merging of external packet and create new merged packet 7. Check sum validation of merged packet 8. Validate and Store merged packet in HDFS 9. Interface to get merged packets from all stages Need More Clarity On 1. Data to be Considered as part of External Packet 2. Clarity on failure scenerio, when to fetch external packet, scenerio for update, activate-deactivate
151 | Registration Processor | SDK Integration - Minutiae extraction | Additional | Tech Story - Integrating with Actual SDK for Minutiae Extraction (De-Scoped) | MOS-17805 | Reg proc should be able to intergate with an actual device to extract minutiae of a Fingerprint Image File | Desirable |  |  |  |  | 2 | [9 empty] | Descoped
152 | Registration Processor | SDK Integration - Biometric quality score | 0.9.5 - Integration | Tech Story - Integrating with Actual SDK for Quality Check | MOS-17610 | Reg Proc should be able to integrate with an actual device to get the quality score of a biometric image file. | Vital | P2 | Not Started |  | SyncByte - SDK | 2 | [9 empty] | Registration Processor should integrate with the Same SDK used by Registration Client for getting a quality score. |  | P2 |  | Using SDK as Reg Client
153 | Registration Processor | Implement Finger Print Quality Checks to categorize FP as Real Finger, Finger of Same Person | Additional | Implement Finger Print Quality Checks to categorize FP as Real Finger, Finger of Same Person | MOS-8460 | Reg Proc should be able to integrate with SDKs that perform validations to check if captured biometrics is of a Real Finger and Finger of the Same person | Desirable |  |  |  |  | 40 | [9 empty] | Need More Clarity 1. Does sdk provide this functionality? 2. No dependent story in ID repo, Reg. Client as same validatio need to be Development completed in client 3. Need more clarity on SDK. 4. Reestimated once get more details on SDK
154 | Registration Processor | SDK Integration - Photo/Age/Gender validation | Additional | Implementing Automated Age/Gender/Photo Validation | MOS-1082 | Reg Proc should be able to integrate with a SDK to perform Photo/Age/Gender validations | Desirable | [14 empty] | SI customization
155 | Registration Processor | Implementing ABIS - One ABIS, multiple-modalities | 0.9.5 - Integration | Implementing ABIS - One ABIS, multiple-modalities | MOS-26088 | Integrating with the ABIS Vendor who Supports Multiple Modalities i.e. Face, Finger and Iris | Vital | P1 | Development Completed | Sprint 14 |  | 84 | [9 empty] | Task Breakdown 1. Security 2. Logging & Auditing 3. XSD validation based on version 2 4. ISO image validation 5. Integration with ABIS vendor 6. Finalize CBEFF structure 7. Update existing code once CBEFF strcture is finalized Add On Points 1. Estimation Development completed based on assumption. The requirement is not clear. 2. Schame validation, iso image validation, design changes on insert /identify is in scope? 3. There will be changes in ID repo and Reg. Clinet which are also need to be estimated
156 | Registration Processor | Multi-partner ABIS - One ABIS per modality | Additional | Implementing Multiple ABIS for MOSIP | MOS-1097 | Reg Proc should be able to integrate with Multi-partner ABIS - One ABIS per Modality | Essential |  | Impact Analysis to be Development completed
157 | Registration Processor | Multiple ABIS with all modalities | Additional | Implementing Multiple ABIS with all modalities | MOS-26089 | Reg Proc should be able to integrate with Multiple ABIS with all modalities | Desirable |  | Impact Analysis to be Development completed
158 | Registration Processor | Auto-deactivation of UIN | Additional | As the MOSIP System, I should be able to automatically deactivate UIN as required/configured | MOS-1085 | Reg Proc should be Auto Deactivate UINs | Desirable |  | Requirement Pending | [12 empty] | SI customization
159 | Registration Processor | OCR Implementation for Doc quality check | Additional | Implement OCR Validation in ID Object for Quality Check | MOS-1081 | Reg Proc should be able to integrate with a SDK to perform OCR Validation of ID Object Fields using Documents | Desirable |  | Requirement Pending
160 | Registration Processor | Archival of rejected packet | Additional | As Registration Processor, I should archive a packet which is Marked as rejected by the Supervisor | MOS-25374 | Reg Proc should not process a Packet rejected by Supervisor, it should archive it | Desirable |  | Detailing Pending
161 | Registration Processor | Extract Bio-metric Data and Store it IDA Database for Authentication | Additional | As Registration Processor, I should be able to Extract Bio-metric Data and Store in IDA Database for Authentication | MOS-21733 | Reg Proc should be able to seed UIN/VID/ID Object and Biometric data of an individual to IDA after UIN Generation, Data Updation in ID Repo. | Essential |  | Requirement Pending
162 | Registration Processor | Date maintainance in DB for Analytics & Reporting and Audit Log Changes/Storage | Additional |  | MOS-18400 | - Data maintenance in DB for Analytics & Reporting - Reg Proc should be able to store meta data in DB for sending it for analytics - Audit Changes - Reg. Proc. should be able to make changes to Audit implementation if there are any changes to Audit Fields - Audit log storage - Reg Proc should be able to store audit logs of a Packet received from Registration Client, in Audit table - Audit data to Analytics system - Weak/Strong Mobile Identification - Reg proc should be able seed audit data to an Analytics system to identify a Weak or Strong Mobile Number | Vital |  | Requirement Pending |  |  | 0 | [9 empty] | Need more clarity - Refer Reg. Processor sheet for details
163 | Registration Processor | First user registration | 0.9.5 - Integration | As Registration Processor, I should be able to register the First User in MOSIP System | MOS-25398 | Reg Proc should be able to register the 1st User in MOSIP without any Supervisor and Officer validation | Vital | P2 | Requirement Pending |  |  | 10 | [9 empty] | OK |  | P2 |  | - Register the Default User from Backend with Role Admin - When Admin Logs into Reg Client Onboarding is not needed - Admin Registers the First user - Deactivate the Admin after 1st User registration is done Note: This is just a suggestion, the shortest possible soluntion should be implemented
164 | Registration Processor | Remove notification to Reg. Client to inform individual to re-register, when Reg. processor in any case triggers notification to individual | Additional | Non-MVP: Packet Processing Flow Change - Remove notification to Reg. Client to inform individual to re-register | MOS-26406 | Non-MVP: Packet Processing Flow Change - Remove notification to Reg. Client to inform individual to re-register, when Reg. processor in any case triggers notification to individual | Desirable |  | Detailing Pending | [12 empty] | Refernce mail from Shrikant on 26Jun - PF review feedback mail
165 | Registration Processor | Configurability to include/exclude VID Issuance for every UIN | Additional | Non-MVP: Configurability to include/exclude VID Issuance for every UIN | MOS-26743 | Country should be able to flag to include/exclude VID issuance on generation of each UIN. Currently - VID issuance for every UIN is hard coded. | Desirable |  | Requirement Pending | [12 empty] | Reference mail from Sasi/Ramesh on 02Jul - SUB: RE: UIN privacy policy
166 | Registration Processor | Display of VID in UIN Card | Additional | Include Perpetual VID in UIN Card | MOS-26758 | VID Should be displayed in UIN Card | Vital? |  | Development Completed |  |  | 0 | [9 empty] | Development Completed as Part of MOS-24108
167 | Registration Processor | Refactoring of MOSIP repository | 0.9.5 - Additional | NA | NA | Refactoring of MOSIP repository | Vital | NA | Development completed
168 | Registration Processor | ABIS Integration | 0.9.5 - Integration | Tech Story - Adding Reference URL in ABIS Identify Request | MOS-27241 | Adding Reference URL in ABIS Identify Request | Vital | P1 | Development Completed | Sprint 14 |  | 3
169 | ID Authentication | ABIS Integration | 0.9.5 - Integration | Tech Story - Integrate with ABIS 1:1 Authentication API | MOS-27242 | Integrate with ABIS 1:1 Authentication API | Vital | P2 | Not Started | Sprint 16 | Tech5 - ABIS | 12 | [9 empty] | Design, Development, UinitTesting, Manual Testing, Integration |  | P2 |  | Split into two parts - Testing and Implementation as Auth Feature (IDA)
170 | Registration Processor | UIN Card | Additional | Tech Story - Print UIN Card with Masked UIN | MOS-27274 | Print UIN Card with Masked UIN | Vital | P1 | Development Completed | NA |  | 0 | [9 empty] | Development Completed as Part of MOS-24108
171 | Registration Processor | Printing and Postal Service | 0.9.5 - Additional | Tech Story - Send RID with UIN Card to Printing and Postal Service Provider | MOS-27328 | Send RID with UIN Card to Printing and Postal Service Provider | Vital | P1 | Development Completed | Sprint 14 |  | 3
172 | Registration Processor | Termininology Update in ID Object | 0.9.5 - Additional | Tech Story - Terminology Change for CNIE/EC Number and Local Administrative Authority | MOS-27342 | Terminology Change for CNIE/EC Number and Local Administrative Authority | Vital | P1 | Development completed | Sprint 15 |  | 3
173 | Registration Processor | Packet Generator | 0.9.5 - Additional | Tech Story - Move Packet Generator to Secure Zone | MOS-27343 | Move Packet Generator to Secure Zone | Vital | P1 | Development Completed | Sprint 14 |  | 5
174 | Registration Processor | Activate/De-Activate | 0.9.5 - Additional | Remove Additional Validation for Activate and De-Activate Packets in Packet Validator Stage | MOS-27987 | Remove Additional Validation for Activate and De-Activate Packets in Packet Validator Stage | Vital | P1 | Development Completed | Sprint 14 |  | 2
175 | Registration Processor | Camel Bridge | 0.9.5 - Additional | Update Camel Route Condition for Internal Error - FALSE for sending notification for all stages | MOS-27988 | Update Camel Route Condition for Internal Error - FALSE for sending notification for all stages | Vital | P1 | Development Completed | Sprint 14 |  | 1
176 | Registration Processor | Update Flow | 0.9.5 - Additional | Validate if UIN is Active before performing any Update Operation on the UIN | MOS-27818 | Validate if UIN is Active before performing any Update Operation on the UIN | Vital | P1 | Development Completed | Sprint 14 |  | 1
177 | Registration Processor | Bug Fixes | 0.9.5 - Additional | Changes due to Integration of Real Bio-metrics Release | MOS-28227 | Changes due to Integration of Real Bio-metrics Release | Vital | P1 | Development completed | Sprint 15
178 | Registration Processor | UIN Update | 0.9.5 - Testing | Tech Story - Integration with Real Biometrics for UIN Update Flow |  | UIN Update flow needs to be tested (Unit Tested) for Biometric Update | Vital | P1 | Not started |  | Registration Client | 8 | [11 empty] | P1 | Small | Only Testing Effort should be given
179 | Registration Processor | Lost UIN | 0.9.5 - Testing | Tech Story - Integration with Real Biometrics for Lost UIN Flow |  | Lost UIN flow needs to be tested (Unit Tested) with Actual Biometrics | Vital | P1 | Not started |  | Registration Client | 8 | [11 empty] | P1 | Small | Only Testing Effort should be given
180 | Registration Processor | ABIS Integration | 0.9.5 - Integration | As the MOSIP registration processor, when I find a potential duplicate during demo-deduplication, I should be able to send the duplicates to ABIS to perform Biometric match using gallery |  | ABIS doesn't support Biometrics Match against Gallery | Vital | P1 | Not started |  | Tech5 - ABIS | 5 | [11 empty] | P1 | Large | Test with Mantra & Tech5 Put a Flag for Demo Dedupe Feature as On or Off based on ABIS support
181 | Registration Processor | Authentication API | 0.9.5 - Testing | As the MOSIP System, I should be able to intergate with IDA Internal API for Biometric Authentication for Officer, Supervisor and Introducer |  | Officer, Supervisor and Introducer Biometric Validation using IDA API | Vital | P1 | Not started |  | IDA | 5 | [11 empty] | P1 | Small | Only Testing Effort should be given
182 | Registration Processor | ABIS Integration | 0.9.5 - Integration | Tech Story - Change in ABIS API Spec to receive Match or Not Match instead of receiving scores |  | Change in ABIS API Spec to receive Match or Not Match instead of receiving scores | Vital | P3 | Not started |  | Tech5 - ABIS | 10 | [11 empty] | P3 |  | Design for this can be P1 and Implementation can be P2/P3
183 | Registration Processor | Manual Verification - UI | 0.9.5 - Integration | As the MOSIP System, I should have Manual Verification - UI to perform Manual Verification for ABISs that don't have a UI |  | Most of the ABIS vendors don't have UI for Manual Verification. There should be a reference impl. for MV UI in MOSIP | Vital | P2 | Not started |  |  | 20 | [11 empty] | P2 |  | Yes we need it but as part of P2
184 | Registration Processor | Device Validation | 0.9.5 - Integration | As the MOSIP System, I should be able to perform device validation using which a packet was created | MOS-27829 | Validate if the Devices were registered and active when the packet was created | Vital | P2 | Not started |  | Registration Client | 5 | [11 empty] | P2 |  | Move to RC1
185 | Registration Processor | Location Hierarchy Update as per GoM | Additional | As the MOSIP Registration Processor, I should support the new Location Hierarchy |  | Reflect the new location hierarchy for Morocco | Vital | P1 | Not started |  |  | 5
186 | Registration Processor | Validations | 0.9.5 - Additional | As MOSIP registration processor, I should be able to perform the same validation which are Development completed in registration client |  | Packet Validation in Registration Processor should be same as Packet Validation in Registration Client | Vital | P2 | Not started |  |  | 5 | [11 empty] | P2
187 | Registration Processor | Version Compatibility | 0.9.5 - Additional | As MOSIP registration processor, I should be able to processor packets created with Multiple Versions of registration client |  | Version Compatibilty in Registration Processor | Vital | P3 | Not started |  |  | 20 | [11 empty] | P3 |  | Move to RC2 Good to have for Pilot Release
188 | Registration Processor | KeyCloak Integration | 0.9.5 - Additional | As MOSIP registration processor, I should be able to intergate with KeyCloak for API Authentication |  | Integration with KeyCloak for User as well as API Authentication | Vital | P1 | Not started |  |  | 15 | [11 empty] | P1 | Small | As KeyCloak is implemented for Admin it should be implemented for all Modules
189 | Registration Processor | Documentation | 0.9.5 - Documentation | Documentation for Real Biometrics Release |  | Covers documentation for all features released as part of Real biometrics release | Vital | P1 | Not started |  |  | 7 | [11 empty] | P1 | Small
190 | ID-Authentication | Analytics Module Feature - UINs for Auth Failure | Additional | As the MOSIP System, I should be able to provide hashed UINs for repeated auth failures to analytics system | MOS-25615 - Accommodated | To provide Analytics module the hashed UINs of successive authentication failures. MOSIP should be enabled to provide hashed UINs | Vital | P2 | Detailing Pending |  |  | 0 | [9 empty] | Analytics Module Not Available
191 | ID-Authentication | Audit Enhancement | 0.9.5 - Additional | Error Description should be logged in Audit logs in case of system exceptions | MOS-23840 | To enhance auditing to include error code for each audit event * Get username from Auth Adapter and assign to entity name * Get system exception message and assign to description * Don't include user errors to audit description. | Vital | P1 | Development In-Progress |  |  | 6 | [11 empty] | P1 | Small | Bug Fix
192 | ID-Authentication | Biometric Authentication - Best Finger Detection | Additional | [non-MVP]As the MOSIP system, I should be able to detect the Best Finger of a Individual during Authentication | MOS-1120 | Best Finger for Authentication to be implemented for IDA. The quality of fingerprints may wear out with time. BFD during authentication will help in identifying Best Finger after registartion | Desirable | NA | NA |  |  | 12 | [9 empty] | Addressed as part of analytics
193 | ID-Authentication | Biometric Authentication - Fingerprint Image based Authentication | Additional | As the MOSIP system, I should be able to support Fingerprint authentication by using Fingerprint Image | MOS-12165 | In addition to the Fingrprint Minutiae based authentication already implemented, Fingerprint Image based authentication has to be implemented | Vital | P1 | Development completed |  |  | 12
194 | ID-Authentication | Biometric Authentication - Integration with devices and SDK | 0.9.5 - Integration | SDK Analysis | MOS-27361 | SDK Analysis | Vital | P0 | Development completed | Sprint 14 |  | 15
195 | ID-Authentication | Biometric Authentication - Integration with devices and SDK | 0.9.5 - Integration | Tech Task: Analyze Biometric SDK | MOS26646 | Tech Task: Analyze Biometric SDK | Vital | P0 | Development completed | Sprint 14 |  | 8
196 | ID-Authentication | Internal Auth - Officer Auth | 0.9.5 - Integration | Devices - Tech Story: Internal API to add FIR - Fingerprint Image Record | MOS-22416 | To integrate with devices and SDK for biometric authentication requests from Registration Client and Registration Supervisor * Enable FIR for internal Auth Types and Check authentication * Send real fingerprint data in Internal Auth Request test. | Vital | P1 | Not started |  |  | 6 | [9 empty] | Tech Story - Testing Effort needed |  | P1 | Medium | Changes related to Internal Auth API
197 | ID-Authentication | Device Validation | 0.9.5 - Integration | Admin Related Requirements for Biometric devices from the perspective of IDA | MOS-21758 | To integrate with PM/Admin for Device Related Requirements like Device Registration and Device Provider Registration | Vital | P2 | Not started |  | Admin | 20 | [9 empty] | Note: Admin high priority Note: Need discussion about estimation breakdown |  | P2 |  | Can be taken latter
198 | ID-Authentication | MDS Integration | 0.9.5 - Integration | There will be one MOSIP Device Service spec, which will be one unified service spec for registration and authentication devices: | MOS-18214 | To integrate with MDS for receiving valid biometric attributes in input in Auth API | Vital | NA | Not started |  | MDS | 20 | [9 empty] | Requires Discussion on Test Authentication Client <07 16> Updated the description Note: Need discussion about estimation breakdown |  | NA |  | Not Req. was already build as part of demo
199 | ID-Authentication | Face Authentication | 0.9.5 - Integration | Tech Story: As the MOSIP System, I should be able to integrate with Face SDK and generate match score | MOS-12073 | FID based Authentication | Vital | P1 | Not started |  | Tech5 - SDK SyncByte | 14 | [9 empty] | Tech5/SyncByte Dependencies/Fixes should be available and the same should be tested. |  | P1 | Medium
200 | ID-Authentication | Finger Print Authentication | 0.9.5 - Integration | Tech Story: As the MOSIP System, I should be able to integrate with Fingerprint scanner and generate match score | MOS-12072 | Fixes from Vendor: 1. Change in composite match score logic (Iris and FingerPrint). 2. Validating fingerprint data whether it’s up to ISO standards or not. 3. When image without face is provided, negative value is returned but expected is BiometricException. 4. Encryption in biometrics. | Vital | P1 | Not started |  | Tech5 - SDK | 28 | [9 empty] | Tech5 Dependencies/Fixes should be available and the same should be tested. |  | P1 | Medium
201 | ID-Authentication | Composite Match Score | 0.9.5 - Integration | Tech Story: As the MOSIP System, I should be able to integrate with SDK to provide the composite match score for two finger/IRIS authentication | MOS-10831 | Fixes from Vendor: 1. Change in composite match score logic (Iris and FingerPrint). 2. Validating fingerprint data whether it’s up to ISO standards or not. 3. When image without face is provided, negative value is returned but expected is BiometricException. 4. Encryption in biometrics. | Vital | P1 | Not started |  | Tech5 - SDK | 28 | [9 empty] | Tech5 Dependencies/Fixes should be available and the same should be tested. |  | P1 | Small
202 | ID-Authentication | Iris Authentication | 0.9.5 - Integration | Tech Story: As the MOSIP System, I should be able to integrate with IRIS scanner and generate match score | MOS-10308 | IIR based Authentication | Vital | P1 | Not started |  | Tech5 - SDK | 14 | [9 empty] | Tech5/SyncByte Dependencies/Fixes should be available and the same should be tested. |  | P1 | Medium
203 | ID-Authentication |  | Additional | Tech Story: As the MOSIP System, I should be able to integrate and deliver all the dependent services for Biometric Authentication | MOS-1150 | Master story for Biometric implementation to be implemented once the devices and SDK are available | Vital | P0 | NA |  |  | 6
204 | ID-Authentication | Biometric Authentication - Redesign biometric authentication independent of biometric type/provider | Additional | Update Biometric Authentication design independent of the biometric provider/Type | MOS-20783 | Need more clarity to understand the requirement - MOSIP should identify biometric type and pass on the CBEFF from auth client to SDK - Agnostic of biometric type | Essential |  |  | NA |  | 6
205 | ID-Authentication | Biometric Authentication - send signed biometrics to Reg Client | Additional | As the MOSIP system, I should be able to authenticate an Individual's biometrics received from Reg. Client and if successful, send back signed biometrics | MOS-22937 | Need additional details on the 'Signed Biometrics' to understand the requirement | Desirable |  |  |  |  | 10 | [9 empty] | As a policy, MOSIP should not send out biometrics - Refer discussion with Vivek
206 | ID-Authentication | Biometric Authentication - Notify Individual to Update Biometrics due to poor quality | Additional | As the MOSIP system, I should be able to to intimate a resident to update their biometrics if quality of the biometrics is below threshold | MOS-13190 | After successive failure in authentication due to quality issue, individual to be intimated to update biometrics | Desirable |  |  |  |  | 5 | [9 empty] | Addressed as part of analytics
207 | ID-Authentication | Demographic Authentication - Morocco Address mapping | Additional | Mapping of platform address attributes in IDA based on Morrocco Address Structure | MOS-21585 | To support Morrocco specific address attributes for Demo authentication based on full address and address line items | Vital | P2 | Requirement Pending |  | GoM | 6 | [9 empty] | Note: Need discussion about estimation breakdown | P2 - To be decided in the next sprint based on the location hierarchy decision from other modules
208 | ID-Authentication | Demographic Authentication - Phonetics and Partial Match | Additional | As the MOSIP system, I should be able to support phonetics/partial match for Demo Authentication | MOS-12166 | In the demo authentication implementation, in addition to the exact match, partial and phonetics based match has to be implemented | Desirable |  | Requirement Pending |  |  | 5
209 | ID-Authentication | KYC Service - Morocco HoH API | Additional | As the MOSIP system, I should be able to support return additional eKYC data to social protection system | MOS-13161 | To support for an additional eKYC api for Morrocco, to retrieve data of a family/child on consent to the head of family | Desirable |  | Requirement Pending |  |  | 6 | [9 empty] | This should be handled as part of Consent provided during Registration and as part of Reg. Proc. during integration
210 | ID-Authentication | Multi-factor Authentication | 0.9.5 - Integration | As the MOSIP system, I should be able to authenticate a Individual using multi-factor authentication during authentication process | MOS-1124 | Fixes from Vendor: 1. Change in composite match score logic (Iris and FingerPrint). 2. Validating fingerprint data whether it’s up to ISO standards or not. 3. When image without face is provided, negative value is returned but expected is BiometricException. 4. Encryption in biometrics. | Vital | NA | Not Started |  | Tech5 - SDK | 6 | [9 empty] | P0 - high priority, once dep is met, need to take it up asap |  | NA |  | Duplicate for 201
211 | ID-Authentication | OTP Authentication - Integrate with Kernel for OTP Validator fix | Additional | As the MOSIP system - IDA, I should be able to integrate once correct format of OTP Validator errors is implemented | MOS-24077 | Integrate with corrected format of error codes and messages of kernel OTP validator | Vital | P2 | Not started |  | Kernel | 6 | [9 empty] | Kernel Dependencies/Fixes should be available and the same should be tested.
212 | ID-Authentication | Security - Partners Authentication and Authorization - Integration with Kernel for Digital Signature | 0.9.5 - Additional | Integrate with the certificate based Digital Signature from Kernel | MOS-23836 | Integrate with kernel Digital Signature service once Digital Signature is generated using Digital Certificate | Vital | P2 | Not started |  | Kernel | 8 | [9 empty] | P2. Dependency task to be added based on Ramesh mail on PM pending tasks |  | P2
213 | ID-Authentication | Partners Authentication and Authorization - Integration with PM | Additional | As the MOSIP System(IDA), I should be able to integrate with PM for retrieving Public Key of partners | MOS-24115 | Integrate with PM to retrive partner public keys to encrpt eKYC request | Vital? | P2 | Requierment Pending |  | Partner Management | [10 empty] | Note: Need discussion about estimation breakdown
214 | ID-Authentication | Partners Authentication and Authorization - Integration with PM | Additional | As the MOSIP system, I should be able to integrate with PM for PartnerID Validation | MOS-13157 | To integrate with PM to validate Partner ID in the auth/eKYC request and retrive the policy corresponding to a partnerID and partner key | Vital? | P2 | Requierment Pending |  | Partner Management | [10 empty] | Note: Need discussion about estimation breakdown
215 | ID-Authentication | Partners Authentication and Authorization - Integration with PM | Additional | As the MOSIP system, I should be able to integrate with PM for MISP License Key Validation | MOS-13156 | To integrate with PM to validate MISP License Key | Vital? | P2 | Requierment Pending |  | Partner Management | [10 empty] | Note: Need discussion about estimation breakdown
216 | ID-Authentication | Partners Authentication and Authorization - Integration with PM | Additional | As the MOSIP System(IDA), I should be able to integrate with PM for Certificate Validation | MOS-1099 | Integrate with PM services, to validate the partner's Digital certificate used in signing auth/eKYC request | Vital? | P2 | Requierment Pending |  | Partner Management | [10 empty] | Note: Need discussion about estimation breakdown
217 | ID-Authentication | Resident Services Feature - Auth Transaction History | 0.9.5 - Additional | As the MOSIP System, I should be able to provide Authentication Transaction History for a UIN or VID_Part 1 | MOS-24680 | To provide authentication history for an individual for all associated id types - UIN and VID | Vital | P1 | Development completed | Sprint 13 |  | 8 | [9 empty] | Estimates are based on data model change and includes testing. Revised from 16 to 24. This includes: 1. SALT generator job for hashing and encrypting UIN
218 | ID-Authentication | Resident Services Feature - Auth Transaction History | 0.9.5 - Additional | As the MOSIP System, I should be able to provide Authentication Transaction History for a UIN or VID_Part 2 | MOS-27360 | To provide authentication history for an individual for all associated id types - UIN and VID | Vital | P1 | Development completed | Sprint 14 |  | 16 | [9 empty] | Estimates are based on data model change and includes testing. Revised from 16 to 24. This includes: 1. SALT generator job for hashing and encrypting UIN
219 | ID-Authentication | Security - Integration with kernel Cryptomanager fix (To accommodate key index based encryption/decryption) | 0.9.5 - Additional | Integrate with the fix- Key expiry error in CryptoManager | MOS-23741 | - IDA receives Key index in input, which is to be used to decrypt the auth request, by calling Kernel Cryptomanager Current implementation of Cryptomanager doesn't support it. - Also when the associated public keys are expired, IDA needs to inform partner with the relevant error message | Vital | P2 | Not started |  | Kernel | 10 | [9 empty] | Kernel Dependencies/Fixes should be available and the same should be tested. |  | P2
220 | ID-Authentication | Technical - Docker Signing | Additional | Tech Story - Docker Signing | MOS-17514 | Verify once Dockers are signed | Vital | P3 | Not started |  | Core Team | [10 empty] | Core team to implement
221 | ID-Authentication | Technical - Integrate with upgraded CBEFF | Additional | Tech Story: Integrate with CBEFF XSD 2.0 | MOS-24840 | When CBEFF XSD is upgraded to 2.0, IDA to integrate with upgraded CBEFF | Vital | P1 | Development completed | Sprint 14 |  | 10
222 | ID-Authentication | Technical - Integration with Kernel on removal of 500 http status | Additional | Verify Kernel API integration for 500 http status | MOS-24598 | When 500 http status is removed from kernel apis, IDA needs to verify if the integration to all kernel services are working as expected | Vital | P2 | Not started |  |  | 6 | [9 empty] | Kernel
223 | ID-Authentication | Technical - Synchronise IDA DB, Secured UIN storage | Additional | Design Change of IDA based on Security review by Sasi/Ramesh | MOS-21584 | Sychronise ID Repo DB with IDA DB, UIN should be securedly stored in IDA | Essential |  | Requierment Pending
224 | ID-Authentication | Technical - Synchronise IDA DB, Secured UIN storage | Additional | Ability to Synchronize changes from Registration DB: As MOSIP system, I should be able to synchronize data changes from Registration DB to auth server | MOS-1141 | Sychronize ID Repo DB with IDA DB, UIN should be securedly stored in IDA | Essential |  | Requierment Pending
225 | ID-Authentication | Technical - Synchronise IDA DB, Secured UIN storage | Additional | As the MOSIP System, I should be able to synchronize Identity data from ID Repo DB to Authentication DB | MOS-25377 | To sync ID Repo DB data to IDA DB | Essential |  | Requierment Pending
226 | ID-Authentication | VID Service | 0.9.5 - Additional | As the MOSIP system, I should be able to maintain lock/unlock auth policy for an UIN | MOS-24732 | To maintain auth-type lock/unlock policy in ID Repo based on the request from Resident Services. The policy is to be validated before any authentication request is processed | Essential | P1 | Development completed | Sprint 14 | [11 empty] | DB changes, Policy to be creaated, create and update API to be created
227 | ID-Authentication | VID Service | 0.9.5 - Additional | As IDA, I should be able to Send all the Auth Type and Status to Resident Services | MOS-26742 | Retrieve status of Auth Types for Individual | Essential | P2 | Development completed | Sprint 14
228 | ID-Authentication | VID Service | 0.9.5 - Additional | Tech Story - Validate if Auth Type is Unlocked Before Performing Authentication | MOS-26641 | Authenticate an Individual based on input Authentication Type only when it is unlocked for an Individual | Essential | P1 | Development In-Progress | Sprint 15
229 | ID-Authentication | Internal Auth | Additional | As IDA, I should be able to Provide an OTP to Resident Services when Requested for a UIN/VID | MOS-26647 | To enable Individual request for an OTP via Resident Services | Vital | P1 | Development completed | Sprint 13 |  | 8
230 | ID-Authentication | Internal Auth | Additional | Tech Story - Implement OTP Authentication as part of Internal Authentication API | MOS-26649 | To enable authenticate an Individual via Resident Services | Vital | P1 | Development completed | Sprint 13 |  | 6
231 | ID-Authentication | VID Policy | 0.9.5 - Additional | Admin Related configuration for VID policy | MOS-27272 | To set up the recommended VID policy for a country 1. VID should be enabled and all the services should be verified. 2. UIN should be disabled and all the services shoul dbe verified | Vital | P2 | Development In-Progress | Sprint 14/15 |  | 4 | [9 empty] | Note: Need discussion on the breakdown |  | P2
232 | ID-Authentication | Partner Management | Additional | Internal API by IDA to validate Partner ID/API key and retrieve policy | MOS-27758 | To set up a policy in IDA to validate Partner ID/API key and retrieve policy which will ultimately be part of Partner Management | Vital |  | Not started | Sprint 15 | [11 empty] | Note: Need discussion about estimation breakdown
233 | ID-Authentication | Partner Management | Additional | Temporary Auth policy creation by IDA | MOS-27759 | To set up a policy in IDA which will ultimately part of Partner Management | Vital |  | Not started | Sprint 15 | [11 empty] | Note: Need discussion about estimation breakdown
234 | ID-Authentication | Authentication | 0.9.5 - Additional | Remove FMR based Authentication from Auth APIs | MOS-27996 | Remove FMR based Authentication from Auth APIs * Remove FMR code an unit tests. * Verify Internal/Externall/KYC Authentications | Vital | NA | Not started | Sprint 15 |  | 4 | [11 empty] | NA |  | No Need to remove
235 | ID-Authentication | SDK Integration | 0.9.5 - Integration | Integrate biometrics SDK in IDA Docker service |  | 1. License in biometrics -> Dependency from Vendor 2. Loading SDK and dependencies | Vital | P2 | Not started |  | Tech5 - SDK | 6 | [9 empty] | License in biometrics has been provided by the Vendor. Working with DevOps on loading SDK dependencies in Docker Container. |  | P2 |  | Can be taken latter
236 | ID-Authentication | UI for Authentication | 0.9.5 - Integration | Reference UI for Testing Authentication |  | Capturing biometrics and Authentication using a Application * Add multiple fingerprint matching option * Add Iris single and multiple authentication option * Add Face authentication options | Vital | P1 | Not started |  |  | 6 | [11 empty] | P1 | Medium
237 | ID-Authentication | KeyCloak Integration | 0.9.5 - Additional | As MOSIP IDA, I should be able to intergate with KeyCloak for API Authentication |  | Integration with KeyCloak for User as well as API Authentication | Vital | P1 | Not started |  | Kernel | 8 | [9 empty] | Need to understand what is the change made and how it will affect IDA. |  | P1 | Small
238 | ID-Authentication | Documentation | 0.9.5 - Documentation | Documentation for Real Biometrics Release |  | Covers documentation for all features released as part of Real biometrics release | Vital | P1 | Not started |  |  | 30 | [9 empty] | Note: Need discussion about estimation breakdown |  | P1 | Small
239 | ID-Repository | Audit Enhancement | 0.9.5 - Additional | Error Description should be logged in Audit logs in case of system exceptions | MOS-26745 | Error Description should be logged in Audit logs in case of system exceptions * Get username from Auth Adapter and assign to entity name * Get system exception message and assign to description * Don't include user errors to audit description. | Vital | P1 | Development In-Progress | Sprint 14/15 |  | 6 | [11 empty] | P1 | Small | Bug Fix
240 | ID-Repository | VID Service | 0.9.5 - Additional | As the MOSIP system, I should be able to re-activate all the VIDs associated to an UIN based on the policy | MOS-24761 | To re-activate all VIDs associated to a reactivated UIN. This UIN is reactivating a deactivated UIN | Vital | P1 | Development completed | Sprint 13/14 |  | 12
241 | ID-Repository | VID Service | 0.9.5 - Additional | As the MOSIP system, I should be able to de-activate all the VIDs associated to an UIN | MOS-24760 | To de-activate all VIDs associated to a deactivated UIN | Vital | P1 | Development completed | Sprint 13 |  | 12
242 | ID-Repository | Identity Service Enhancement | Additional | Retrieve RID for input UIN | MOS-26747 | To retrieve RID for a given UIN | Desirable |  | NA | NA |  | 3 | [9 empty] | Descoped (Reg. Processor)
243 | ID-Repository | Technical - Integrate with upgraded CBEFF | 0.9.5 - Additional | Integrate with CBEFF XSD 2.0 | MOS-26748 | When CBEFF XSD is upgraded to 2.0, IDRepo to integrate with upgraded CBEFF | Vital | P1 | Development completed | Sprint 14 |  | 10
244 | ID-Repository | ID Object Schema and ID Object Validator | 0.9.5 - Additional | Tech Story - Remove Dependency on Attributes – CNIE and LocalAdministrativeAuthority from ID Object | MOS-27303 | Remove GoM specific terminologies from ID Object. | Vital | P1 | Development completed | Sprint 14 |  | 6 | [9 empty] | Required for all Modules
245 | ID-Repository | Re-Activate and De-Activate UIN API Changes for Admin Module | Additional | Re-Activate and De-Activate UIN API Changes | MOS-27942 | Re-Activate and De-Activate UIN API Changes | Vital |  | Not started | Sprint 15
246 | ID-Repository | Update Flow | 0.9.5 - Testing | As ID Repository, I should be able to Update the biometrics of the resident when a Update request comes from registration processor |  | Biometric data update in ID Repository Unit Testing to be Development completed - Testing | Vital | P1 | Not started |  |  | 6 | [9 empty] | Note: Need discussion about estimation breakdown |  | P1 | Small
247 | ID-Repository | Lost UIN | 0.9.5 - Testing | As ID Repository, I should be able to link the registration id with the UIN after Lost UIN is found |  | Lost UIN integration Unit Testing to be Development completed - Testing | Vital | P1 | Not started |  |  | 8 | [9 empty] | Note: Need discussion about estimation breakdown |  | P1 | Small | Only Testing Effort should be given
248 | ID-Repository | First User Registration | 0.9.5 - Integration | As MOSIP ID Repository, I should be able to register the first user in MOSIP ecosystem |  | First User registration in MOSIP ecosystem | Vital | P2 | Not started |  |  | 6 | [9 empty] | Note: Need discussion about estimation breakdown |  | P2 |  | Can be taken latter
249 | ID-Repository | KeyCloak Integration | 0.9.5 - Additional | As MOSIP registration processor, I should be able to intergate with KeyCloak for API Authentication |  | Integration with KeyCloak for User as well as API Authentication | Vital | P1 | Not started |  | Kernel | 8 | [9 empty] | Note: Need discussion about estimation breakdown |  | P1 | Small | Only Testing Effort should be given
250 | ID-Repository | Document Capture | 0.9.5 - Additional | Document Code should come as part of ID Object same should be stored in ID Repository (internalization) |  | Document Code should come as part of ID Object same should be stored in ID Repository (internalization) | Vital | P1 | Not started |  |  | 8 | [9 empty] | Note: Need discussion about estimation breakdown |  | P1 | Small | Bug Fix
251 | ID-Repository | Location Hierarchy Update as per GoM | Additional | As the MOSIP ID Repository, I should support the new Location Hierarchy |  | Reflect the new location hierarchy for Morocco | Vital |  | Not started |  | GoM | 6 | [9 empty] | Note: Need discussion about estimation breakdown
252 | ID-Repository | Documentation | 0.9.5 - Documentation | Documentation for Real Biometrics Release |  | Covers documentation for all features released as part of Real biometrics release | Vital | P1 | Not started |  |  | 20 | [9 empty] | Note: Need discussion about estimation breakdown |  | P1 | Small
253 | Kernel | SMS/EmailNotification | Additional | Non-MVP: SMS/Email Notification - Add interface for Delivery Reports | MOS-23810 | Adding an interface to support capturing of delivery reports sent by thrid party Email/SMS Vendor | Essential | P2 | On Hold due to Bootcamp Demo
254 | Kernel | Crypto Management | 0.9.5 - Additional | Non MVP: Crypto Manager - As the MOSIP system, I should be able to decrypt using Key Index | MOS-23599 | Ability to decrypt data using Key Index instead of Timestamp in IDA | Vital | P2 | Not Started | Sprint 16 | 4 | [10 empty] | On Hold Due to MOS-27314 |  | P2
255 | Kernel | Audit Management | 0.9.5 - Additional | Non MVP: Enable data loss prevention in Audit | MOS-23263 | Tech Story - Implementing Kafka as message queue to prevent data loss during Audit Logging | Vital | P3 | Development In-Progress | Sprint 14/15 |  | 15 | [9 empty] | Architects to further discuss |  | P3
256 | Kernel | Sync Data | 0.9.5 - Additional | Non MVP: Changes in Sync data as per new location hierarchy | MOS-22655 | Change in Sync data response based on the Morocco Location Hierarcy | Vital | P3 | Requirement pending |  | GoM | 15 | [9 empty] | Architects to further discuss |  | P3 |  | Please Revisit
257 | Kernel | License Key Validation | Additional | Non MVP: As the MOSIP system, I should be able to perform License Key pattern validation against a defined License Key generation policy | MOS-22446 | Perfroming a Pattern and Length validation on License Key | Vital | P2 | NA |  |  | 4 | [9 empty] | De-scoped from Kernel. Part of Partner Management
258 | Kernel | Parter ID Validation | Additional | Non MVP: As the MOSIP system, I should be able to perform Partner ID validation against a defined Partner ID policy | MOS-22445 | Perfroming data type and Length validation on Partner ID | Vital | P2 | NA |  |  | 4 | [9 empty] | De-scoped from Kernel. Part of Partner Management
259 | Kernel | Pre-registration Dependency: Partial Search on Location | Additional | Non MVP: Partial Search on Location for Pre_reg | MOS-22038 | Adding support/query to search and fetch location data based on a partial search on pre-registration | Desirable | P2 | Requirement pending |  |  | 5 | [9 empty] | Subject to bandwidth
260 | Kernel | OTP Management | Additional | Non MVP: As the MOSIP system, I should be able have multiple OTP active for a single UIN | MOS-21931 | Ability to have multiple OTPs active for a single UIN - Inclusive of mapping each active OTP to a transaction | Desirable
261 | Kernel | Moving to hardware HSM | 0.9.5 - Additional | Moving to hardware HSM | MOS-26254 | TBD | Vital | P2 | Development In-Progress | Sprint 14/15 |  | 8 | [9 empty] | Estimates covers only the code change. Pre-Requirtes is HSM should beavilable for usage |  | P2 |  | Not Important can be Part of RC1
262 | Kernel | Technical - Integration with Kernel on removal of 500 http status | 0.9.5 - Additional | Verify Kernel API integration for 500 http status | MOS-26255 | - 500 http status to be removed from kernel apis | Vital | P2 | Not Started | Sprint 15 |  | 3 | [11 empty] | P2
263 | Kernel | (Resident Service Dependency) Password Protected PDF - | 0.9.5 - Additional | As the MOSIP System, I should be able to generate Password Protected PDF | MOS-27221 | As the MOSIP System, I should be able to generate Password Protected PDF | Vital | NA | Development completed | Sprint 14/15 |  | 12 | [11 empty] | NA
264 | Kernel | (IDA Dependency) Key Expiry Error In Crypto-Manager | 0.9.5 - Additional | As the MOSIP System, I should be able to respond with an error if a Key is expired | MOS-27307 | As the MOSIP System, I should be able to respond with an error if a Key is expired | Vital | P2 | Not Started | Sprint 15 |  | 8 | [9 empty] | On Hold due to dependency on MOS-23599 |  | P2
265 | Kernel | (IDA Dependency) Fix error messages - OTP Validator | 0.9.5 - Additional | Tech Story: Fix error messages format in OTP Validator Component | MOS-24012 | Fix error messages format in OTP Validator Component | Vital | P1 | Development In-Progress | Sprint 14/15 |  | 2 | [11 empty] | P1 | Small
266 | Kernel | Termininology Update in Location | 0.9.5 - Additional | Tech Story: Update the Masterdata for Location Hierarcy | MOS-27310 | Update the Masterdata for Location Hierarcy | Vital | P1 | Development completed | Sprint 14 |  | 1
267 | Kernel | Digital Certificate Manager | 0.9.5 - Additional | Implement Digital Certificate Manager to have Certificate based Digital Signature | MOS-27314 | Implement Digital Certificate Manager to have Certificate based Digital Signature | Vital | P1 | Development In-Progress | Sprint 14/15 | 4 | [12 empty] | P1 | Medium
268 | Kernel | Working Hours Change | 0.9.5 - Additional | Implement requirement of maintaining Working days (Pre-reg. dependency) | MOS-28244 | Implement requirement of maintaining Working days (Pre-reg. dependency) | Vital | P1 | Detailing pending | Sprint 16 | [11 empty] | Yet to be estimated as Internal Analysis Pending |  | P1 | Medium
269 | Kernel | Documentation | 0.9.5 - Documentation | Documentation for Real Biometrics Release |  | Covers documentation for all features released as part of Real biometrics release | Vital | P1 | Not started |  | 7 | [12 empty] | P1 | Small
270 | Client | Certificate pinning | Additional |  | Need clarity for estimating |  | Vital | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
271 | Client | Protection of residents document and receipts | Additional |  | Need clarity for estimating |  | Vital | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
272 | Client | No rollback | Additional |  | Need clarity for estimating |  | Vital | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
273 | Client | Lockdown the signed jars and launcher so fake jars or older jars can not be used | Additional |  | Need clarity for estimating |  | Essential | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
274 | Client | TPM for Android | Additional |  | Need clarity for estimating |  | Essential | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
275 | Client | TPM for Linux | Additional |  | Need clarity for estimating |  | Desirable | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
276 | Client | All external facing API’s will be digitally signed with domain (segregation of keys by security domain) specific keys | Additional |  | Covered as part of - MOS-23836 |  | Vital |  |  |  |  | 4 | 4 | [8 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
277 | Client | All the API’s are validated for JWT | Additional |  | Need clarity for estimating |  | Vital | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
278 | Client | JWT token based authorization for all the services. | Additional |  | Need clarity for estimating |  | Vital | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
279 | API | API registration as service so only registered API’s and services are accessible over proxy | Additional |  | Need clarity for estimating |  | Desirable | [5 empty] | Need more clarification | [8 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
280 | API | All internal API’s will need to be over two way SSL channel | Additional |  | Need clarity for estimating |  | Desirable | [5 empty] | Same as line item 19 | [8 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
281 | API | Role engineering & filtering | Additional |  | This is under progress. Every module should change the code of encryption logic using Kernel services to DTO Layer. |  | Vital |  |  |  |  | 21 | Need more clarification |  | 7 | 7 | 7 |  |  |  |  | Input from Sasi/Ramesh - Refer mail dtd 25Jun
282 | API | IAM Integration | Additional |  | We had decided to use the Keycloak and we might have to roll back this. TBD |  | Vital | [5 empty] | Same as line item 19 | [8 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
283 | API | HSM integration | Additional |  | Need clarity for estimating |  | Vital | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
284 | Server | CORS settings and optimization | Additional |  | This will have minor effect on web applications and micro services |  | Vital |  |  |  |  | 17 | 8 |  | 2 | 4 | 3 |  |  |  |  | Input from Sasi/Ramesh - Refer mail dtd 25Jun
285 | Server | CSRF Protection | Additional |  | Web applications and microservices will have impact on this. Need more clarity on this also. |  | Vital |  |  |  |  | 12 | 8 |  | 4 | [6 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
286 | Server | Server configuration to be protected for sensitive data | Additional |  | Need more clarity on this. |  | Vital | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
287 | Server | Approval flow for sensitive server configuration | Additional |  | Might not have impact in any module in the application layer |  | Vital | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
288 | Server | JWT Auth Token Renewal | Additional |  | Depends on the 3rd party IAM decision. Need clarity for estimating |  | Vital | [11 empty] | Need clarity for estimating |  |  | Input from Sasi/Ramesh - Refer mail dtd 25Jun
289 | Server | Key Management (Auto renewal, auto rotation) | Additional |  | Only Kernel will be affected |  | Vital |  |  |  |  | 0 | Already Development completed | [5 empty] | Need clarity for estimating |  |  | Input from Sasi/Ramesh - Refer mail dtd 25Jun
290 | Server | Encryption layer moved to hibernate | Additional |  | Kernel has to make changes to the DAO layer and everybody have to refer to this new version. And everybody have to stop calling Kernel services for encryption and use the declarative features in their DTOs |  | Vital |  |  |  |  | 21 |  |  | 7 | 7 | 7 |  | Need clarity for estimating |  |  | Input from Sasi/Ramesh - Refer mail dtd 25Jun
291 | Server | API throttling & DDOS protection | Additional |  | Might not have impact in any module in the application layer |  | Vital | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
292 | Server | Master data should be publish and read not CRUD | Additional |  | Need more clarity on this. |  | Vital | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
293 | Server | Domain specific otp messages | Additional |  | Need more clarity on this. |  | Vital | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
294 | Server | OCSP Stapling | Additional |  | Need more clarity on this. |  | Vital | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
295 | Server | File protection | Additional |  | Need more clarity on this. |  | Vital | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
296 | Server | Device management | Additional |  | Need more clarity on this. |  | Vital | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
297 | Server | Anti spam/anti bot solutions. | Additional |  | Need clarity for estimating |  | Vital | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
298 | Server | VID only Auth | Additional |  | Need clarity for estimating - Can we use UIN for internal auth? |  | Vital | [10 empty] | Need clarity for estimating - Can we use UIN for internal auth? |  |  |  | Input from Sasi/Ramesh - Refer mail dtd 25Jun
299 | Server | Distributed readonly Zero knowledge database | Additional |  | Need clarity for estimating |  | Vital | [10 empty] | Need clarity for estimating |  |  |  | Input from Sasi/Ramesh - Refer mail dtd 25Jun
300 | Server | Auth message replay protection | Additional |  | Need clarity for estimating |  | Vital | [10 empty] | Need clarity for estimating |  |  |  | Input from Sasi/Ramesh - Refer mail dtd 25Jun
301 | Auth Service | Auth transaction validation | Additional |  | Need clarity for estimating |  | Vital | [10 empty] | Need clarity for estimating |  |  |  | Input from Sasi/Ramesh - Refer mail dtd 25Jun
302 | Auth Service | Auth purpose validation | Additional |  | Need clarity for estimating |  | Vital | [10 empty] | Need clarity for estimating |  |  |  | Input from Sasi/Ramesh - Refer mail dtd 25Jun
303 | Auth Service | Auth registered device L1 validation | Additional |  | Need clarity for estimating |  | Essential | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
304 | Auth Service | Auth with just VID and age greater than or less than or just with VID and parts of address | Additional |  | Need clarity for estimating |  | Essential | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
305 | Auth Service | Independant Auth systems with a simple publisher to refresh data. | Additional |  |  |  | Desirable | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
306 | Auth Service | Segregation of ekyc and auth services | Additional |  |  |  | Desirable | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
307 | Auth Service | TOTP based auth | Additional |  |  |  | Desirable | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
308 | Auth Service | OCSP Stapling | Additional |  |  |  | Desirable | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
309 | Auth Service | Should follow the rules of 1:N match for recovery | Additional |  | Need clarity for estimating |  | Vital | [11 empty] | Need clarity for estimating |  |  | Input from Sasi/Ramesh - Refer mail dtd 25Jun
310 | Auth Service | Integrated Subnet and firewall segregation | Additional |  | Impact on Infrastructure-TBD |  | Vital | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
311 | Auth Service | Integrated url filtering | Additional |  | Impact on Infrastructure-TBD |  | Vital | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
312 | UIN Recovery Service | NTP integration on standard | Additional |  | Impact on Infrastructure-TBD |  | Vital | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
313 | Security Integration | A proper inbuilt certification authority | Additional |  |  |  | Essential | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
314 | Security Integration | A way to publish the approved certificates to all app | Additional |  |  |  | Essential | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
315 | Security Integration | OCSP/CRL | Additional |  |  |  | Desirable | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
316 | Security Integration | Zoning & Service segregation | Additional |  | Impact on Infrastructure-TBD |  | Vital | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
317 | Security Integration | Protection against SIM Swap | Additional |  | Need clarity for estimating |  | Vital | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
318 | Security Integration | Protection against OTP SPAM | Additional |  | Need clarity for estimating |  | Vital | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
319 | Security Integration | All residents data should be stored in encrypted form | Additional |  | Need clarity for estimating |  | Vital | [10 empty] | Already Development completed, need clarity on the requirement for estimating |  |  |  | Input from Sasi/Ramesh - Refer mail dtd 25Jun
320 | Security Integration | All sensitive configuration should be stored in encrypted form | Additional |  | Need clarity for estimating |  | Vital | [10 empty] | DB passwords are encrypted, Need clarity on the requirement for estimating |  |  |  | Input from Sasi/Ramesh - Refer mail dtd 25Jun
321 | Security Integration | Avoid enumeration of data | Additional |  | Need clarity for estimating |  | Vital | [6 empty] | Need more clarification | [7 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
322 | Data protection | Audit all changes to the data | Additional |  | Need clarity for estimating |  | Vital |  |  |  |  | 6 |  | 6 |  |  |  | Already Development completed, need clarity on the requirement for estimating |  |  |  | Input from Sasi/Ramesh - Refer mail dtd 25Jun
323 | Data protection | Publicly publishable audits | Additional |  |  |  | Essential | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
324 | Admin portal | Non repudiable with timestamp service | Additional | Non repudiable with timestamp service | Need clarity to estimate |  | Essential | [14 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
325 | Audit | Anonymised publishable data | Additional |  | Need clarity for estimating |  | Vital | P1 | [13 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
326 | Audit | Consolidation of logs from all pods for enhanced debugging | Additional |  |  | Consolidation of logs from all pods for better debugging - eg: today we have reg proc logs one each in each pod for each stage | Vital? | P2 |  |  |  | 30
327 | Admin | Integrating all modules with the KeyCloak implementation for authentication and authorization | Additional |  |  |  | Vital | P1 |  |  |  | 4
328 | Admin | TPM for Windows (initial design is not enough) | Additional |  |  |  | Vital | P1 |  |  |  | 100 | [9 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
329 | Admin | Device enrollment and validation | Additional |  | Need input from Ramesh/ Sasi, What validation required from Reg. Client? |  | Vital | P1 | [13 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
330 | Admin | Protection of local data management | Additional |  | Need clarity for estimating |  | Vital | P1 | [13 empty] | Input from Sasi/Ramesh - Refer mail dtd 25Jun
331 | Admin | Account Unlock | Additional | UI: As the MOSIP Administrator, I should be able to unlock my locked account | MOS-23691 |  | Desirable | P2 |  |  |  | 2.6 | [9 empty] | Key Cloak Feature
332 | Admin | Account Unlock | Additional | API: As the MOSIP Admin Application, I should enable functionality to unlock a locked account | MOS-23690 |  | Desirable | P2 |  |  |  | 2.6 | [9 empty] | Key Cloak Feature
333 | Admin | Approvals | Additional | UI: As the MOSIP Administrator, I should be able to approve created Centers, Machine, Devices, Users and Masterdata | MOS-24132 |  | Desirable | P2 |  |  |  | 0 | [9 empty] | Need more clarifiaction on Requirements and Design
334 | Admin | Approvals | Additional | Tech Story - API: Create an Approval Framework | MOS-23791 |  | Desirable | P2 |  |  |  | 0 | [9 empty] | Need more clarifiaction on Requirements and Design
335 | Admin | Auto Logout | Additional | UI: As the MOSIP Admin Application, I should be able to Auto-Logout a logged in user | MOS-23606 |  | Desirable | P2 |  |  |  | 5.2 | [9 empty] | Key Cloak Feature
336 | Admin | Balcklisted Word Create | Additional | UI: As the MOSIP Administrator, I should be able to create a Blacklisted Word | MOS-23667 |  | Desirable | P2 |  |  |  | 3.9
337 | Admin | Balcklisted Word Create | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to create a Blacklisted Word | MOS-23666 |  | Vital | P1 | Development completed | MOS Sprint 12 |  | 3.9
338 | Admin | Blacklisted Word Activate/Deactivate | Additional | UI: As the MOSIP Administrator, I should be able to Activate and Deactivate a Blacklisted Word | MOS-23670 |  | Desirable | P2 |  |  |  | 3.9
339 | Admin | Blacklisted Word Update | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to update a Blacklisted Word | MOS-23671 |  | Vital | P1 | Development completed | MOS Sprint 12 |  | 3.9
340 | Admin | Blacklisted Word Update | Additional | UI: As the MOSIP Administrator, I should be able to update a Blacklisted Word | MOS-23668 |  | Desirable | P2 |  |  |  | 3.9
341 | Admin | Center Activate/Deactivate | 0.9.5 - Additional | UI: As the MOSIP Administrator, I should be able to Activate/Deactivate a Registration Center | MOS-23635 |  | Vital | P1 | Development In-Progress | MOS Sprint 15 |  | 3.9 | [11 empty] | P1 | Medium
342 | Admin | Center Create | 0.9.5 - Additional | UI: As the MOSIP Administrator, I should be able to create a Registration Center | MOS-23631 |  | Vital | P1 | Development completed | MOS Sprint 13 |  | 5.2
343 | Admin | Center Create | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to create a Registration Center | MOS-23630 |  | Vital | P1 | Development completed | MOS Sprint 12 |  | 3.9
344 | Admin | Center Create | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should not allow creation of a Registration Center if data is not received in all configured languages | MOS-25629 |  | Vital | P1 | Development completed | MOS Sprint 14 |  | 3.9
345 | Admin | Device View | 0.9.5 - Additional | API: Implementation of Registration Search API | MOS-24950 |  | Vital | P1 | Development completed | MOS Sprint FIT 5 |  | 5.85
346 | Admin | Center Decommission | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to decommission a Registration Center | MOS-25261 |  | Vital | P1 | Development completed | MOS Sprint 13 |  | 5.2
347 | Admin | Center Decommission | 0.9.5 - Additional | UI: As the MOSIP Administrator, I should be able to Decommission a Registration Center | MOS-25368 |  | Vital | P1 | Development completed | MOS Sprint 13 |  | 3.9
348 | Admin | Center Detail View | 0.9.5 - Additional | UI: As the MOSIP Administrator, I should be able to view complete details of a Registration Center | MOS-23619 |  | Vital | P1 | Development completed | MOS Sprint 14 |  | 2.6
349 | Admin | Center List View | 0.9.5 - Additional | UI: As the MOSIP Administrator, I should be able to view list of Registration Centers | MOS-23617 |  | Vital | P1 | Development completed | MOS Sprint 14 |  | 2.6
350 | Admin | Center List View | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to view list of Registration Centers | MOS-23616 |  | Vital | P1 | Development completed | MOS Sprint 12 |  | 4.55
351 | Admin | Center List View Machine List View Device List View | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should be able to fetch columns to be displayed on Center/Machine/Device view page from Configurations | MOS-25638 |  | Vital | P1 | Development completed | MOS Sprint 13 |  | 2.6
352 | Admin | Center Update | 0.9.5 - Additional | UI: As the MOSIP Administrator, I should be able to Update details of a Registration Center | MOS-23633 |  | Vital | P1 | Development completed | MOS Sprint 13 |  | 2.6
353 | Admin | Center Update | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to Update details of a Registration Center | MOS-23632 |  | Vital | P1 | Development completed | MOS Sprint 12 |  | 3.9
354 | Admin | Center Update | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should not allow updation of a Registration Center if data is not received in all configured languages | MOS-25630 |  | Vital | P1 | Development completed | MOS Sprint 14 |  | 3.9
355 | Admin | Center-Device Mapping Create | Additional | UI: As the MOSIP Administrator, I should be able to map Devices to a Registration Center | MOS-23628 |  | Desirable | P2 |  |  |  | 3.9
356 | Admin | Center-Device Mapping Create | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to map/re-map a Device to a Registration Center | MOS-23627 |  | Vital | P1 | Development In-Progress | MOS Sprint 16 |  | 3.9 | [11 empty] | P1 | Small
357 | Admin | Location Filter | 0.9.5 - Additional | UI: Implement Filters on Location List View Screen | MOS-24837 |  | Vital | P1 | Development In-Progress | MOS Sprint 15 |  | 2.6 | [11 empty] | P1 | Medium
358 | Admin | Center-Device Unmap | Additional | UI: As the MOSIP Administrator, I should be able to Un-Map Devices from a Registration Center | MOS-23677 |  | Desirable | P2 |  |  |  | 3.9
359 | Admin | Center-Device Unmap | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to Un-Map a Device from a Registration Center | MOS-23676 |  | Vital | P1 | Development In-Progress | MOS Sprint 16 |  | 3.9 | [11 empty] | P1 | Small
360 | Admin | Center-Machine Mapping Create | Additional | UI: As the MOSIP Administrator, I should be able to map Machines to a Registration Center | MOS-23625 |  | Desirable | P2 |  |  |  | 3.9
361 | Admin | Center-Machine Mapping Create | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to map/re-map of a Machine to a Registration Center | MOS-23624 |  | Vital | P1 | Development In-Progress | MOS Sprint 16 |  | 3.9 | [11 empty] | P1 | Small
362 | Admin | Location Update | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to update details of a Location_Part2 | MOS-25217 |  | Vital | P1 | Development In-Progress | MOS Sprint 15 |  | 5.2 | [11 empty] | P1 | Small
363 | Admin | Locatiom List View | 0.9.5 - Additional | UI: Update columns on Location List View Screen | MOS-24836 |  | Vital | P1 | Development In-Progress | MOS Sprint 15 |  | 2.6 | [11 empty] | P1 | Medium
364 | Admin | Center-Machine Unmap | Additional | UI: As the MOSIP Administrator, I should be able to Un-Map Machines from a Registration Center | MOS-23675 |  | Desirable | P2 |  |  |  | 3.9
365 | Admin | Center-Machine Unmap | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to Un-Map a Machine from a Registration Center | MOS-23674 |  | Vital | P1 | Development In-Progress | MOS Sprint 16 |  | 3.9 | [11 empty] | P1 | Small
366 | Admin | Center-User Mapping Create | Additional | UI: As the MOSIP Administrator, I should be able to map Users to a Registration Center | MOS-23621 |  | Desirable | P2 |  |  |  | 5.2
367 | Admin | Center-User Mapping Create | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to map/re-map a User to a Registration Center | MOS-23620 |  | Vital | P1 | Development In-Progress | MOS Sprint 16 |  | 5.2 | [11 empty] | P1 | Small
368 | Admin | Holiday List View | 0.9.5 - Additional | UI: Update the Holiday List View Screen | MOS-24835 |  | Vital | P1 | Development In-Progress | MOS Sprint 15 |  | 2.6 | [11 empty] | P1 | Medium
369 | Admin | Center-User Unmap | Additional | UI: As the MOSIP Administrator, I should be able to Un-Map Users from a Registration Center | MOS-23673 |  | Desirable | P2 |  |  |  | 3.9
370 | Admin | Center-User Unmap | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to Un-Map a User from a Registration Center | MOS-23672 |  | Vital | P1 | Development In-Progress | MOS Sprint 16 |  | 5.2 | [11 empty] | P1 | Small
371 | Admin | Change Password | Additional | UI: As the MOSIP Administrator, I should be able to change my password | MOS-23611 |  | Desirable | P2 |  |  |  | 3.9 | [9 empty] | Key Cloak Feature
372 | Admin | Change Password | Additional | API: As the MOSIP Admin Application, I should enable functionality to change password | MOS-23610 |  | Desirable | P2 |  |  |  | 2.6 | [9 empty] | Key Cloak Feature
373 | Admin | Device Activate/Deactivate | Additional | UI: As the MOSIP Administrator, I should be able to Activate/Deactivate a Device | MOS-23647 |  | Desirable | P2 |  |  |  | 3.9
374 | Admin | Device Create | Additional | UI: As the MOSIP Administrator, I should be able to create a Device | MOS-23643 |  | Desirable | P2 |  |  |  | 3.9
375 | Admin | Device Create | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to create a Device | MOS-23642 |  | Vital | P1 | Development completed | MOS Sprint 12 |  | 3.9
376 | Admin | Device Decommission | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to decommission a Device | MOS-25263 |  | Vital | P1 | Development completed | MOS Sprint 13 |  | 3.9
377 | Admin | Device Decommission | Additional | UI: As the MOSIP Administrator, I should be able to Decommission a Device | MOS-25372 |  | Desirable | P2 |  |  |  | 3.9
378 | Admin | Device List View | 0.9.5 - Additional | UI: As the MOSIP Administrator, I should be able to view list of Devices | MOS-23629 |  | Vital | P1 | Development completed | MOS Sprint 13 |  | 2.6
379 | Admin | Device List View | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to view list of Devices | MOS-23626 |  | Vital | P1 | Development completed | MOS Sprint 12 |  | 3.9
380 | Admin | Device List View | Additional | UI: As the MOSIP system, I should be able to view associated Devices for a Registration Center | MOS-25373 |  | Desirable | P2 |  |  |  | 6.5
381 | Admin | Device Update | Additional | UI: As the MOSIP Administrator, I should be able to Update details of a Device | MOS-23645 |  | Desirable | P2 |  |  |  | 3.9
382 | Admin | Device Update | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to Update details of a Device | MOS-23644 |  | Vital | P1 | Development completed | MOS Sprint 12 |  | 3.9
383 | Admin | Device View | 0.9.5 - Additional | API: Implement Multi-language data validation during creation of a Center | MOS-23785 |  | Vital | P1 | Development completed | MOS Sprint 14 |  | 3.9
384 | Admin | Document Type Activate/Deactivate | Additional | UI: As the MOSIP Administrator, I should be able to Activate and Deactivate a Document type | MOS-23653 |  | Desirable | P2 |  |  |  | 2.6
385 | Admin | Document Type Create | Additional | UI: As the MOSIP Administrator, I should be able to create a Document Type | MOS-23649 |  | Desirable | P2 |  |  |  | 3.9
386 | Admin | Document Type Create | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to create a Document Type | MOS-23648 |  | Vital | P1 | Development completed | MOS Sprint 12 |  | 2.6
387 | Admin | Document Type Update | Additional | UI: As the MOSIP Administrator, I should be able to update details of a Document Type | MOS-23651 |  | Desirable | P2 |  |  |  | 3.9
388 | Admin | Document Type Update | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to update details of a Document Type | MOS-23650 |  | Vital | P1 | Development completed | MOS Sprint 12 |  | 3.9
389 | Admin | Document Type-Category Mapping Activate/Deactivate | Additional | UI: As the MOSIP Administrator, I should be able to Activate and Deactivate a mapping of a Document Type and Document Category | MOS-23659 |  | Desirable | P2 |  |  |  | 3.9
390 | Admin | Document Type-Category Mapping Create | Additional | UI: As the MOSIP Administrator, I should be able to map Document Types to a Document Category | MOS-23655 |  | Desirable | P2 |  |  |  | 3.9
391 | Admin | Document Type-Category Mapping Create | 0.9.5 - Additional | As the MOSIP Admin Application, I should enable functionality to map Document Types to a Document Category | MOS-23654 |  | Vital | P1 | Development completed | MOS Sprint 13 |  | 5.2
392 | Admin | Document Type-Category Mapping Update | Additional | UI: As the MOSIP Administrator, I should be able to update Document Types mapped to a Document Category | MOS-23657 |  | Desirable | P2 |  |  |  | 3.9
393 | Admin | Document Type-Category Mapping Update | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to update Document Types mapped to a Document Category | MOS-23656 |  | Vital | P1 | Development In-Progress | MOS Sprint 15 |  | 3.9 | [11 empty] | P1 | Small
394 | Admin | Dssign | 0.9.5 - Additional | Design for "Admin" - Sprint 12 stories | MOS-24134 |  | Vital | P1 | Development completed | MOS Sprint 13 |  | 7
395 | Admin | Edit Personal Details | Additional | UI: As the MOSIP Administrator, I should be able to edit my personal details under "Profile Management" option | MOS-23609 |  | Desirable | P2 |  |  |  | 13 | [9 empty] | Key Cloak Feature
396 | Admin | Edit Personal Details | Additional | API: As the MOSIP Admin Application, I should enable functionality to edit user details | MOS-23608 |  | Desirable | P2 |  |  |  | 6.5 | [9 empty] | Key Cloak Feature
397 | Admin | Export data (CSV) | Additional | UI: As the MOSIP Administrator, I should be able to export displayed data on a List view page to a CSV file | MOS-25370 |  | Desirable | P2 |  |  |  | 5.2
398 | Admin | Forgot Username | Additional | UI: As the MOSIP Administrator, I should be able to retrieve my Username | MOS-23685 |  | Desirable | P2 |  |  |  | 3.9 | [9 empty] | Key Cloak Feature
399 | Admin | Forgot Username | Additional | API: As the MOSIP Admin Application, I should enable functionality to retrieve Username | MOS-23684 |  | Desirable | P2 |  |  |  | 3.25
400 | Admin | Home Page | 0.9.5 - Additional | UI: As the MOSIP Administrator, I should be able to view and navigate on Admin Application Home Page | MOS-23607 |  | Vital | P1 | Development completed | MOS Sprint 13 |  | 2.6
401 | Admin | Location Data Activate/Deactivate | Additional | UI: As the MOSIP Administrator, I should be able to Activate and Deactivate a Location | MOS-23665 |  | Desirable | P2 |  |  |  | 5.2
402 | Admin | Location Data Create | Additional | UI: As the MOSIP Administrator, I should be able to create a Location | MOS-23661 |  | Desirable | P2 |  |  |  | 5.2
403 | Admin | Location Data Create | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to create a Location | MOS-23660 |  | Vital | P1 | Development completed | MOS Sprint 12 |  | 6.5
404 | Admin | Location Data Update | Additional | UI: As the MOSIP Administrator, I should be able to update details of a Location | MOS-23663 |  | Desirable | P2 |  |  |  | 5.2
405 | Admin | Location Data Update | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to update details of a Location | MOS-23662 |  | Vital | P1 | Development completed | MOS Sprint 12 |  | 5.2
406 | Admin | Login | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should fetch the security policy based on a username | MOS-23788 |  | Vital | P1 | Development completed | MOS Sprint FIT 5 |  | 3.9
407 | Admin | Login | Additional | UI: As the MOSIP Administrator, I should be able to login to the admin portal with Username and Password | MOS-23223 |  | Desirable | P2 |  |  |  | 2.6 | [9 empty] | Key Cloak Feature
408 | Admin | Login | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable login to the admin portal | MOS-23168 |  | Vital | P1 | Development completed | MOS Sprint FIT 5 |  | 2.6
409 | Admin | Login - Captcha | Additional | Implementing Captcha in Login Screen | MOS-25105 |  | Desirable | P2 |  |  |  | 3.9 | [9 empty] | We will only use KeyCloak Captcha Feature
410 | Admin | Logout | 0.9.5 - Additional | UI: Update the Blacklisted Words List View Screen | MOS-23855 |  | Vital | P1 | Development In-Progress | MOS Sprint 15 |  | 2.6 | [11 empty] | P1 | Medium
411 | Admin | Machine Activate/Deactivate | Additional | UI: As the MOSIP Administrator, I should be able to Activate/Deactivate a Machine | MOS-23641 |  | Desirable | P2 |  |  |  | 3.9
412 | Admin | Machine Activate/Deactivate | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should be able to update the number of Kiosk for a Registration Center for every deactivation of the assigned machine | MOS-25212 |  | Vital | P1 | Development In-Progress | MOS Sprint 16 |  | 3.9 | [11 empty] | P1 | Small
413 | Admin | Machine Create | Additional | UI: As the MOSIP Administrator, I should be able to create a Machine | MOS-23637 |  | Desirable | P2 |  |  |  | 3.9
414 | Admin | Machine Create | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to create a Machine | MOS-23636 |  | Vital | P1 | Development completed | MOS Sprint 12 |  | 3.9
415 | Admin | Machine Decommission | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to decommission a Machine | MOS-25262 |  | Vital | P1 | Development In-Progress | MOS Sprint 15 |  | 3.9 | [11 empty] | P1 | Small
416 | Admin | Machine Decommission | Additional | UI: As the MOSIP Administrator, I should be able to Decommission a Machine | MOS-25371 |  | Desirable | P2 |  |  |  | 3.9
417 | Admin | Machine List View | 0.9.5 - Additional | UI: As the MOSIP Administrator, I should be able to view list of any Masterdata Type | MOS-23623 |  | Vital | NA | Development completed | MOS Sprint 14 |  | 2.6 | [11 empty] | NA
418 | Admin | Machine List View | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to view list of Machines | MOS-23622 |  | Vital | P1 | Development completed | MOS Sprint 12 |  | 3.9
419 | Admin | Machine List View | Additional | UI: As the MOSIP system, I should be able to view associated Machines for a Registration Center | MOS-25369 |  | Desirable | P2 |  |  |  | 6.5
420 | Admin | Machine Update | Additional | UI: As the MOSIP Administrator, I should be able to Update details of a Machine | MOS-23639 |  | Desirable | P2 |  |  |  | 3.9
421 | Admin | Machine Update | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to Update details of a Machine | MOS-23638 |  | Vital | P1 | Development completed | MOS Sprint 12 |  | 2.6
422 | Admin | Machine View | 0.9.5 - Additional | UI: As the MOSIP Administrator, I should be able to view complete details of a Machine | MOS-23784 |  | Vital | P1 | Development completed | MOS Sprint 13 |  | 4.55
423 | Admin | Masterdata View | 0.9.5 - Additional | UI: As the MOSIP Administrator, I should be able to view list of Masterdata Types | MOS-23896 |  | Vital | P1 | Development completed | MOS Sprint 13 |  | 3.9
424 | Admin | Masterdata View | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should be able to fetch list of Masterdata Types in all the languages | MOS-23787 |  | Vital | P1 | Development completed | MOS Sprint FIT 5 |  | 3.9
425 | Admin | Masterdata View | 0.9.5 - Additional | UI: As the MOSIP Administrator, I should be able to view list of any Masterdata Type | MOS-23613 |  | Vital | P1 | Development completed | MOS Sprint 14 |  | 5.2
426 | Admin | Masterdata View | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to view Masterdata | MOS-23612 |  | Vital | P1 | Development completed | MOS Sprint 12 |  | 6.5
427 | Admin | Mobile Number Validation | Additional | API: As the MOSIP Admin Application, I should be able to validate if a Mobile Number is registered in User Database | MOS-23897 |  | Desirable | P2 |  |  |  | 3.25 | [9 empty] | Key Cloak Feature
428 | Admin | Navigation | 0.9.5 - Additional | UI: As the MOSIP Administrator, I should be able to view profile management functionalities under Profile Management Option | MOS-25362 |  | Vital | P1 | Development completed | MOS Sprint 14 |  | 5.2 | [9 empty] | Key Cloak Feature
429 | Admin | Navigation | 0.9.5 - Additional | UI: As the MOSIP Administrator, I should have a left Navigation menu with options to access required functionalities | MOS-25363 |  | Vital | P1 | Development completed | MOS Sprint 14 |  | 3.9
430 | Admin | Machine Update | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to update a Machine_Part 2 | MOS-24947 |  | Vital | P1 | Development In-Progress | MOS Sprint 15 |  | 3.9 | [11 empty] | P1 | Small
431 | Admin | Location Create | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to create a Location_Part2 | MOS-24833 |  | Vital | P1 | Development completed | MOS Sprint 13 |  | 5.2
432 | Admin | Requirement Detailing | 0.9.5 - Additional | Requirements detailing for "Admin" - API stories | MOS-24172 |  | Vital | P1 | Development completed | MOS Sprint 13 |  | 11
433 | Admin | Reset Password | Additional | UI: As the MOSIP Administrator, I should be able to reset my User Password | MOS-23689 |  | Desirable | P2 |  |  |  | 3.9 | [9 empty] | Key Cloak Feature
434 | Admin | Reset Password | Additional | API: As the MOSIP Admin Application, I should enable functionality to reset User Password | MOS-23688 |  | Desirable | P2 |  |  |  | 5.2 | [9 empty] | Key Cloak Feature
435 | Admin | Sort/Filter/Search | 0.9.5 - Additional | UI: As the MOSIP Administrator, I should be able to Sort/Filter/Search on a column when in a List view page on Admin Portal | MOS-25367 |  | Vital | P1 | Development completed | MOS Sprint 13 |  | 7.8
436 | Admin | Tech Story | 0.9.5 - Additional | Tech Story - Setup LDAP | MOS-25625 |  | Vital | P1 | Development completed | MOS Sprint FIT 5 |  | 2.6
437 | Admin | Tech Story | 0.9.5 - Additional | Tech Story - Create Jenkins Pipeline | MOS-25626 |  | Vital | P1 | Development completed | MOS Sprint FIT 5 |  | 5.2
438 | Admin | Tech Story | 0.9.5 - Additional | Tech Story - Create a separate environment for Admin | MOS-25627 |  | Vital | P1 | Development completed | MOS Sprint FIT 5 |  | 5.2
439 | Admin | Tech Story | 0.9.5 - Additional | Tech Story - Restructure UI Project Structure | MOS-25628 |  | Vital | P1 | Development completed | MOS Sprint FIT 5 |  | 2.6
440 | Admin | UIN Activation/Deactivation | Additional | UI: As the MOSIP Administrator, I should be able to Deactivate/Activate a UIN | MOS-23694 |  | Desirable | P2 |  |  |  | 5.2
441 | Admin | UIN Activation/Deactivation | Additional | API: As the MOSIP Admin Application, I should enable functionality to Deactivate/Activate a UIN | MOS-23693 |  | Desirable | P2 |  |  |  | 9.1
442 | Admin | UIN Activation/Deactivation | Additional | UI: As the MOSIP Administrator, I should be able to Activate and Deactivate a MOSIP Administrator | MOS-23683 |  | Desirable | P2 |  |  |  | 2.6 | [9 empty] | Key Cloak Feature
443 | Admin | User Blacklist | Additional | UI: As the MOSIP Administrator, I should be able to Blacklist and Whitelist a MOSIP Administrator | MOS-23687 |  | Desirable | P2 |  |  |  | 3.9 | [9 empty] | Key Cloak Feature
444 | Admin | User Creation | 0.9.5 - Additional | Tech Story - Modify code for Ldap | MOS-24834 |  | Vital | P1 | Development completed | MOS Sprint FIT 5 |  | 3.9
445 | Admin | User Creation | Additional | API: As the MOSIP Admin Application, I should enable functionality to Add Password and RID against a Username | MOS-24723 |  | Desirable | P2 |  |  |  | 2.6
446 | Admin | User Creation | 0.9.5 - Additional | Tech Story - API - Change the existing Auth (LDAP) code | MOS-24722 |  | Vital | P1 | Development completed | MOS Sprint 12 |  | 5.2
447 | Admin | User Creation | Additional | UI: As the potential MOSIP Administrator, I should be able to complete my Registration into MOSIP | MOS-23681 |  | Desirable | P2 |  |  |  | 2.6 | [9 empty] | Key Cloak Feature
448 | Admin | User Creation | Additional | UI: As the MOSIP Administrator, I should be able create a MOSIP Administrator | MOS-23679 |  | Desirable | P2 |  |  |  | 5.2 | [9 empty] | Key Cloak Feature
449 | Admin | User Creation | Additional | API: As the MOSIP Admin Application, I should enable functionality to create a MOSIP User | MOS-23678 |  | Desirable | P2 |  |  |  | 6.5 | [9 empty] | Key Cloak Feature
450 | Admin | User List View | Additional | UI: As the MOSIP Administrator, I should be able to view list of Users | MOS-23615 |  | Desirable | P2 |  |  |  | 2.6 | [9 empty] | Key Cloak Feature
451 | Admin | User List View | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to view list of Users | MOS-23614 |  | Vital | P1 | Development completed | MOS Sprint 12 |  | 2.6
452 | Admin | User Update | Additional | UI: As the MOSIP Administrator, I should be able to edit a User Details | MOS-23682 |  | Desirable | P2 |  |  |  | 3.9 | [9 empty] | Key Cloak Feature
453 | Admin | User View | Additional | UI: As the MOSIP Administrator, I should be able to view complete details of a User | MOS-23786 |  | Desirable | P2 |  |  |  | 2.6
454 | Admin | Username Validation | Additional | API: As the MOSIP Admin Application, I should be able to validate if a Username is registered in User Database | MOS-23898 |  | Desirable | P2 |  |  |  | 2.6
455 | Admin | Validate ID Schema | Additional | API: As the MOSIP Admin Application, I should be able to validate the ID Schema | MOS-23790 |  | Desirable | P2 |  |  |  | 7.8
456 | Admin | Validate Process Flow Config | Additional | API: As the MOSIP Admin Application, I should be able to validate Document Upload rule in Process Flow Configurations | MOS-23692 |  | Desirable | P2 |  |  |  | 5.2
457 | Admin | View Packet Status | Additional | UI: As the MOSIP Administrator, I should be able to check UIN Generation status against a given RID | MOS-23696 |  | Desirable | P2 |  |  |  | 5.2
458 | Admin | View Packet Status | Additional | API: As the MOSIP Admin Application, I should enable functionality to check UIN Generation status against a given RID | MOS-23695 |  | Desirable | P2 |  |  |  | 6.5
459 | Admin | Document Category-Type Mapping View | 0.9.5 - Additional | API: Implementation for Document Category-Type Mapping Search | MOS-26636 |  | Vital | P1 | Development completed | MOS Sprint FIT 5 |  | 5.2
460 | Admin | Titles View | 0.9.5 - Additional | API: Implementation for Titles Search | MOS-26173 |  | Vital | P1 | Development completed | MOS Sprint FIT 5 |  | 3.9
461 | Admin | Templates View | 0.9.5 - Additional | API: Implementation for Templates Search | MOS-26172 |  | Vital | P1 | Development completed | MOS Sprint FIT 5 |  | 3.9
462 | Admin | Location Data View | 0.9.5 - Additional | API: Implementation for Location Data Search | MOS-26171 |  | Vital | P1 | Development completed | MOS Sprint FIT 5 |  | 5.2
463 | Admin | Holidays View | 0.9.5 - Additional | API: Implementation for Holidays Search | MOS-26170 |  | Vital | P1 | Development completed | MOS Sprint FIT 5 |  | 3.9
464 | Admin | Individual Types View | 0.9.5 - Additional | API: Implementation for Individual Types Search | MOS-26169 |  | Vital | P1 | Development completed | MOS Sprint FIT 5 |  | 3.9
465 | Admin | Genders View | 0.9.5 - Additional | API: Implementation for Genders Search | MOS-26168 |  | Vital | P1 | Development completed | MOS Sprint FIT 5 |  | 3.9
466 | Admin | Document Types View | 0.9.5 - Additional | API: Implementation for Document Types Search | MOS-26167 |  | Vital | P1 | Development completed | MOS Sprint FIT 5 |  | 5.2
467 | Admin | Document Category View | 0.9.5 - Additional | API: Implementation for Document Category Search | MOS-26166 |  | Vital | P1 | Development completed | MOS Sprint FIT 5 |  | 5.2
468 | Admin | Center Types View | 0.9.5 - Additional | API: Implementation for Center Types Search | MOS-26165 |  | Vital | P1 | Development completed | MOS Sprint FIT 5 |  | 3.9
469 | Admin | Machine Specifications View | 0.9.5 - Additional | API: Implementation for Machine Specifications Search | MOS-26164 |  | Vital | P1 | Development completed | MOS Sprint FIT 5 |  | 3.9
470 | Admin | Machine Types View | 0.9.5 - Additional | API: Implementation for Machine Types Search | MOS-26163 |  | Vital | P1 | Development completed | MOS Sprint FIT 5 |  | 5.2
471 | Admin | Device Specifications View | 0.9.5 - Additional | API: Implementation for Device Specifications Search | MOS-26162 |  | Vital | P1 | Development completed | MOS Sprint FIT 5 |  | 5.2
472 | Admin | Device Types View | 0.9.5 - Additional | API: Implementation for Device Types Search | MOS-26161 |  | Vital | P1 | Development completed | MOS Sprint FIT 5 |  | 5.2
473 | Admin | Blacklisted Word View | 0.9.5 - Additional | API: Implementation for Blacklisted Word Search | MOS-26160 |  | Vital | P1 | Development completed | MOS Sprint FIT 5 |  | 5.2
474 | Admin | Machine View | 0.9.5 - Additional | API: Implementation for Machine Search | MOS-26156 |  | Vital | P1 | Development completed | MOS Sprint FIT 5 |  | 5.2
475 | Admin | Device View | 0.9.5 - Additional | API: Implementation for Device Search | MOS-26106 |  | Vital | P1 | Development completed | MOS Sprint FIT 5 |  | 5.2
476 | Admin | Search Utility | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should be able to support Look Ahead filter and Wildcard search | MOS-25831 |  | Vital | P1 | Development completed | MOS Sprint FIT 5 |  | 6.5
477 | Admin | Login | 0.9.5 - Additional | UI: As the MOSIP Administration, I should be able to login into Admin Application using Key-Cloak UI by providing Username and Password | MOS-25710 |  | Vital | P1 | Development completed | MOS Sprint FIT 5 |  | 14.3
478 | Admin | Ui Template - Detail View | 0.9.5 - Additional | UI: As the MOSIP Admin Application, I should be able to provide a UI template screen for Detail view of a record for an entity in multiple languages | MOS-25705 |  | Vital | P1 | Development completed | MOS Sprint FIT 5 |  | 5.2
479 | Admin | Ui Template - List View | 0.9.5 - Additional | UI: As the MOSIP Admin Application, I should be able to provide a UI template screen for List view of entities | MOS-25703 |  | Vital | P1 | Development completed | MOS Sprint FIT 5 |  | 6.5
480 | Admin | Document Type Update | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should not allow update of a Document Type if all the mandatory data is not received in all the country supported languages | MOS-26656 |  | Vital | P1 | Development In-Progress | MOS Sprint 16 |  | 3.9 | [11 empty] | P1 | Small
481 | Admin | Document Type Create | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should not allow create of a Document Type if all the mandatory data is not received in all the country supported languages | MOS-26655 |  | Vital | P1 | Development completed | MOS Sprint 13 |  | 3.9
482 | Admin | Center Update | Additional | UI: Updation of Registration Center - Add Zone as a drop-down field and replace Stubbed values by Configurable Values | MOS-26654 |  | Desirable | P2 |  |  |  | 6.5
483 | Admin | Center Create | Additional | UI: Creation of Registration Center - Add Zone as a drop-down field and replace Stubbed values by Configurable Values | MOS-26653 |  | Desirable | P2 |  |  |  | 6.5
484 | Admin | Center Update | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should only allow updation of Registration Center belonging to the Zone of the Administrator | MOS-26652 |  | Vital | NA | Development completed | MOS Sprint 15 |  | 3.9
485 | Admin | Center Create | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable creation of Registration Center only to the Zone of the Administrator | MOS-26643 |  | Vital | P1 | Development completed | MOS Sprint 13 |  | 3.9
486 | Admin | Device Update | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to update a Device_Part 2 | MOS-26637 |  | Vital | P1 | Development In-Progress | MOS Sprint 15 |  | 3.9 | [11 empty] | P1 | Small
487 | Admin | Device Create | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to create a Device_Part 2 | MOS-26408 |  | Vital | P1 | Development In-Progress | MOS Sprint 15 |  | 3.9 | [11 empty] | P1 | Small
488 | Admin | Machine Create | 0.9.5 - Additional | API: As the MOSIP Admin Application, I should enable functionality to create a Machine_Part 2 | MOS-25719 |  | Vital | P1 | Development In-Progress | MOS Sprint 15 |  | 3.9 | [11 empty] | P1 | Small
489 | Admin | Location Clone | Additional | UI: As the MOSIP Administration, I should be able to clone a Location data so that I can create a new Location | MOS-26393 |  | Desirable | P2 |  |  |  | 3.9
490 | Admin | UIN Activation/Deactivation | Additional | UI: As the MOSIP Admin Application, I should support maker-checker process for UIN Deactivation/Activation | MOS-26392 |  | Desirable | P2 |  |  |  | 3.9 | [9 empty] | More Clarification Needed
491 | Admin | Center-Device View | Additional | UI: As the MOSIP Administrator, I should be able to view list of all Devices from the List of Registration Centers | MOS-25640 |  | Desirable | P2 |  |  |  | 3.9
492 | Admin | Center-Machine View | Additional | UI: As the MOSIP Administrator, I should be able to view list of all Machines from the List of Registration Centers | MOS-25639 |  | Desirable | P2 |  |  |  | 3.9
493 | Admin | Ui Template - Detail View | Additional | UI: As the MOSIP Admin Application, I should be able to provide a UI template screen for Detail view of a record for an entity in Single language | MOS-25709 |  | Desirable | P2 |  |  |  | 0
494 | Admin | Masterdata Detail View | 0.9.5 - Additional | UI: As the MOSIP Administrator, I should be able to view complete details of a particular entity for any Masterdata Types | MOS-23784 |  | Vital | P1 | Development completed | MOS Sprint 13 |  | 18.2
495 | Admin | Masterdata List View | 0.9.5 - Additional | UI: As the MOSIP Administrator, I should be able to view list of any Masterdata Type | MOS-23623 |  | Vital | P1 | Development completed | MOS Sprint 13 |  | 6.5
496 | Admin | Machine List View | 0.9.5 - Additional | API: Update Implementation for Machine Search API | MOS-27021 |  | Vital | P1 | Development completed | MOS Sprint 13 |  | 2.6
497 | Admin | Device List View | 0.9.5 - Additional | API: Update Implementation for Devices Search API | MOS-27022 |  | Vital | P1 | Development completed | MOS Sprint 13 |  | 2.6
498 | Admin | Center List View | 0.9.5 - Additional | API: Update Implementation for Registration Center Search API | MOS-27020 |  | Vital | P1 | Development completed | MOS Sprint 13 |  | 5.2
499 | Admin | Capture User Zone | 0.9.5 - Additional | API: Implement Utility to capture zone for a User | MOS-27017 |  | Vital | P1 | Development completed | MOS Sprint 13 |  | 3.9
500 | Admin | List view Filter | 0.9.5 - Additional | API: Support search by a "Text" value in the Filter API | MOS-27019 |  | Vital | P1 | Development completed | MOS Sprint 13 |  | 2.6
501 | Admin | Device Provider Management | 0.9.5 - Additional | API: Implementation of Device Provider Management | MOS-27315 |  | Desirable | P2 | Internal Analysis Pending | TBD | [11 empty] | Yet to be analyzed for estimates
502 | Admin | Device Registration | 0.9.5 - Additional | API: Implement Device Register/De-register API | MOS-27941 | API: Implement Device Register/De-register API | Vital | P1 | Development In-Progress | MOS Sprint 15 |  | 6.5 | [11 empty] | P1 | Small
503 | Admin | Documentation | 0.9.5 - Documentation | Documentation for Real Biometrics Release |  | Covers documentation for all features released as part of Real biometrics release | Vital | P1 | Not started |  | 7 | [12 empty] | P1 | Small
504 | Resident Services | Reference UI portal for resident services | Additional | Reference UI portal for resident services |  |  | Desirable | P2 |  |  |  |  | Community contribution
505 | Resident Services | Mosip Resident Services - Reference App | Additional | Mosip Resident Services - Reference App |  |  | Desirable | P2
506 | Resident Services | Address Validation Letter | Additional | Non-MVP: Address Validation Letter | MOS-24702 | Address Validation Letter is letter which is sent to the Address Verifier’s address. The letter will contain a secret code sent for validation after the Address Verifier consents to the use of his/her address by the requesting resident. | Desirable | P2 | Not started
507 | Resident Services | Authentication with non-registered mobile | Additional | Non-MVP: Service to authenticate with non registered mobile number on which the OTP can be received | MOS-24701 | Resident Service should be able to validate a user on a different mobile number other than the registered mobile number. | Desirable | P2 | Not started
508 | Resident Services | Weak Mobile Identification | Additional | Non-MVP: Weak Mobile Identification | MOS-25624 | Resident Service should be able to call an API which can determine if a mobile number as weak based on multiple associations to UIN's for that mobile number. | Desirable | P2 | Not started
509 | Resident Services | Retrieve VID | Additional | Non-MVP: Retrieve VID | MOS-25600 | An individual should have the provision to retrieve the existing valid Virtual Identity for the resident by taking PIN and OTP as input. | Desirable | P2 | Not started
510 | Resident Services | Track UIN Reprint Status | Additional | Non-MVP: Track UIN Reprint Status: As the MOSIP system, I should be able to process a Reprint UIN Status check request | MOS-26651 | An individual can track the status of Reprint UIN by providing a Request ID(RID). | Desirable | P2 | Not started
511 | Resident Services | VID Revocation notification story | Additional | Non-MVP: VID Revocation notification story As the MOSIP system, I should be able to notify a user for automatic generation of a new VID in case of auto revocation of existing VID | MOS-27145 | An individual should be notified if his/her VID gets auto revoked due to an event and also notified about the new VID generated due to auto-revocation event. | Desirable | P2 | Not started
512 | Resident Services | View Auth History | Additional | As the MOSIP system, I should be able to process a request to view Authentication requests history for a specific UIN/VID | MOS-23863 | An individual can view authentication- requests history for a specific UIN/VID. The system will fetch unarchived data and show it in a paginated format to user. | Vital | P1 | Not started |  |  | 6 | [9 empty] | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
513 | Resident Services | Download e-UIN | Additional | As the MOSIP system, I should be able to enable download of e-UIN | MOS-23862 | An individual can raise a request to download his/her e-UIN by providing the UIN/VID, full name, postal code, and security code. | Vital | P1 | Not started |  |  | 6 | [9 empty] | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
514 | Resident Services | Track UIN Generation Status | Additional | As the MOSIP system, I should be able to process UIN Generation status check request | MOS-23861 | An individual can track the stats of UIN generation by providing a Registration ID(RID). | Vital | P1 | Not started |  |  | 6 | [9 empty] | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
515 | Resident Services | Track UIN Update Request | Additional | As the MOSIP system, I should be able to process a UIN Update Status check request | MOS-23860 | An individual can track the status related to UIN updates based on a registration ID.An individual provides the Registration ID for which he/she wants to track the status of UIN updates. | Vital | P1 | Not started |  |  | 6 | [9 empty] | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
516 | Resident Services | UIN Update | Additional | As the MOSIP system, I should be able to process a UIN Update request | MOS-23859 | MOSIP allows an individual to process a request to update the demographic data of the UIN. An individual provides the UIN/VID for which he/she wants to update. | Desirable | P2 | Not started |  |  | 6 | [9 empty] | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
517 | Resident Services | Retrieve Lost UIN | Additional | As the MOSIP system, I should be able to process a request to retrieve lost UIN | MOS-23858 | MOSIP allows an individual to initiate a request to retrieve the Registration ID by providing the Full Name, Mobile Number/E-Mail ID, Postal Code | Desirable | P2 | Not started |  |  | 6 | [9 empty] | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
518 | Resident Services | Retrieve Lost RID | Additional | As the MOSIP system, I should be able to process a request to retrieve lost RID | MOS-23856 | An individual can retrieve the RID by providing the Full Name, Mobile Number/E-Mail ID, Postal Code. | Desirable | P2 | Not started |  |  | 6 | [9 empty] | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
519 | Resident Services | Reprint UIN | Additional | As the MOSIP system, I should be able to process a request to re-print UIN | MOS-23746 | MOSIP allows an individual to raise a reprint request for their UIN. The individual provides the UIN/VID for which he/she wants to reprint. | Vital | P1 | Not started |  |  | 6 | [9 empty] | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
520 | Resident Services | Unlock AUTH | Additional | As the MOSIP system, I should be able to process a request to unlock UIN/VID for a specific authentication type | MOS-23745 | MOSIP allows an individual to unlock the authentication type(s) (Demographic, Biometrics (FP/Iris/Face/All)) associated with the UIN/VID. Only the unlocked authentication type(s) of demographic and biometric (FP/Iris/Face/All) can be used for any required authentication purpose | Vital | P1 | Not started |  |  | 6 | [9 empty] | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
521 | Resident Services | Lock AUTH | Additional | As the MOSIP system, I should be able to process a request to lock UIN/VID for a specific authentication type | MOS-23744 | MOSIP allows an individual to lock the authentication type(s) (Demographic, Biometrics (FP/Iris/Face/All)) associated with the UIN/VID. Only the locked authentication type(s) cannot be used for any authentication purpose | Vital | P1 | Not started |  |  | 6 | [9 empty] | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
522 | Resident Services | Generate VID | Additional | As a system, I should be able to generate VID for a user who requests for it so that he/she may be able to mask his/her UIN using the VID | MOS-25580 | Upon receiving a VID generation and storage request with the parameters: UIN, ver, requestTime, vidType, the system performs steps to create VID in the defined policy. | Vital | P1 | Not started |  |  | 6 | [9 empty] | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
523 | Resident Services | Revoke VID | Additional | As a system, I should be able to revoke a VID for a user who requests for it | MOS-25583 | Upon receiving a request with the parameter: VID, ver to revoke a VID based on the type, the system performs steps to revoke a VID based on the type. | Vital | P1 | Not started |  |  | 6 | [9 empty] | Considered only Resident Services and not RegProc or IDA or IDRepo. Effort includes the manual testing effort
524 | Resident Services | Documentation | Additional | Documentation coverage |  | Covers documentation for all features released as part of the released version | Vital | P1 | Not started
525 | Partner Management | Digital Certificate Signing/Resigning | Additional | As the MOSIP system, I should be able to Validate and Re-Issue the Digital Certificate provided by a Partner | MOS-24500 |  | Vital | P1 | Not started |  |  | 10.4 | [9 empty] | Sharing the Digital Certificate to Partners and Partners Uploading their certificates
526 | Partner Management | Digital Certificate Signing/Resigning | Additional | As the MOSIP system - PM, I should be able to integrate with kernel for Partner Certificate signing and resigning | MOS-24068 |  | Vital | P1 | Not started |  |  | 9.1
527 | Partner Management | ID/Key Generation and Validation | Additional | Tech Story - Integrate with kernel for MISP License Key Generation | MOS-24069 |  | Vital | P1 | Not started |  |  | 6.5 | [9 empty] | Kernel to encrypt/De-crypt MISP LK
528 | Partner Management | ID/Key Generation and Validation | Additional | As the MOSIP system I should be able to validate Partner api key pattern | MOS-26025 |  | Vital | P1 | Not started |  |  | 6.5 | [9 empty] | Kernel to validate paatern, encryption and decryption
529 | Partner Management | ID/Key Generation and Validation | Additional | As the MOSIP system, I should be able to generate Partner api key | MOS-26024 |  | Vital | P1 | Not started |  |  | 6.5
530 | Partner Management | ID/Key Generation and Validation | Additional | As the MOSIP system , I should be able to generate Partner Manager ID | MOS-26023 |  | Vital | P1 | Not started |  |  | 6.5
531 | Partner Management | ID/Key Generation and Validation | Additional | As the MOSIP system, I should be able to generate Policy Manager ID | MOS-26022 |  | Vital | P1 | Not started |  |  | 6.5
532 | Partner Management | ID/Key Generation and Validation | Additional | As the MOSIP system, I should be able to generate MISP ID | MOS-26021 |  | Vital | P1 | Not started |  |  | 6.5
533 | Partner Management | ID/Key Generation and Validation | Additional | As the MOSIP system- PM, I should be able to integrate with kernel to integrate kernel dependencies [To be deleted] | MOS-24504 |  | Vital | P1 | Not started |  |  | 0
534 | Partner Management | ID/Key Generation and Validation | Additional | As the MOSIP system , I should be able to accomodate key Management related features - key Generation, key Validation and Key Re-generation | MOS-24072 |  | Vital | P1 | Not started |  |  | 7.8
535 | Partner Management | ID/Key Generation and Validation | Additional | As the MOSIP system, I should be able to validate MISP License Key Pattern | MOS-24071 |  | Vital | P1 | Not started |  |  | 5.85
536 | Partner Management | ID/Key Generation and Validation | Additional | Tech Story - Integrate with kernel for MISP ID Generation [To be deleted] | MOS-24070 |  | Vital | P1 | Not started |  |  | 5.2 | [9 empty] | Now a part of Partner Mgmt
537 | Partner Management | ID/Key Generation and Validation | Additional | As the MOSIP system, I should be able to validate Partner ID pattern | MOS-24067 |  | Vital | P1 | Not started |  |  | 6.5 | [9 empty] | Now a part of Partner Mgmt
538 | Partner Management | ID/Key Generation and Validation | Additional | As the MOSIP system, I should be able to generate Partner ID | MOS-24066 |  | Vital | P1 | Not started |  |  | 6.5 | [9 empty] | Now a part of Partner Mgmt
539 | Partner Management | Integration with IDA for PM | Additional | As the MOSIP system- PM, I should be able to integrate with IDA to provide IDA requested services | MOS-24503 |  | Vital | P1 | Not started |  |  | 7.8
540 | Partner Management | Master Data Management | Additional | As the MOSIP system, I should be able to define the master data for PM services | MOS-24481 |  | Vital | P1 | Not started |  |  | 11.7
541 | Partner Management | MISP Self-Service | Additional | As the MOSIP system, I should be able to regenerate license keys | MOS-24479 |  | Vital | P1 | Not started |  |  | 7.8
542 | Partner Management | NFR | Additional | As the MOSIP system - PM, I should be able to implement the NFR requirements | MOS-24505 |  | Essential | P2 | Not started |  |  | 33.8 | [9 empty] | This would cover Logging, Tracing, Performance, Load, Availability, Security, Config
543 | Partner Management | Partner API key Issuance/Management | Additional | As the partner Manager, I should be able to update Partner api key to Policy Mappings | MOS-26026 |  | Vital | P1 | Not started |  |  | 6.5
544 | Partner Management | Partner API key Issuance/Management | Additional | As the Partner Manager, I should be able to activate/deactivate Partner api key based on 'policy group' | MOS-26020 |  | Vital | P1 | Not started |  |  | 6.5
545 | Partner Management | Partner API key Issuance/Management | Additional | As the Partner Manager, I should be able to approve/reject Partner api key requests based on 'policy group' | MOS-26019 |  | Vital | P1 | Not started |  |  | 6.5
546 | Partner Management | Partner API key Issuance/Management | Additional | As the Partner Manager, I should be able to view Partner api key requests based on 'policy group' | MOS-26018 |  | Vital | P1 | Not started |  |  | 5.85
547 | Partner Management | Partner API key Issuance/Management | Additional | As the Partner Manger, I should be able to retrieve Partner API key to Policy Mappings | MOS-24492 |  | Vital | P1 | Not started |  |  | 6.5
548 | Partner Management | Partner API key Issuance/Management | Additional | As the Partner Manager, I should be able to Create Partner API key to Policy Mappings | MOS-24491 |  | Vital | P1 | Not started |  |  | 6.5
549 | Partner Management | Partner Authentication | Additional | As the MOSIP system, I should be able to check status of a Partner | MOS-24490 |  | Vital | P1 | Not started |  |  | 6.5
550 | Partner Management | Partner Authentication | Additional | As the MOSIP system - IDA, I should be able to retrive policy of a partner with partner-ID and partner api key | MOS-24478 |  | Vital | P1 | Not started |  |  | 7.8
551 | Partner Management | Partner Management | Additional | As the Partner Manager, I should be able to view Auth/E-KYC Partners | MOS-26017 |  | Vital | P1 | Not started |  |  | 6.5
552 | Partner Management | Partner Management | Additional | As the Partner Manager, I should be able to deactivate Auth/E-KYC Partners | MOS-24489 |  | Vital | P1 | Not started |  |  | 6.5
553 | Partner Management | Partner Self-Service | Additional | As the Partners, I should be able to View Partner api key request status | MOS-26016 |  | Vital | P1 | Not started |  |  | 6.5
554 | Partner Management | Partner Self-Service | Additional | As the Partners, I should be able to submit Partner api key request | MOS-26015 |  | Vital | P1 | Not started |  |  | 6.5
555 | Partner Management | Partner Self-Service | Additional | As the Partners, I should be able to update Auth/E-KYC Partners | MOS-24488 |  | Vital | P1 | Not started |  |  | 6.5
556 | Partner Management | Partner Self-Service | Additional | As the Partners, I should be able to retrieve Auth/E-KYC Partners | MOS-24487 |  | Vital | P1 | Not started |  |  | 6.5
557 | Partner Management | Partner Self-Service | Additional | As the Partners, I should be able to Create Auth/E-KYC Partners | MOS-24486 |  | Vital | P1 | Not started |  |  | 6.5
558 | Partner Management | Policy Management | Additional | As the MOSIP system, I should be able to deactivate Auth/E-KYC Policy | MOS-26014 |  | Vital | P1 | Not started |  |  | 7.8
559 | Partner Management | Policy Management | Additional | As the MOSIP system, I should be able to update Auth/E-KYC Policy | MOS-26013 |  | Vital | P1 | Not started |  |  | 7.8
560 | Partner Management | Policy Management | Additional | As the Policy Manger, I should be able to retrieve Auth/E-KYC Policy | MOS-24483 |  | Vital | P1 | Not started |  |  | 5.2
561 | Partner Management | Policy Management | Additional | As the Policy Manager, I should be able to Create Auth/E-KYC Policy | MOS-24482 |  | Vital | P1 | Not started |  |  | 6.5
562 | Partner Management | Public Key Management | Additional | As the MOSIP system, I should be able to retrieve Public key from Partners for encryption of e-kyc response | MOS-24502 |  | Vital | P1 | Not started |  |  | 7.8
563 | Partner Management | Public Key Management | Additional | As the MOSIP system, I should be able to distribute Public Key to Partners for Encryption of auth/KYC Request | MOS-24501 |  | Vital | P1 | Not started |  |  | 7.8
564 | Partner Management | Role Management | Additional | Tech Story - integrate with Kernel (IAM) for Role Mangement for PM services | MOS-24473 |  | Vital | P1 | Not started |  |  | 10.4
565 | Partner Management | User Management - Admin | Additional | As the MOSIP Admin, I should be able to deactivate Partner Managers | MOS-26012 |  | Vital | P1 | Not started |  |  | 6.5
566 | Partner Management | User Management - Admin | Additional | As the MOSIP Admin, I should be able to update Partner Managers | MOS-26011 |  | Vital | P1 | Not started |  |  | 6.5
567 | Partner Management | User Management - Admin | Additional | As the MOSIP Admin, I should be able to retrieve Partner Managers | MOS-26010 |  | Vital | P1 | Not started |  |  | 6.5
568 | Partner Management | User Management - Admin | Additional | As the MOSIP Admin, I should be able to Create Partner Managers | MOS-26009 |  | Vital | P1 | Not started |  |  | 0 | [9 empty] | Part of IAM
569 | Partner Management | User Management - Admin | Additional | As the MOSIP Admin, I should be able to deactivate Policy Managers | MOS-26008 |  | Vital | P1 | Not started |  |  | 7.8
570 | Partner Management | User Management - Admin | Additional | As the MOSIP Admin, I should be able to update Policy Manager | MOS-26007 |  | Vital | P1 | Not started |  |  | 7.8
571 | Partner Management | User Management - Admin | Additional | As the MOSIP Admin, I should be able to retrieve Policy Managers | MOS-26005 |  | Vital | P1 | Not started |  |  | 6.5
572 | Partner Management | User Management - Admin | Additional | As the MOSIP Admin, I should be able to Create Policy Managers | MOS-26003 |  | Vital | P1 | Not started |  |  | 0 | [9 empty] | Part of IAM
573 | Partner Management | User Management - Admin | Additional | As the MOSIP Admin, I should be able to deactivate/suspend MISPs (update MISP License Key Status) | MOS-24477 |  | Vital | P1 | Not started |  |  | 9.1
574 | Partner Management | User Management - Admin | Additional | As the MOSIP Admin, I should be able to update MISPs | MOS-24476 |  | Vital | P1 | Not started |  |  | 7.8
575 | Partner Management | User Management - Admin | Additional | As the MOSIP Admin, I should be able to retrieve MISPs | MOS-24475 |  | Vital | P1 | Not started |  |  | 5.85
576 | Partner Management | User Management - Admin | Additional | As the MOSIP Admin, I should be able to Create MISPs (MOSIP Infrastructure Service Provider) | MOS-24474 |  | Vital | P1 | Not started |  |  | 6.5
577 | Partner Management | Documentation | Additional | Documentation coverage |  | Covers documentation for all features released as part of the released version | Vital | P1 | Not started
578 | BI |  | Additional |  |  |  | Desirable | P2
579 | General |  | Additional |  |  |  | Desirable | P2
[7 empty] | Total PDs: |  |  |  |  | 4806.45
Note on G200: Gurpreet: This is already available, need more information on this.
Note on G224: Gurpreet: This is a cross-cutting feature, Core-team can provide estimate on this. Please add in consolidated sheet